## Sheet1
DSF Project | Status | Domain | Sub-Domain | Flow | Plan Work | Replan Work | Closed Work | Planned FNI Nodes | FNIs Completed | Planned SNI Nodes | SNIs Completed | Plan Start | Replan Start | Actual Start | Plan End | Replan End | Actual End | Plan Days | Sum of Replan Days | Plan Hrs | Replan Hrs | Logged Hrs | EAC Hrs | Efficiency At EAC | Work Progress | Time Progress | Effort Progress | RAG | RAG Reason
DSFFLOW-245 | In Progress | Network Management | Element Management & Reporting | Upgrade, Maiden Installation | 869 | 573 | 36 | 1 | 0% | 28 | 4% | May 15 2025 | Apr 07 2025 |  | Oct 01 2025 | Oct 01 2025 |  | 139 | 177 | 24189 | 17322 | 11151 | 16314 | 6% | 6% | 76% | 64% | Red | [In Prog] efforts burnt outweighing work output; projecting 1%+ EAC effort overrun ; work progress misaligned with time progress;
DSFFLOW-760 | In Progress | BOS | D&A Mediation, Monetization Charging | Upgrade | 2546 | 2546 | 608 | 9 | 44% | 597 | 16% | Apr 08 2025 | Apr 08 2025 | May 12 2025 | Apr 20 2026 | Apr 20 2026 |  | 377 | 377 | 30976.4 | 30976.4 | 8298.6617 | 29533.8117 | 5% | 24% | 35% | 27% | Green | [In Prog] late start;
DSFFLOW-1840 | In Progress | Network Management | Element Management & Reporting | Upgrade | 1221 | 1221 | 521 | 2 | 0% | 75 | 33% | Jun 08 2025 | Jun 08 2025 | Jun 23 2025 | Nov 29 2025 | Nov 29 2025 |  | 174 | 174 | 17146.71 | 17146.71 | 7383.3644 | 16921.5111 | 1% | 43% | 42% | 43% | Green | [In Prog] late start;
DSFFLOW-447 | In Progress | BOS | Monetization Billing | Upgrade | 37 | 37 | 15 | 1 | 0% |  |  | Apr 01 2025 | Apr 01 2025 | May 20 2025 | Dec 05 2025 | Dec 05 2025 |  | 248 | 248 | 10676.2 | 10676.2 | 5801.8997 | 9951.2 | 7% | 41% | 57% | 54% | Green | [In Prog] late start;
DSFFLOW-741 | In Progress | Network Management | Element Management & Reporting | Upgrade | 159 | 159 | 148 | 5 | 40% |  |  | Apr 22 2025 | Apr 22 2025 | May 19 2025 | Aug 31 2025 | Aug 31 2025 |  | 131 | 131 | 4986 | 4986 | 4740.8333 | 5211.8333 | -5% | 93% | 91% | 95% | Red | [In Prog] projecting 5%+ EAC effort overrun; late start;
DSFFLOW-507 | In Progress | Network Management | Element Management & Reporting | Upgrade | 527 | 527 | 460 | 1 | 0% | 36 | 92% | Feb 28 2025 | Mar 01 2025 | Jun 26 2025 | Jul 30 2025 | Sep 30 2025 |  | 152 | 213 | 6628 | 6628 | 4524.6833 | 5137.1833 | 22% | 87% | 80% | 68% | Green | [In Prog] late start;
DSFFLOW-576 | In Progress | BOS | Monetization Billing | Upgrade | 34 | 34 | 17 | 1 | 0% |  |  | Mar 03 2025 | Mar 03 2025 | May 13 2025 | Aug 14 2025 | Oct 10 2025 |  | 164 | 221 | 8446.6 | 8446.6 | 4286.6 | 8237.3167 | 2% | 50% | 77% | 51% | Green | [In Prog] work progress misaligned with time progress; late start;
DSFFLOW-1278 | In Progress | Core Network | IMS | Migration | 353 | 341 | 139 | 9 | 0% | 17 | 0% | May 08 2025 | May 08 2025 | May 22 2025 | Sep 15 2025 | Sep 19 2025 | Sep 19 2025 | 130 | 134 | 4478.5 | 4478.5 | 2641.3458 | 4014.5758 | 10% | 41% | 100% | 59% | Green | [In Prog] work progress misaligned with time progress; late start; actual End Date exceeds Today;
DSFFLOW-2009 | In Progress | Core Network | Cloud, EPC, IMS, UDM | Upgrade | 172 | 172 | 120 | 10 | 20% | 6 | 33% | Apr 29 2025 | Apr 29 2025 | Jun 23 2025 | Mar 31 2026 | Mar 31 2026 |  | 336 | 336 | 3200 | 3200 | 2637.5 | 3011 | 6% | 70% | 34% | 82% | Amber | [In Prog] efforts burnt misaligned with work progress; efforts burnt misaligned with time progress; late start;
DSFFLOW-1416 | In Progress | Core Network, Network Management | Activation, EPC, IMS, MSS, UDM | Migration | 155 | 155 | 16 | 11 | 0% |  |  | Apr 23 2025 | Apr 23 2025 | May 27 2025 | Dec 31 2025 | Dec 31 2025 |  | 252 | 252 | 8449.25 | 8449.25 | 2600.005 | 8234.75 | 3% | 10% | 47% | 31% | Amber | [In Prog] projecting 1%+ EAC effort overrun ; late start;
DSFFLOW-2724 | In Progress | Core Network, Network Management | Cloud, Core Network Automation, EPC, IMS, MSS, Resource Orchestration, UDM | Migration | 68 | 68 | 11 | 20 | 0% | 3 | 0% | Jun 01 2025 | Jun 01 2025 | Jul 07 2025 | Sep 29 2025 | Sep 29 2025 |  | 120 | 120 | 10250 | 10250 | 2415 | 10170 | 1% | 16% | 66% | 24% | Amber | [In Prog] time ticking without any work progress; efforts burnt misaligned with work progress; late start;
DSFFLOW-2529 | In Progress | Core Network | Cloud, EPC, IMS, MSS, UDM | Maiden Installation | 15 | 15 | 4 | 5 | 0% |  |  | Jun 24 2025 | Jun 24 2025 | Jun 26 2025 | Aug 29 2025 | Aug 29 2025 |  | 66 | 66 | 2325 | 2325 | 2322 | 2318 | 0% | 27% | 85% | 100% | Red | [In Prog] efforts burning without any work progress; time ticking without any work progress;
DSFFLOW-2078 | In Progress | Core Network | EPC, IMS | Upgrade, Maiden Installation | 46 | 46 | 39 | 2 | 50% | 2 | 0% | Apr 03 2025 | Apr 03 2025 | Jun 17 2025 | Sep 06 2025 | Sep 06 2025 |  | 156 | 156 | 1930 | 1930 | 2306 | 2434 | -26% | 85% | 89% | 119% | Red | [In Prog] effort budget breached; projecting 5%+ EAC effort overrun; efforts burnt misaligned with work progress; late start;
DSFFLOW-477 | In Progress | Core Network | EPC | Upgrade, Maiden Installation | 76 | 76 | 34 | 6 | 0% |  |  | Nov 08 2024 | Nov 08 2024 | Apr 29 2025 | Feb 28 2026 | Feb 28 2026 |  | 477 | 477 | 2867.5 | 2867.5 | 2254 | 2797.5 | 2% | 45% | 60% | 79% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-206 | In Progress | Core Network | IMS | Upgrade | 214 | 196 | 80 | 7 | 0% | 14 | 0% | Feb 16 2025 | Feb 16 2025 | Apr 22 2025 | Dec 18 2025 | Dec 18 2025 | Oct 31 2025 | 305 | 305 | 3892 | 3892 | 2134.5 | 3881.6 | 0% | 41% | 84% | 55% | Green | [In Prog] late start; actual End Date exceeds Today; Delivery Manager not assigned
DSFFLOW-1629 | Closed | Core Network | EPC, UDM, Signaling | Upgrade | 175 | 175 | 175 | 21 | 100% |  |  | Apr 01 2025 | Apr 01 2025 | Jun 03 2025 | Jun 29 2025 | Jun 29 2025 | Jul 07 2025 | 89 | 89 | 2725.1292 | 2725.1292 | 2134.05 | 2134.05 | 22% | 100% | 109% | 78% | Red | [Closed] schedule overrun > 10%; efforts saved; feedback: opportunity for optimized effort baseline; late start;
DSFFLOW-2402 | In Progress | BOS | Monetization Charging | Upgrade | 169 | 169 | 24 |  |  |  |  | May 05 2025 | May 05 2025 | Jul 08 2025 | Jun 29 2026 | Jun 30 2026 |  | 420 | 421 | 18647.44 | 18647.44 | 2017.5 | 17668 | 5% | 14% | 25% | 11% | Green | [In Prog] late start;
DSFFLOW-115 | In Progress | Network Management | Element Management & Reporting | Upgrade | 192 | 181 | 81 | 7 | 29% | 3 | 100% | Mar 16 2025 | Mar 17 2025 | Mar 27 2025 | Jun 29 2025 | Aug 29 2025 |  | 105 | 165 | 3732 | 3580 | 1948 | 2722 | 24% | 45% | 94% | 54% | Green | [In Prog] late start;
DSFFLOW-1307 | In Progress | BOS | Monetization Charging | Expansion | 161 | 161 | 155 | 2 | 0% | 2 | 0% | May 11 2025 | May 11 2025 | May 11 2025 | Aug 21 2025 | Aug 21 2025 |  | 102 | 102 | 3979.5 | 3979.5 | 1943.5167 | 2756.0167 | 31% | 96% | 98% | 49% | Amber | [In Prog] efforts burnt misaligned with work progress;
DSFFLOW-1584 | In Progress | Core Network, Network Management | Activation, Core Network Automation, EPC, IMS, Resource Orchestration, UDM | Maiden Installation | 53 | 53 | 39 | 7 | 0% | 12 | 0% | May 12 2025 | May 12 2025 | May 12 2025 | Sep 15 2025 | Sep 15 2025 |  | 126 | 126 | 2633.99 | 2633.99 | 1933 | 2607.25 | 1% | 74% | 79% | 73% | Red | [In Prog] projecting 5%+ EAC effort overrun;
DSFFLOW-2123 | In Progress | Core Network, Network Management | Activation, Core Network Automation, EPC, Exposure, UDM | Maiden Installation | 81 | 81 | 18 | 7 | 0% |  |  | May 07 2025 | May 07 2025 | Jun 20 2025 | Oct 30 2026 | Oct 30 2026 |  | 541 | 541 | 5900 | 5900 | 1876 | 5735 | 3% | 22% | 19% | 32% | Green | [In Prog] late start;
DSFFLOW-3475 | In Progress | Core Network | EPC, IMS, Signaling, UDM | Upgrade | 190 | 190 | 20 | 9 | 0% | 9 | 0% | Apr 30 2025 | Apr 30 2025 | May 05 2025 | Sep 29 2025 | Sep 29 2025 |  | 152 | 152 | 3427.5 | 3427.5 | 1781.25 | 3235.5 | 6% | 11% | 73% | 52% | Amber | [In Prog] efforts burnt misaligned with work progress; work progress misaligned with time progress;
DSFFLOW-80 | Closed | Core Network | EPC, UDM, IMS | Upgrade | 176 | 150 | 150 | 10 | 100% |  |  | Feb 06 2025 | Feb 06 2025 | Mar 10 2025 | Jun 06 2025 | Jun 06 2025 | Jun 05 2025 | 120 | 120 | 1786 | 1786 | 1758 | 1758 | 2% | 100% | 99% | 98% | Green | [Closed] ahead of schedule; efforts saved; late start;
DSFFLOW-401 | Closed | Core Network | EPC | Upgrade, Expansion, Migration | 152 | 152 | 62 | 10 | 70% | 5 | 40% | Jul 10 2024 | Jul 10 2024 | Apr 30 2025 | Dec 12 2025 | Dec 12 2025 | Jun 23 2025 | 520 | 520 | 2112 | 2112 | 1746.1 | 2112 | 0% | 41% | 67% | 83% | Red | [Closed] incomplete work; ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; feedback: opportunity for optimized effort baseline; late start;
DSFFLOW-2513 | In Progress | Core Network | EPC, Signaling | Maiden Installation | 46 | 46 | 0 | 2 | 0% | 2 | 0% | Jul 25 2024 | Jul 25 2024 | Jul 24 2025 | Dec 31 2025 | Dec 31 2025 |  | 524 | 524 | 1896 | 1896 | 1584 | 1736 | 8% | 0% | 74% | 84% | Red | [In Prog] efforts burning without any work progress; time ticking without any work progress; late start;
DSFFLOW-133 | On Hold | BOS | Core Commerce | Upgrade | 423 | 423 | 165 | 4 | 50% | 17 | 12% | Mar 17 2025 | Mar 17 2025 | Apr 09 2025 | Jun 30 2025 | Aug 15 2025 |  | 105 | 151 | 3067 | 3067 | 1563.0008 | 3136.9992 | -2% | 39% | 103% | 51% | Amber | [In Prog] projecting 1%+ EAC effort overrun ; work progress misaligned with time progress; late start;
DSFFLOW-1745 | Closed | Core Network, Network Management | EPC, Exposure, Resource Orchestration, UDM | Upgrade, Expansion | 101 | 101 | 89 | 8 | 100% |  |  | Jun 04 2025 | Jun 04 2025 | Jun 06 2025 | Aug 30 2025 | Aug 30 2025 | Jul 28 2025 | 87 | 87 | 1424 | 1424 | 1432 | 1432 | -1% | 88% | 63% | 101% | Red | [Closed] incomplete work; effort budget spent; effort overrun < 1%; ahead of schedule; feedback: opportunity for optimized time plan;
DSFFLOW-4070 | In Progress | BOS | Core Commerce, D&A Mediation, Monetization Billing | Maiden Installation | 60 | 60 | 0 | 4 | 0% | 16 | 0% | Jun 06 2025 | Jun 06 2025 | Jul 31 2025 | Dec 31 2027 | Dec 31 2027 |  | 938 | 938 | 48905.4997 | 48905.4997 | 1384.75 | 48677.4997 | 0% | 0% | 8% | 3% | Green | [In Prog] late start; Delivery Manager not assigned
DSFFLOW-2047 | In Progress | Network Management | Element Management & Reporting | Upgrade | 360 | 360 | 40 | 9 | 0% | 8 | 0% | May 08 2025 | May 08 2025 | Jun 18 2025 | Aug 31 2026 | Aug 31 2026 |  | 480 | 480 | 9297 | 9297 | 1333 | 9222 | 1% | 11% | 22% | 14% | Green | [In Prog] late start;
DSFFLOW-862 | In Progress | Core Network | MSS | Upgrade | 63 | 63 | 18 | 4 | 0% | 2 | 0% | May 05 2025 | May 05 2025 | May 19 2025 | Dec 31 2025 | Dec 31 2025 |  | 240 | 240 | 2474.75 | 2474.75 | 1252.1 | 2514.75 | -2% | 29% | 44% | 51% | Red | [In Prog] projecting 5%+ EAC effort overrun; efforts burnt misaligned with work progress; late start;
DSFFLOW-151 | In Progress | Network Management | Element Management & Reporting | Upgrade | 87 | 79 | 50 | 3 | 0% |  |  | Apr 13 2025 | Apr 13 2025 | Apr 13 2025 | Jul 30 2025 | Aug 31 2025 |  | 108 | 140 | 1719 | 1637 | 1246 | 1487 | 9% | 63% | 91% | 76% | Green | [In Prog]
DSFFLOW-2384 | In Progress | Network Management | Resource Orchestration | Upgrade | 12 | 12 | 4 | 1 | 100% |  |  | Jun 16 2025 | Jun 01 2025 | Jun 24 2025 | Jun 30 2026 | Dec 31 2026 |  | 379 | 578 | 4016.25 | 4016.25 | 1236.75 | 4016.25 | 0% | 33% | 14% | 31% | Green | [In Prog] late start; Delivery Manager not assigned
DSFFLOW-1911 | In Progress | Core Network | EPC | Migration | 41 | 41 | 19 | 2 | 0% | 2 | 0% | Apr 03 2025 | Apr 03 2025 | Jun 13 2025 | Nov 30 2025 | Nov 30 2025 |  | 241 | 241 | 3433 | 3433 | 1148 | 3433 | 0% | 46% | 57% | 33% | Red | [In Prog] projecting 5%+ EAC effort overrun; late start;
DSFFLOW-1223 | Backlog | Core Network | EPC, UDM, Signaling | Expansion | 166 | 166 | 1 | 39 | 0% | 12 | 0% | May 09 2025 | May 09 2025 |  | Dec 31 2025 | Dec 31 2025 |  | 236 | 236 | 33976 | 33976 | 1129 | 33976 | 0% | 1% | 43% | 3% | Red | [Backlog] with wrong project state with work happening; efforts burning; 94 days past due start date;
DSFFLOW-3044 | In Progress | Core Network, Network Management | Activation, Signaling, UDM | Maiden Installation | 263 | 263 | 42 | 10 | 0% | 7 | 0% | Jul 09 2025 | Jul 09 2025 | Jul 15 2025 | Dec 31 2025 | Dec 31 2025 |  | 175 | 175 | 3496 | 3496 | 1105.1 | 3432 | 2% | 16% | 24% | 32% | Green | [In Prog]
DSFFLOW-1119 | In Progress | Network Management | Element Management & Reporting | Upgrade | 161 | 160 | 37 | 2 | 0% | 4 | 0% | May 15 2025 | May 21 2025 | Jun 02 2025 | Dec 31 2025 | Dec 31 2025 |  | 230 | 224 | 3306 | 3298 | 1090.5 | 2875 | 13% | 23% | 40% | 33% | Amber | [In Prog] projecting 1%+ EAC effort overrun ; late start;
DSFFLOW-64 | In Progress | Network Management | Element Management & Reporting | Upgrade | 50 | 48 | 36 | 1 | 100% | 1 | 0% | Mar 02 2025 | Mar 02 2025 | Mar 13 2025 | Aug 30 2025 | Aug 30 2025 |  | 181 | 181 | 1180.12 | 1180.12 | 1082.5097 | 1040.6197 | 12% | 75% | 94% | 92% | Green | [In Prog] late start;
DSFFLOW-677 | In Progress | Core Network | IMS | Upgrade | 101 | 101 | 67 | 6 | 33% | 10 | 10% | Apr 24 2025 | Apr 24 2025 | Apr 14 2025 | Dec 31 2025 | Dec 31 2025 | Sep 30 2025 | 251 | 251 | 1584 | 1584 | 1058 | 1504 | 5% | 66% | 63% | 67% | Green | [In Prog] early start; actual End Date exceeds Today;
DSFFLOW-993 | In Progress | Core Network | UDM | Maiden Installation | 40 | 40 | 10 | 1 | 0% | 1 | 0% | Feb 10 2025 | Feb 10 2025 | Feb 10 2025 | Dec 31 2025 | Dec 31 2025 | Dec 31 2025 | 324 | 324 | 1955 | 1955 | 1025 | 1676 | 14% | 25% | 100% | 52% | Amber | [In Prog] efforts burnt misaligned with work progress; work progress misaligned with time progress; actual End Date exceeds Today;
DSFFLOW-2882 | In Progress | BOS | D&A Mediation, Monetization Billing | Upgrade | 37 | 37 | 3 | 2 | 0% | 2 | 0% | May 10 2025 | May 10 2025 | Jul 10 2025 | Nov 18 2025 | Nov 18 2025 |  | 192 | 192 | 2844.2497 | 2844.2497 | 1011.5 | 2750.8497 | 3% | 8% | 53% | 36% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-386 | Closed | Core Network | EPC | Maiden Installation | 30 | 30 | 30 | 1 | 100% | 1 | 100% | Nov 10 2024 | Nov 10 2024 | Jan 01 2025 | Jan 26 2025 | Jan 26 2025 | Jun 30 2025 | 77 | 77 | 1773 | 1773 | 993 | 993 | 44% | 100% | 299% | 56% | Red | [Closed] schedule overrun > 10%; efforts saved; feedback: opportunity for optimized effort baseline; late start;
DSFFLOW-4140 | In Progress | Core Network | Cloud, EPC, IMS, UDM | Upgrade | 97 | 97 | 0 | 6 | 0% | 6 | 0% | Apr 16 2025 | Apr 16 2025 | Aug 01 2025 | Dec 30 2025 | Dec 30 2025 |  | 258 | 258 | 2201 | 2201 | 980 | 2105 | 4% | 0% | 49% | 45% | Amber | [In Prog] time ticking without any work progress; efforts burnt misaligned with work progress; late start;
DSFFLOW-1383 | Closed | Core Network | EPC | Upgrade | 63 | 63 | 0 | 3 | 100% | 2 | 100% | Dec 31 2024 | Dec 31 2024 | Jan 01 2025 | Jun 30 2025 | Jun 30 2025 | May 27 2025 | 181 | 181 | 952 | 952 | 952 | 942 | 1% | 0% | 81% | 100% | Red | [Closed] incomplete work; effort budget spent; ahead of schedule; feedback: opportunity for optimized time plan;
DSFFLOW-626 | Backlog | Core Network | EPC | Maiden Installation | 34 | 34 | 0 | 2 | 0% | 2 | 0% | Apr 29 2025 | Apr 29 2025 | Apr 29 2025 | Aug 31 2025 | Aug 31 2025 | Sep 15 2025 | 124 | 124 | 2496 | 2496 | 904 | 2392 | 4% | 0% | 112% | 36% | Red | [Backlog] with wrong project state with efforts burning; 104 days past due start date; actual End Date exceeds Today;
DSFFLOW-3760 | In Progress | Core Network | Signaling, UDM | Maiden Installation | 29 | 29 | 0 | 3 | 0% | 3 | 0% | Mar 31 2025 | Mar 31 2025 | Jul 29 2025 | Mar 31 2026 | Mar 31 2026 |  | 365 | 365 | 6752 | 6752 | 904 | 6752 | 0% | 0% | 39% | 13% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-2656 | In Progress | Network Management | Element Management & Reporting | Upgrade | 98 | 98 | 39 | 4 | 0% | 2 | 0% | Jul 01 2025 | Jul 01 2025 | Jul 01 2025 | Dec 19 2025 | Dec 19 2025 |  | 171 | 171 | 2840 | 2840 | 903.7333 | 2817 | 1% | 40% | 29% | 32% | Green | [In Prog]
DSFFLOW-1568 | In Progress | BOS | D&A Mediation | Upgrade | 33 | 33 | 9 | 2 | 0% | 1 | 0% | May 25 2025 | May 25 2025 | Jun 30 2025 | Aug 28 2025 | Aug 28 2025 |  | 95 | 95 | 1614.5 | 1614.5 | 886.8933 | 1634.89 | -1% | 27% | 91% | 55% | Red | [In Prog] projecting 5%+ EAC effort overrun; efforts burnt misaligned with work progress; work progress misaligned with time progress; late start;
DSFFLOW-3109 | In Progress | Core Network | IMS | Upgrade | 150 | 148 | 33 | 7 | 0% | 7 | 0% | Jul 14 2025 | Jul 14 2025 | Jul 14 2025 | Aug 29 2025 | Aug 29 2025 | Aug 29 2025 | 46 | 46 | 2101 | 2101 | 881.76 | 1939.26 | 8% | 22% | 100% | 42% | Amber | [In Prog] efforts burnt misaligned with work progress; efforts burnt misaligned with time progress; work progress misaligned with time progress; actual End Date exceeds Today;
DSFFLOW-1103 | In Progress | Core Network, Network Management | EPC, Resource Orchestration | Maiden Installation | 44 | 44 | 33 | 3 | 0% |  |  | May 16 2025 | May 16 2025 | May 19 2025 | Aug 30 2025 | Aug 30 2025 |  | 106 | 106 | 938 | 938 | 863 | 892 | 5% | 75% | 90% | 92% | Red | [In Prog] work lagging as effort nears budget; projecting 1%+ EAC effort overrun ; efforts burnt misaligned with work progress;
DSFFLOW-1713 | In Progress | Core Network | UDM | Upgrade | 18 | 18 | 2 | 2 | 0% | 2 | 0% | Mar 15 2025 | Mar 15 2025 | Jul 21 2025 | Jul 30 2025 | Jul 30 2025 |  | 137 | 137 | 2328 | 2328 | 858 | 2328 | 0% | 11% | 114% | 37% | Amber | [In Prog] efforts burnt misaligned with work progress; efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-4085 | In Progress | Core Network | Cloud | Upgrade | 206 | 206 | 11 | 1 | 0% | 30 | 0% | Jul 07 2025 | Jul 07 2025 | Aug 04 2025 | Nov 14 2025 | Nov 14 2025 |  | 130 | 130 | 7116.98 | 7116.98 | 838.59 | 7021.91 | 1% | 5% | 34% | 12% | Green | [In Prog] late start;
DSFFLOW-4778 | In Progress | Core Network | EPC, IMS, Signaling | Upgrade | 70 | 70 | 49 | 6 | 50% |  |  | Jun 22 2025 | Jun 22 2025 | Aug 14 2025 | Aug 30 2025 | Aug 30 2025 |  | 69 | 69 | 1167 | 1167 | 752 | 1030 | 12% | 70% | 84% | 64%
DSFFLOW-1322 | Backlog | Core Network | EPC, Exposure, UDM | Upgrade | 88 | 88 | 22 | 4 | 50% | 6 | 17% | Apr 22 2025 | Apr 22 2025 |  | Aug 30 2025 | Aug 30 2025 |  | 130 | 130 | 981.5 | 981.5 | 748.5 | 981.5 | 0% | 25% | 92% | 76% | Red | [Backlog] with wrong project state with work happening; efforts burning; 111 days past due start date;
DSFFLOW-1662 | In Progress | Network Management | Element Management & Reporting | Upgrade | 67 | 67 | 36 | 2 | 0% |  |  | May 07 2025 | Jul 14 2025 | Jun 06 2025 | Jul 31 2025 | Sep 15 2025 | Sep 15 2025 | 85 | 63 | 1440 | 1440 | 738 | 1355 | 6% | 54% | 100% | 51% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress; early start; actual End Date exceeds Today;
DSFFLOW-1041 | In Progress | Core Network | IMS | Maiden Installation | 17 | 13 | 13 | 4 | 100% | 5 | 100% | May 14 2025 | May 14 2025 | May 16 2025 | Apr 30 2027 | Apr 30 2027 | Jun 27 2025 | 716 | 716 | 728 | 728 | 728 | 604 | 17% | 100% | 6% | 100% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress;
DSFFLOW-611 | In Progress | Core Network | EPC | Maiden Installation | 58 | 58 | 0 | 2 | 0% | 2 | 0% | Feb 10 2025 | Feb 10 2025 | Jul 21 2025 | Dec 31 2025 | Dec 31 2025 |  | 324 | 324 | 2055 | 2055 | 727 | 1899 | 8% | 0% | 59% | 35% | Amber | [In Prog] time ticking without any work progress; efforts burnt misaligned with work progress; late start;
DSFFLOW-2482 | In Progress | Core Network | EPC | Expansion | 24 | 24 | 2 | 1 | 0% | 1 | 0% | Jun 09 2025 | Jun 09 2025 | Jun 24 2025 | Dec 12 2025 | Dec 12 2025 |  | 186 | 186 | 816 | 816 | 707 | 763 | 6% | 8% | 39% | 87% | Red | [In Prog] efforts burnt outweighing work output; projecting 1%+ EAC effort overrun ; late start;
DSFFLOW-2750 | In Progress | Core Network | IMS | Maiden Installation, Migration | 189 | 189 | 7 | 12 | 0% | 30 | 0% | Jun 24 2025 | Jun 24 2025 | Jul 09 2025 | Dec 26 2025 | Dec 26 2025 |  | 185 | 185 | 5869 | 5869 | 700.6 | 5749 | 2% | 4% | 31% | 12% | Green | [In Prog] late start;
DSFFLOW-1894 | In Progress | Core Network | EPC | Upgrade | 25 | 25 | 1 | 5 | 0% |  |  | Dec 31 2024 | Dec 31 2024 | Jun 26 2025 | Dec 30 2025 | Dec 30 2025 |  | 364 | 364 | 1584 | 1584 | 688 | 1584 | 0% | 4% | 64% | 43% | Amber | [In Prog] efforts burnt misaligned with work progress; work progress misaligned with time progress; late start;
DSFFLOW-1368 | In Progress | Core Network | EPC | Migration | 21 | 21 | 0 | 1 | 0% |  |  | May 23 2025 | May 23 2025 | Jun 25 2025 | Dec 31 2025 | Dec 31 2025 |  | 222 | 222 | 1214.8 | 1214.8 | 672.03 | 1214.8 | 0% | 0% | 40% | 55% | Red | [In Prog] efforts burning without any work progress; time ticking without any work progress; late start;
DSFFLOW-1247 | In Progress | Core Network | EPC, IMS, UDM | Upgrade | 168 | 168 | 0 | 6 | 0% | 6 | 0% | May 06 2025 | May 06 2025 | May 23 2025 | Dec 31 2025 | Dec 31 2025 |  | 239 | 239 | 2729 | 2729 | 667.25 | 2643.25 | 3% | 0% | 44% | 24% | Amber | [In Prog] time ticking without any work progress; efforts burnt misaligned with work progress; late start;
DSFFLOW-168 | Closed | BOS | Monetization Charging | Upgrade | 59 | 59 | 59 | 1 | 0% | 5 | 40% | Mar 21 2025 | Mar 18 2025 | Mar 18 2025 | Sep 03 2025 | Sep 03 2025 | Jun 13 2025 | 166 | 169 | 790.8 | 790.8 | 652.5 | 652.5 | 17% | 100% | 52% | 83% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; feedback: opportunity for optimized effort baseline;
DSFFLOW-2169 | In Progress | Core Network | EPC, Signaling, UDM | Maiden Installation | 327 | 327 | 0 | 10 | 0% | 10 | 0% | Jun 15 2025 | Jun 15 2025 | Jun 24 2025 | Aug 20 2027 | Aug 20 2027 |  | 796 | 796 | 29308.1 | 29308.1 | 630.2 | 29302.09 | 0% | 0% | 8% | 2% | Green | [In Prog] late start;
DSFFLOW-550 | Closed | Network Management | Element Management & Reporting | Upgrade | 43 | 43 | 43 |  |  | 1 | 100% | Apr 30 2025 | Apr 07 2025 | Jul 02 2025 | Feb 27 2026 | Jul 23 2025 | Jul 18 2025 | 303 | 107 | 624 | 624 | 618 | 618 | 1% | 100% | 95% | 99% | Green | [Closed] ahead of schedule; efforts saved; late start;
DSFFLOW-2107 | In Progress | Core Network | UDM, IMS | Maiden Installation | 90 | 90 | 0 | 5 | 0% | 5 | 0% | May 29 2025 | May 29 2025 | Jun 30 2025 | Feb 27 2026 | Feb 27 2026 |  | 274 | 274 | 4425.7 | 4425.7 | 606.5997 | 4382.2 | 1% | 0% | 30% | 14% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-2497 | In Progress | Core Network, Network Management | Activation, EPC, Resource Orchestration | Migration | 96 | 96 | 18 | 4 | 0% | 2 | 0% | May 29 2025 | May 29 2025 | Jun 27 2025 | Feb 27 2026 | Feb 27 2026 |  | 274 | 274 | 2112 | 2112 | 606 | 2112 | 0% | 19% | 30% | 29% | Green | [In Prog] late start;
DSFFLOW-1200 | Closed | Network Management | Element Management & Reporting | Upgrade | 192 | 35 | 35 | 2 | 100% | 2 | 100% | May 08 2025 | Feb 10 2025 | Apr 22 2025 | Aug 31 2026 | Oct 31 2025 | Jun 19 2025 | 480 | 263 | 3156 | 1055.5 | 605.5 | 605.5 | 43% | 100% | 49% | 57% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; feedback: opportunity for optimized effort baseline; late start;
DSFFLOW-1445 | Closed | Core Network | IMS | Upgrade | 78 | 59 | 59 | 3 | 0% | 3 | 0% | May 27 2025 | May 27 2025 | May 28 2025 | Jul 18 2025 | Jul 04 2025 | Jul 04 2025 | 52 | 38 | 801 | 639.5 | 600.2697 | 600.2697 | 6% | 100% | 100% | 94% | Green | [Closed] efforts saved;
DSFFLOW-1057 | In Progress | Core Network | EPC | Upgrade, Maiden Installation | 86 | 86 | 6 | 3 | 0% | 6 | 0% | May 07 2025 | May 07 2025 | May 16 2025 | Jan 30 2026 | Jan 30 2026 | Jan 30 2026 | 268 | 268 | 3893.75 | 3893.75 | 589 | 3876.75 | 0% | 7% | 100% | 15% | Amber | [In Prog] projecting 1%+ EAC effort overrun ; efforts burnt misaligned with time progress; work progress misaligned with time progress; late start; actual End Date exceeds Today;
DSFFLOW-3669 | In Progress | Core Network | EPC, IMS, Signaling, UDM | Upgrade | 226 | 226 | 0 | 9 | 0% | 9 | 0% | Jun 09 2025 | Jun 09 2025 | Jul 28 2025 | Oct 30 2025 | Oct 30 2025 |  | 143 | 143 | 4764 | 4764 | 588.75 | 4691.75 | 2% | 0% | 50% | 12% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-2249 | In Progress | BOS | Monetization Charging | Upgrade, Expansion, Maiden Installation | 396 | 396 | 11 | 10 | 0% | 10 | 0% | Jun 22 2025 | Jun 22 2025 | Jun 27 2025 | Sep 19 2025 | Sep 19 2025 |  | 89 | 89 | 3683.11 | 3683.11 | 579.73 | 3482.11 | 5% | 3% | 66% | 16% | Green | [In Prog] work progress misaligned with time progress;
DSFFLOW-97 | Closed | Network Management | Element Management & Reporting | Upgrade | 50 | 47 | 47 | 4 | 100% |  |  | Mar 12 2025 | Mar 12 2025 | Mar 13 2025 | May 31 2025 | Jul 31 2025 | Jul 15 2025 | 80 | 141 | 844 | 801.5 | 575 | 575 | 28% | 100% | 89% | 72% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; feedback: opportunity for optimized effort baseline;
DSFFLOW-3649 | Closed | Core Network | IMS | Upgrade | 31 | 31 | 12 | 3 | 0% | 9 | 0% | Jul 03 2025 | Jul 03 2025 | Jul 24 2025 | Dec 30 2025 | Dec 30 2025 | Jul 30 2025 | 180 | 180 | 2715 | 2715 | 570 | 2615 | 4% | 39% | 15% | 21% | Red | [Closed] incomplete work; ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; feedback: opportunity for optimized effort baseline; late start;
DSFFLOW-1166 | In Progress | Core Network | Cloud | Upgrade | 70 | 70 | 26 | 2 | 50% | 6 | 50% | May 19 2025 | May 19 2025 | Jun 06 2025 | Dec 30 2025 | Dec 30 2025 |  | 225 | 225 | 1196 | 1196 | 567.6 | 1159.5 | 3% | 37% | 41% | 47% | Green | [In Prog] late start;
DSFFLOW-2321 | In Progress | Core Network | Exposure | Upgrade | 51 | 51 | 23 | 1 | 0% | 1 | 0% | Jun 02 2025 | Jun 02 2025 | Jun 19 2025 | Aug 29 2025 | Aug 29 2025 |  | 88 | 88 | 881.75 | 881.75 | 558.55 | 841.75 | 5% | 45% | 89% | 63% | Green | [In Prog] late start;
DSFFLOW-1926 | In Progress | Core Network | Cloud | Maiden Installation | 97 | 97 | 0 | 3 | 0% | 6 | 0% | May 26 2025 | May 26 2025 | Jul 10 2025 | Dec 31 2026 | Dec 31 2026 |  | 584 | 584 | 2188.6 | 2188.6 | 557.6 | 2158.6 | 1% | 0% | 15% | 25% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-1135 | Closed | BOS | D&A Mediation | Upgrade | 34 | 34 | 34 | 2 | 100% |  |  | May 19 2025 | May 19 2025 | May 19 2025 | Jun 20 2025 | Jun 20 2025 | Jun 20 2025 | 32 | 32 | 569.1 | 569.1 | 548 | 548 | 4% | 100% | 100% | 96% | Green | [Closed] efforts saved;
DSFFLOW-1087 | In Progress | Network Management | Element Management & Reporting | Upgrade | 58 | 56 | 17 | 2 | 0% | 1 | 0% | May 14 2025 | May 14 2025 | May 17 2025 | Nov 29 2025 | Nov 29 2025 |  | 199 | 199 | 990 | 978 | 543.5 | 938 | 4% | 30% | 49% | 56% | Amber | [In Prog] projecting 1%+ EAC effort overrun ; efforts burnt misaligned with work progress;
DSFFLOW-1337 | In Progress | BOS | Monetization Charging | Upgrade, Expansion | 338 | 338 | 5 | 14 | 0% | 24 | 0% | Apr 14 2025 | Apr 14 2025 | May 30 2025 | Oct 30 2026 | Oct 30 2026 |  | 564 | 564 | 5063 | 5063 | 537.25 | 4853 | 4% | 1% | 23% | 11% | Green | [In Prog] late start;
DSFFLOW-2689 | In Progress | Network Management | Element Management & Reporting | Upgrade | 124 | 122 | 40 | 2 | 0% | 3 | 0% | Jun 23 2025 | Jun 23 2025 | Jul 14 2025 | Mar 31 2026 | Mar 31 2026 |  | 281 | 281 | 1759.9 | 1759.9 | 529.8997 | 1720.3997 | 2% | 33% | 21% | 30% | Green | [In Prog] late start;
DSFFLOW-3233 | In Progress | Core Network | UDM | Migration | 16 | 15 | 1 |  |  | 1 | 0% | Jul 14 2025 | Jul 14 2025 | Aug 12 2025 | Aug 15 2025 | Aug 15 2025 |  | 32 | 32 | 614 | 614 | 529 | 614 | 0% | 7% | 112% | 86% | Red | [Assigned] with wrong project state with efforts burning; 28 days past due start date;
DSFFLOW-2467 | In Progress | BOS | D&A Mediation | Upgrade | 25 | 25 | 3 | 1 | 0% |  |  | Jun 11 2025 | Jun 11 2025 | Jun 26 2025 | Nov 30 2025 | Nov 30 2025 |  | 172 | 172 | 1232.5 | 1232.5 | 528 | 1155.35 | 6% | 12% | 40% | 43% | Amber | [In Prog] projecting 1%+ EAC effort overrun ; efforts burnt misaligned with work progress; late start;
DSFFLOW-1263 | In Progress | Core Network | EPC | Maiden Installation | 36 | 36 | 6 | 2 | 0% | 2 | 0% | May 11 2025 | May 11 2025 | Jul 11 2025 | Aug 01 2025 | Aug 01 2025 |  | 82 | 82 | 871 | 871 | 527.25 | 823 | 6% | 17% | 122% | 61% | Amber | [In Prog] projecting 1%+ EAC effort overrun ; efforts burnt misaligned with work progress; efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-3396 | In Progress | BOS | Monetization Billing | Maiden Installation | 19 | 19 | 10 | 1 | 0% |  |  | Jun 15 2025 | Jun 15 2025 | Jul 28 2025 | Jul 31 2025 | Oct 10 2025 |  | 46 | 117 | 620.5 | 620.5 | 527 | 561 | 10% | 53% | 56% | 85% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-3142 | In Progress | Core Network | Cloud | Maiden Installation | 115 | 115 | 0 | 3 | 0% | 6 | 0% | Jul 06 2025 | Jul 06 2025 | Jul 15 2025 | Sep 14 2025 | Sep 14 2025 |  | 70 | 70 | 2441.85 | 2441.85 | 518 | 2403.85 | 2% | 0% | 63% | 21% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-1646 | On Hold | Network Management | Element Management & Reporting | Upgrade | 67 | 67 | 24 | 2 | 0% |  |  | May 27 2025 | Jul 21 2025 | Jun 09 2025 | Aug 29 2025 | Sep 30 2025 |  | 94 | 71 | 1440 | 1440 | 504.01 | 1424.01 | 1% | 36% | 42% | 35% | Green | [On Hold] early start;
DSFFLOW-2234 | In Progress | Network Management | Element Management & Reporting | Upgrade | 38 | 38 | 38 |  |  | 1 | 100% | Jun 17 2025 | Jun 17 2025 | Jun 30 2025 | Oct 31 2025 | Oct 31 2025 |  | 136 | 136 | 652 | 652 | 501 | 501 | 23% | 100% | 47% | 77% | Amber | [In Prog] efforts burnt misaligned with work progress; work progress misaligned with time progress; late start;
DSFFLOW-798 | In Progress | Core Network | Cloud | Maiden Installation | 77 | 77 | 0 | 11 | 0% |  |  | May 05 2025 | Apr 01 2025 | Jun 03 2025 | Dec 30 2025 | Mar 20 2026 |  | 239 | 353 | 6839 | 6839 | 487.75 | 7613.5 | -11% | 0% | 40% | 7% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-1729 | In Progress | Network Management | Element Management & Reporting | Upgrade | 67 | 64 | 24 | 2 | 0% |  |  | May 07 2025 | May 07 2025 | Jun 09 2025 | Oct 31 2025 | Oct 31 2025 |  | 177 | 177 | 1240 | 1200 | 487 | 1187 | 1% | 38% | 59% | 41% | Green | [In Prog] late start;
DSFFLOW-2858 | Closed | BOS | Monetization Charging | Upgrade | 34 | 34 | 34 | 2 | 100% | 4 | 100% | May 09 2025 | Jun 09 2025 | Jul 16 2025 | Jul 25 2025 | Jul 25 2025 | Aug 06 2025 | 77 | 46 | 486 | 486 | 486 | 486 | 0% | 100% | 126% | 100% | Red | [Closed] schedule overrun > 10%; late start;
DSFFLOW-894 | Backlog | Core Network | UDM | Upgrade | 23 | 23 | 0 | 1 | 0% | 1 | 0% | May 06 2025 | May 06 2025 |  | Dec 31 2025 | Dec 31 2025 |  | 239 | 239 | 924 | 924 | 480 | 924 | 0% | 0% | 44% | 52% | Red | [Backlog] with wrong project state with efforts burning; 97 days past due start date;
DSFFLOW-2219 | In Progress | Core Network | Cloud | Expansion | 37 | 35 | 25 | 1 | 0% | 1 | 0% | Jun 09 2025 | Jun 09 2025 | Jun 18 2025 | Dec 12 2025 | Dec 12 2025 |  | 186 | 186 | 517.35 | 502.35 | 476.35 | 498.85 | 1% | 71% | 39% | 95% | Red | [In Prog] projecting 5%+ EAC effort overrun; work lagging as effort nears budget; efforts burnt misaligned with work progress; efforts burnt misaligned with time progress; late start;
DSFFLOW-462 | In Progress | Core Network | MSS | Upgrade | 28 | 28 | 10 | 1 | 0% | 4 | 0% | Mar 17 2025 | Mar 17 2025 | Apr 30 2025 | Jun 30 2025 | Jun 30 2025 |  | 105 | 105 | 469 | 469 | 469 | 831 | -77% | 36% | 147% | 100% | Red | [Closed] incomplete work; effort budget spent; schedule overrun > 10%; late start;
DSFFLOW-1599 | In Progress | Network Management | Element Management & Reporting | Upgrade | 63 | 63 | 17 | 2 | 0% |  |  | May 15 2025 | May 15 2025 | Jun 24 2025 | Aug 29 2025 | Sep 30 2025 |  | 106 | 138 | 1102 | 1102 | 458.5 | 918.5 | 17% | 27% | 70% | 42% | Green | [In Prog] late start;
DSFFLOW-3870 | In Progress | Core Network | Cloud | Expansion | 62 | 62 | 15 | 4 | 100% | 4 | 50% | Jul 14 2025 | Jul 14 2025 | Jul 29 2025 | Dec 24 2025 | Dec 24 2025 |  | 163 | 163 | 727.94 | 727.94 | 458.2697 | 727.9397 | 0% | 24% | 23% | 63% | Amber | [In Prog] efforts burnt misaligned with work progress; efforts burnt misaligned with time progress; late start;
DSFFLOW-32 | Closed | Network Management | Element Management & Reporting | Upgrade | 57 | 31 | 31 | 2 | 100% |  |  | Dec 08 2024 | Dec 08 2024 | Dec 09 2024 | Feb 17 2025 | Feb 18 2025 | Feb 17 2025 | 71 | 72 | 910 | 459 | 457 | 457 | 0% | 100% | 99% | 100% | Green | [Closed] ahead of schedule;
DSFFLOW-952 | In Progress | Core Network | UDM | Migration | 18 | 17 | 4 |  |  | 1 | 0% | May 12 2025 | May 12 2025 | May 12 2025 | Jun 29 2025 | Jun 29 2025 |  | 48 | 48 | 542.75 | 542.75 | 446.25 | 542.75 | 0% | 24% | 204% | 82% | Red | [In Prog] efforts burnt outweighing work output; efforts burnt misaligned with time progress; work progress misaligned with time progress;
DSFFLOW-3786 | In Progress | Core Network | EPC, UDM | Maiden Installation | 29 | 29 | 0 | 3 | 0% | 3 | 0% | Mar 31 2025 | Mar 31 2025 | Jul 29 2025 | Mar 31 2026 | Mar 31 2026 |  | 365 | 365 | 10283 | 10283 | 440 | 10283 | 0% | 0% | 39% | 4% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-2593 | In Progress | Core Network | EPC | Maiden Installation | 16 | 16 | 2 | 2 | 0% | 1 | 0% | May 25 2025 | May 25 2025 | Jul 02 2025 | Dec 31 2025 | Dec 31 2025 |  | 220 | 220 | 2581 | 2581 | 439 | 2551 | 1% | 13% | 39% | 17% | Green | [In Prog] late start;
DSFFLOW-2368 | On Hold | Network Management | Activation, Resource Orchestration | Upgrade | 34 | 34 | 15 | 2 | 0% | 1 | 0% | Jun 01 2025 | Jun 01 2025 | Jun 20 2025 | Aug 31 2033 | Aug 31 2033 |  | 3013 | 3013 | 766.71 | 766.71 | 437.7 | 738.71 | 4% | 44% | 3% | 57% | Amber | [On Hold] projecting 1%+ EAC effort overrun ; efforts burnt misaligned with time progress; late start;
DSFFLOW-49 | Closed | Network Management | Element Management & Reporting | Upgrade | 30 | 30 | 30 | 1 | 100% |  |  | Feb 19 2025 | Feb 20 2025 | Feb 28 2025 | Aug 29 2025 | Apr 17 2025 | Mar 27 2025 | 191 | 56 | 488 | 488 | 430 | 430 | 12% | 100% | 63% | 88% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; feedback: opportunity for optimized effort baseline; late start;
DSFFLOW-2138 | Closed | Network Management | Resource Orchestration | Upgrade, Maiden Installation | 52 | 37 | 36 | 2 | 100% | 2 | 50% | Jun 12 2025 | Jun 12 2025 | Jun 18 2025 | Dec 31 2025 | Aug 31 2025 | Aug 14 2025 | 202 | 80 | 646.6497 | 559.9 | 412.9 | 425.65 | 24% | 97% | 79% | 74% | Amber | [In Prog] efforts burnt misaligned with work progress;
DSFFLOW-2641 | In Progress | Network Management | Element Management & Reporting | Upgrade | 24 | 24 | 9 | 1 | 0% |  |  | Jul 01 2025 | Jul 01 2025 | Jul 01 2025 | Sep 29 2025 | Sep 29 2025 |  | 90 | 90 | 850 | 850 | 405.7 | 804.8 | 5% | 38% | 55% | 48% | Red | [In Prog] projecting 5%+ EAC effort overrun;
DSFFLOW-4457 | Closed | Network Management | Element Management & Reporting | Upgrade | 38 | 14 | 14 | 2 | 100% |  |  | Aug 04 2025 | Jul 08 2025 | Aug 05 2025 | Dec 26 2025 | Sep 15 2025 | Aug 13 2025 | 144 | 69 | 946.5 | 505.5 | 405.5 | 405.5 | 20% | 100% | 53% | 80% | Green | [In Prog] late start;
DSFFLOW-3093 | In Progress | Core Network | Cloud | Expansion | 89 | 89 | 16 | 4 | 0% | 4 | 0% | Jun 04 2025 | Jun 04 2025 | Jul 15 2025 | Mar 31 2026 | Mar 31 2026 |  | 300 | 300 | 2265.5 | 2265.5 | 397 | 2223.5 | 2% | 18% | 26% | 18% | Green | [In Prog] late start;
DSFFLOW-1864 | In Progress | Network Management | Element Management & Reporting | Upgrade | 35 | 35 | 35 |  |  | 1 | 100% | Jun 09 2025 | Jun 09 2025 | Jun 18 2025 | Dec 31 2025 | Dec 31 2025 |  | 205 | 205 | 506 | 506 | 397 | 397 | 22% | 100% | 35% | 78% | Amber | [In Prog] projecting 1%+ EAC effort overrun ; work progress misaligned with time progress; late start;
DSFFLOW-4124 | In Progress | Network Management | Element Management & Reporting | Maiden Installation | 113 | 113 | 6 | 2 | 0% | 2 | 0% | Jul 31 2025 | Jul 31 2025 | Aug 04 2025 | Jan 30 2026 | Jan 30 2026 |  | 183 | 183 | 4680 | 4680 | 384 | 4664 | 0% | 5% | 11% | 8% | Green | [In Prog]
DSFFLOW-2947 | Closed | Core Network | MSS | Upgrade | 21 | 21 | 21 | 1 | 100% |  |  | Mar 18 2025 | May 08 2025 | May 08 2025 | Aug 15 2025 | Jul 15 2025 | Jul 15 2025 | 150 | 68 | 411.5 | 411.5 | 382.5 | 382.5 | 7% | 100% | 100% | 93% | Green | [Closed] efforts saved;
DSFFLOW-1400 | In Progress | Core Network | EPC | Maiden Installation | 37 | 37 | 5 | 2 | 0% | 2 | 0% | May 22 2023 | May 22 2023 | May 27 2025 | Jul 30 2025 | Jul 30 2025 |  | 800 | 800 | 1432 | 1432 | 376 | 1432 | 0% | 14% | 102% | 26% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-1008 | In Progress | Network Management | Resource Orchestration | Upgrade | 26 | 25 | 22 | 1 | 0% |  |  | Jun 16 2025 | Jun 03 2025 | Jun 18 2025 | Aug 30 2025 | Aug 30 2025 |  | 75 | 88 | 451 | 451 | 370.1 | 428 | 5% | 88% | 88% | 82% | Amber | [In Prog] projecting 1%+ EAC effort overrun ; late start;
DSFFLOW-2352 | Closed | Core Network | Signaling | Upgrade | 26 | 26 | 23 | 2 | 100% |  |  | Jun 02 2025 | Jun 02 2025 | Jun 27 2025 | Jul 04 2025 | Jul 30 2025 | Aug 05 2025 | 32 | 58 | 511 | 511 | 369 | 452 | 12% | 88% | 110% | 72% | Red | [Closed] incomplete work; schedule overrun > 10%; efforts saved; feedback: opportunity for optimized effort baseline; late start;
DSFFLOW-1151 | In Progress | BOS | Monetization Charging | Upgrade | 498 | 498 | 14 | 5 | 20% | 38 | 0% | Jun 01 2025 | Jun 01 2025 | Jun 01 2025 | Feb 28 2026 | Feb 28 2026 |  | 272 | 272 | 3023 | 3023 | 368.5 | 2963 | 2% | 3% | 29% | 12% | Green | [In Prog]
DSFFLOW-3745 | In Progress | Core Network | UDM | Migration | 15 | 14 | 0 |  |  | 1 | 0% | Jul 28 2025 | Jul 28 2025 | Aug 12 2025 | Dec 26 2025 | Dec 26 2025 |  | 151 | 151 | 2080 | 2080 | 363.5 | 2080 | 0% | 0% | 15% | 17% | Red | [Assigned] with wrong project state with efforts burning; 14 days past due start date;
DSFFLOW-1790 | In Progress | Core Network | Cloud | Upgrade | 85 | 85 | 35 | 5 | 40% | 15 | 33% | Jun 02 2025 | Jun 02 2025 | Jul 10 2025 | Mar 31 2026 | Mar 31 2026 |  | 302 | 302 | 726 | 726 | 350 | 728 | 0% | 41% | 26% | 48% | Green | [In Prog] late start;
DSFFLOW-2264 | In Progress | BOS | Monetization Charging | Upgrade, Maiden Installation | 571 | 571 | 3 | 7 | 0% | 29 | 0% | Jun 16 2025 | Jun 16 2025 | Jun 16 2025 | Feb 16 2026 | Feb 16 2026 |  | 245 | 245 | 5197.5 | 5197.5 | 341.5 | 5045 | 3% | 1% | 26% | 7% | Amber | [In Prog] time ticking without any work progress;
DSFFLOW-2828 | Assigned | Core Network | UDM | Migration | 15 | 15 | 0 |  |  | 1 | 0% | Jul 14 2025 | Jul 14 2025 |  | Nov 28 2025 | Nov 28 2025 |  | 137 | 137 | 593 | 593 | 324 | 593 | 0% | 0% | 27% | 55% | Red | [Assigned] with wrong project state with efforts burning; 28 days past due start date;
DSFFLOW-3311 | In Progress | BOS | Monetization Charging | Expansion | 415 | 415 | 50 | 2 | 0% | 4 | 0% | Jul 27 2025 | Jul 27 2025 | Jul 22 2025 | Sep 30 2025 | Sep 30 2025 |  | 65 | 65 | 3078.6 | 3078.6 | 323.75 | 3028.1 | 2% | 12% | 36% | 11% | Green | [In Prog]
DSFFLOW-2610 | In Progress | Core Network | Signaling | Upgrade | 11 | 11 | 0 | 1 | 0% |  |  | Jun 27 2025 | Jun 27 2025 | Jul 02 2025 | Dec 31 2025 | Dec 31 2025 |  | 187 | 187 | 605 | 605 | 320 | 605 | 0% | 0% | 29% | 53% | Amber | [In Prog] time ticking without any work progress; efforts burnt misaligned with work progress;
DSFFLOW-310 | Closed | Core Network | UDM | Upgrade | 19 | 19 | 19 | 1 | 100% | 1 | 100% | Apr 20 2025 | Apr 20 2025 | Jun 05 2025 | May 31 2025 | May 31 2025 | Jun 05 2025 | 41 | 41 | 267 | 267 | 315 | 315 | -18% | 100% | 112% | 118% | Red | [Closed] effort overrun > 1%; schedule overrun > 10%; late start;
DSFFLOW-662 | In Progress | Network Management | Resource Orchestration | Maiden Installation | 71 | 54 | 6 | 1 | 0% | 3 | 0% | Mar 04 2025 | Mar 04 2025 | Jun 05 2025 | Dec 31 2026 | Dec 31 2026 |  | 667 | 667 | 914.7 | 515.0667 | 312.2167 | 847.7833 | -65% | 11% | 25% | 61% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-3562 | In Progress | Core Network | Cloud | Upgrade | 23 | 23 | 2 | 2 | 0% |  |  | Jul 23 2025 | Jul 23 2025 | Jul 23 2025 | Sep 30 2025 | Sep 30 2025 |  | 69 | 69 | 844 | 844 | 312 | 872 | -3% | 9% | 40% | 37% | Amber | [In Prog] projecting 1%+ EAC effort overrun ; efforts burnt misaligned with work progress;
DSFFLOW-1697 | In Progress | Core Network | EPC | Upgrade | 30 | 21 | 20 | 2 | 50% | 2 | 100% | May 26 2025 | May 26 2025 | Jun 12 2025 | Aug 31 2025 | Aug 31 2025 |  | 97 | 97 | 346 | 346 | 310 | 310 | 10% | 95% | 88% | 90% | Green | [In Prog] late start;
DSFFLOW-3060 | In Progress | Core Network | UDM | Upgrade | 71 | 71 | 10 | 3 | 0% | 12 | 0% | Jun 25 2025 | Jun 25 2025 | Jul 16 2025 | Nov 28 2025 | Nov 28 2025 |  | 156 | 156 | 967 | 967 | 303 | 921 | 5% | 14% | 36% | 31% | Green | [In Prog] late start;
DSFFLOW-1614 | In Progress | Network Management | Resource Orchestration | Upgrade | 54 | 52 | 52 | 1 | 100% | 1 | 100% | May 28 2025 | May 28 2025 | Jun 04 2025 | Jan 30 2026 | Jan 30 2026 |  | 247 | 247 | 299.7533 | 299.7533 | 300.12 | 300.12 | 0% | 100% | 34% | 100% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress;
DSFFLOW-3498 | In Progress | Core Network | EPC, Signaling, UDM | Migration | 77 | 77 | 0 | 5 | 0% | 8 | 0% | Jun 18 2025 | Jun 18 2025 | Jul 23 2025 | Dec 31 2025 | Dec 31 2025 |  | 196 | 196 | 1514.6 | 1514.6 | 292.5 | 1457.6 | 4% | 0% | 32% | 19% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-3852 | In Progress | Core Network | Cloud | Migration | 118 | 118 | 0 | 2 | 0% | 10 | 0% | Jul 22 2025 | Jul 22 2025 | Jul 31 2025 | Dec 31 2025 | Dec 31 2025 |  | 162 | 162 | 2002.5 | 2002.5 | 288 | 2002.5 | 0% | 0% | 18% | 14% | Green | [In Prog] late start;
DSFFLOW-3342 | In Progress | Network Management | Activation, Resource Orchestration | Upgrade | 145 | 140 | 15 | 6 | 0% | 2 | 0% | Jul 10 2025 | Jul 10 2025 | Jul 10 2025 | Nov 21 2025 | Nov 21 2025 |  | 134 | 134 | 3933 | 3933 | 279.5 | 3864.5 | 2% | 11% | 30% | 7% | Amber | [In Prog] projecting 1%+ EAC effort overrun ;
DSFFLOW-3836 | In Progress | Network Management | Activation | Upgrade | 48 | 48 | 18 | 2 | 50% | 1 | 0% | May 31 2025 | May 31 2025 | Jul 30 2025 | Sep 29 2025 | Sep 29 2025 |  | 121 | 121 | 612 | 612 | 274 | 620 | -1% | 38% | 66% | 45% | Amber | [In Prog] projecting 1%+ EAC effort overrun ; late start;
DSFFLOW-1879 | Closed | Network Management | Element Management & Reporting | Maiden Installation | 25 | 14 | 14 | 1 | 100% |  |  | May 26 2025 | May 26 2025 | May 26 2025 | Jun 30 2025 | Jun 30 2025 | Jun 30 2025 | 35 | 35 | 304.5 | 298 | 268.5 | 268.5 | 10% | 100% | 100% | 90% | Green | [Closed] efforts saved;
DSFFLOW-2931 | On Hold | Network Management | Activation | Maiden Installation | 46 | 46 | 4 | 1 | 0% | 1 | 0% | Jun 08 2025 | Jun 08 2025 | Jun 09 2025 | Dec 30 2025 | Dec 30 2025 |  | 205 | 205 | 1061.25 | 1061.25 | 267.72 | 1027.07 | 3% | 9% | 35% | 25% | Green | [On Hold]
DSFFLOW-2625 | Closed | Core Network | IMS | Upgrade | 30 | 28 | 28 | 1 | 0% | 1 | 0% | Jun 29 2025 | Jun 29 2025 | Jun 30 2025 | Jul 31 2025 | Jul 25 2025 | Aug 01 2025 | 32 | 26 | 267 | 267 | 267.01 | 267.01 | 0% | 100% | 126% | 100% | Red | [Closed] schedule overrun > 10%;
DSFFLOW-340 | Closed | Core Network | UDM | Upgrade | 17 | 17 | 7 | 1 | 100% | 1 | 100% | Mar 04 2025 | Mar 04 2025 | Mar 04 2025 | Jun 30 2025 | Jun 30 2025 | Aug 11 2025 | 118 | 118 | 264 | 264 | 264 | 240 | 9% | 41% | 135% | 100% | Red | [In Prog] efforts burnt outweighing work output; work lagging as effort nears budget; work progress misaligned with time progress;
DSFFLOW-1026 | Closed | Network Management | Resource Orchestration | Upgrade | 22 | 19 | 19 | 1 | 100% | 1 | 100% | Apr 20 2025 | Apr 20 2025 | Jun 13 2025 | Jun 29 2025 | Jun 29 2025 | Jul 09 2025 | 70 | 70 | 277.75 | 260.77 | 260.77 | 260.77 | 0% | 100% | 114% | 100% | Red | [Closed] schedule overrun > 10%; late start;
DSFFLOW-3513 | In Progress | Network Management | Activation | Maiden Installation | 69 | 69 | 0 | 1 | 0% | 3 | 0% | Jul 11 2025 | Jul 11 2025 | Jul 24 2025 | Dec 26 2025 | Dec 26 2025 |  | 168 | 168 | 3075.1 | 3075.1 | 255 | 3075.1 | 0% | 0% | 24% | 8% | Green | [In Prog] late start;
DSFFLOW-2901 | In Progress | Network Management | Resource Orchestration | Maiden Installation | 34 | 33 | 13 | 1 | 0% |  |  | Jun 01 2025 | Jun 01 2025 | Jul 08 2025 | Aug 30 2025 | Aug 30 2025 |  | 90 | 90 | 777.75 | 777.75 | 248.75 | 742.75 | 5% | 39% | 88% | 32% | Amber | [In Prog] projecting 1%+ EAC effort overrun ; late start;
DSFFLOW-3458 | Closed | Core Network | Cloud | Upgrade | 18 | 18 | 14 | 1 | 100% | 1 | 100% | Jul 22 2025 | Jul 22 2025 | Jul 29 2025 | Aug 29 2025 | Aug 29 2025 | Aug 11 2025 | 38 | 38 | 242 | 242 | 242 | 242 | 0% | 78% | 54% | 100% | Amber | [In Prog] projecting 1%+ EAC effort overrun ;
DSFFLOW-3730 | In Progress | Core Network | UDM | Migration | 16 | 15 | 0 |  |  | 1 | 0% | Jul 28 2025 | Jul 28 2025 | Aug 12 2025 | Oct 31 2025 | Oct 31 2025 |  | 95 | 95 | 1283 | 1283 | 241.5 | 1283 | 0% | 0% | 24% | 19% | Red | [Assigned] with wrong project state with efforts burning; 14 days past due start date;
DSFFLOW-2813 | In Progress | Network Management | Resource Orchestration | Maiden Installation | 11 | 11 | 1 | 1 | 0% |  |  | May 04 2025 | May 04 2025 | Jul 10 2025 | Mar 31 2026 | Mar 31 2026 |  | 331 | 331 | 1125 | 1125 | 241 | 1125 | 0% | 9% | 33% | 21% | Green | [In Prog] late start;
DSFFLOW-921 | Closed | Core Network | UDM | Upgrade | 23 | 23 | 23 | 1 | 100% | 2 | 100% | May 09 2025 | May 09 2025 | May 14 2025 | Jul 31 2025 | Jul 31 2025 | Jul 04 2025 | 83 | 83 | 202.5 | 202.5 | 232 | 232 | -15% | 100% | 68% | 115% | Red | [Closed] effort overrun > 1%; ahead of schedule; feedback: opportunity for optimized time plan;
DSFFLOW-4396 | In Progress | Core Network | MSS | Upgrade | 43 | 43 | 7 | 1 | 0% | 7 | 0% | Aug 04 2025 | Aug 04 2025 | Aug 05 2025 | Oct 06 2025 | Oct 06 2025 |  | 63 | 63 | 734 | 734 | 229.5 | 734 | 0% | 16% | 25% | 31% | Green | [In Prog]
DSFFLOW-2560 | Closed | Network Management | Resource Orchestration | Upgrade | 24 | 18 | 18 | 1 | 100% |  |  | Jun 26 2025 | Jun 26 2025 | Jun 27 2025 | Jul 08 2025 | Jul 08 2025 | Jul 07 2025 | 12 | 12 | 222 | 222 | 222 | 222 | 0% | 100% | 92% | 100% | Green | [Closed] ahead of schedule;
DSFFLOW-3029 | In Progress | Core Network | IMS | Migration | 20 | 20 | 2 | 2 | 0% | 2 | 0% | May 07 2025 | May 07 2025 | Jul 14 2025 | Dec 31 2025 | Dec 31 2025 |  | 238 | 238 | 902 | 902 | 216 | 902 | 0% | 10% | 44% | 24% | Green | [In Prog] late start;
DSFFLOW-3547 | Closed | Core Network | MSS | Upgrade | 13 | 13 | 13 | 1 | 100% |  |  | Jul 06 2025 | Jul 08 2025 | Jul 08 2025 | Aug 14 2025 | Aug 08 2025 | Aug 18 2025 | 39 | 31 | 220 | 220 | 210 | 210 | 5% | 100% | 131% | 95% | Amber | [In Prog] efforts burnt misaligned with work progress; work progress misaligned with time progress;
DSFFLOW-4564 | In Progress | Core Network | Cloud | Upgrade | 32 | 32 | 0 | 2 | 0% | 2 | 0% | Jul 22 2025 | Jul 22 2025 | Aug 08 2025 | Jan 15 2026 | Jan 15 2026 |  | 177 | 177 | 1211 | 1211 | 208 | 1193 | 1% | 0% | 16% | 17% | Green | [In Prog] late start;
DSFFLOW-535 | In Progress | Core Network | EPC | Maiden Installation | 14 | 14 | 13 | 1 | 0% |  |  | Jan 01 2025 | Dec 31 2024 | Jan 01 2025 | Jul 31 2025 | May 29 2025 | Apr 30 2025 | 211 | 149 | 149 | 149 | 206 | 198 | -33% | 93% | 81% | 138% | Red | [In Prog] effort budget breached; projecting 5%+ EAC effort overrun; efforts burnt misaligned with work progress; efforts burnt misaligned with time progress;
DSFFLOW-3581 | Closed | Core Network | MSS | Upgrade | 13 | 13 | 13 | 1 | 100% |  |  | Jul 22 2025 | Jul 03 2025 | Jul 03 2025 | Aug 15 2025 | Aug 08 2025 | Aug 18 2025 | 24 | 36 | 220 | 220 | 204.5 | 204.5 | 7% | 100% | 127% | 93% | Amber | [In Prog] time ticking without any work progress; efforts burnt misaligned with work progress;
DSFFLOW-2419 | Closed | Core Network | IMS | Upgrade | 52 | 52 | 52 | 2 | 100% | 2 | 100% | Jun 05 2025 | Jun 05 2025 | Jul 24 2025 | Jun 26 2025 | Jun 26 2025 | Jul 24 2025 | 21 | 21 | 322 | 322 | 200 | 200 | 38% | 100% | 227% | 62% | Red | [Closed] schedule overrun > 10%; efforts saved; feedback: opportunity for optimized effort baseline; late start;
DSFFLOW-2575 | In Progress | Core Network | Cloud | Maiden Installation | 32 | 32 | 2 | 2 | 0% |  |  | Jun 23 2025 | Jun 23 2025 | Jul 14 2025 | Dec 01 2025 | Dec 01 2025 |  | 161 | 161 | 1262 | 1262 | 200 | 1221 | 3% | 6% | 36% | 16% | Amber | [In Prog] projecting 1%+ EAC effort overrun ; late start;
DSFFLOW-2962 | In Progress | Core Network | Cloud | Maiden Installation | 101 | 101 | 0 | 2 | 0% | 8 | 0% | Jul 07 2025 | Jul 07 2025 | Aug 05 2025 | Dec 30 2025 | Dec 30 2025 |  | 176 | 176 | 1816 | 1816 | 192.0008 | 1816 | 0% | 0% | 25% | 11% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-2435 | In Progress | Core Network | EPC | Upgrade | 16 | 16 | 0 | 1 | 0% | 2 | 0% | Jun 16 2025 | Jun 16 2025 | Jul 07 2025 | Jun 30 2025 | Jun 30 2025 |  | 14 | 14 | 558 | 558 | 192 | 558 | 0% | 0% | 433% | 34% | Amber | [In Prog] time ticking without any work progress; efforts burnt misaligned with work progress; late start;
DSFFLOW-4299 | In Progress | Core Network | Cloud, EPC, UDM | Upgrade | 88 | 88 | 0 | 8 | 0% |  |  | Jul 21 2025 | Jul 21 2025 | Aug 06 2025 | Oct 31 2025 | Oct 31 2025 |  | 102 | 102 | 1686 | 1686 | 182.75 | 1677.5 | 1% | 0% | 29% | 11% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-3381 | Closed | Core Network | Signaling | Upgrade | 19 | 19 | 19 | 1 | 100% | 1 | 100% | Jun 10 2025 | Jun 04 2025 | Jun 04 2025 | Jul 30 2025 | Jul 22 2025 | Jul 22 2025 | 50 | 48 | 179 | 179 | 178.5 | 178.5 | 0% | 100% | 100% | 100% | Green | [Closed]
DSFFLOW-4677 | In Progress | Core Network | EPC | Maiden Installation | 127 | 127 | 0 | 4 | 0% | 13 | 0% | Aug 11 2025 | Aug 11 2025 | Aug 11 2025 | Dec 31 2026 | Dec 31 2026 |  | 507 | 507 | 10485.6 | 10485.6 | 178 | 10485.6 | 0% | 0% | 2% | 2%
DSFFLOW-4213 | In Progress | Core Network | IMS | Upgrade | 80 | 80 | 1 | 3 | 0% | 3 | 0% | Jul 25 2025 | Jul 25 2025 | Aug 01 2025 | Oct 31 2025 | Oct 31 2025 |  | 98 | 98 | 1036 | 1036 | 173.45 | 1032 | 0% | 1% | 26% | 17% | Green | [In Prog]
DSFFLOW-4343 | In Progress | Core Network | Cloud, EPC | Upgrade | 141 | 141 | 0 | 3 | 0% | 12 | 0% | Jun 19 2025 | Jun 19 2025 | Aug 18 2025 | Dec 19 2025 | Dec 19 2025 |  | 183 | 183 | 3597 | 3597 | 168 | 3481 | 3% | 0% | 34% | 5% | Amber | [Assigned] with 53 days past due start date;
DSFFLOW-591 | In Progress | Core Network | Cloud-3PP/MPBN | Upgrade | 15 | 15 | 1 |  |  |  |  | Apr 22 2025 | Apr 22 2025 | Jun 05 2025 | Jun 30 2025 | Jun 30 2025 |  | 69 | 69 | 248 | 248 | 143 | 187.5 | 24% | 7% | 171% | 58% | Amber | [In Prog] efforts burnt misaligned with work progress; efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-4427 | Closed | Network Management | Element Management & Reporting | Upgrade | 24 | 18 | 18 |  |  | 1 | 100% | Jul 28 2025 | Jul 28 2025 | Aug 06 2025 | Aug 08 2025 | Aug 08 2025 | Aug 11 2025 | 11 | 11 | 148 | 148 | 140 | 140 | 5% | 100% | 125% | 95% | Red | [In Prog] efforts burnt outweighing work output; projecting 1%+ EAC effort overrun ; efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-3700 | Closed | Core Network | Signaling | Upgrade | 20 | 19 | 18 | 1 | 100% |  |  | Jun 04 2025 | Jun 04 2025 | Jul 24 2025 | Jul 31 2026 | Jul 31 2026 | Jul 25 2025 | 422 | 422 | 138 | 138 | 138 | 137 | 1% | 95% | 12% | 100% | Red | [Closed] incomplete work; effort budget spent; ahead of schedule; feedback: opportunity for optimized time plan; late start;
DSFFLOW-3443 | On Hold | Network Management | Element Management & Reporting | Upgrade | 21 | 15 | 8 | 1 | 0% |  |  | Jul 14 2025 | Jul 14 2025 | Jul 14 2025 | Sep 19 2025 | Sep 19 2025 | Aug 01 2025 | 67 | 67 | 158.5 | 158.5 | 137 | 229 | -44% | 53% | 28% | 86% | Red | [On Hold] projecting 5%+ EAC effort overrun; efforts burnt misaligned with work progress; efforts burnt misaligned with time progress;
DSFFLOW-3685 | In Progress | Core Network | MSS | Upgrade | 24 | 24 | 3 | 2 | 0% | 2 | 0% | Jun 30 2025 | Jun 27 2025 | Jun 27 2025 | Sep 14 2025 | Sep 14 2025 | Sep 14 2025 | 76 | 79 | 434.5 | 434.5 | 129 | 434.5 | 0% | 13% | 100% | 30% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress; actual End Date exceeds Today;
DSFFLOW-3812 | In Progress | Core Network | Cloud | Upgrade | 36 | 36 | 4 | 2 | 0% | 2 | 0% | May 05 2025 | May 05 2025 | Jul 28 2025 | Dec 30 2025 | Dec 30 2025 |  | 239 | 239 | 785 | 785 | 129 | 776 | 1% | 11% | 45% | 16% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-3715 | In Progress | Core Network | MSS | Upgrade | 15 | 15 | 3 | 1 | 0% |  |  | Jun 10 2025 | Jun 10 2025 | Jul 25 2025 | Aug 30 2025 | Aug 30 2025 |  | 81 | 81 | 187 | 187 | 127.5 | 187 | 0% | 20% | 87% | 68% | Amber | [In Prog] efforts burnt misaligned with work progress; work progress misaligned with time progress; late start;
DSFFLOW-4744 | In Progress | Core Network | EPC, UDM | Maiden Installation | 25 | 25 | 1 |  |  |  |  | Feb 11 2025 | Feb 11 2025 | Aug 14 2025 | Dec 31 2025 | Dec 31 2025 |  | 323 | 323 | 1001 | 1001 | 124 | 1001 | 0% | 4% | 59% | 12%
DSFFLOW-2708 | In Progress | Core Network | Cloud, Signaling | Upgrade | 14 | 14 | 3 | 2 | 0% | 2 | 0% | Jun 01 2025 | Jun 01 2025 | Jul 04 2025 | Oct 31 2025 | Oct 31 2025 |  | 152 | 152 | 315 | 315 | 121 | 308 | 2% | 21% | 52% | 38% | Amber | [In Prog] time ticking without any work progress; efforts burnt misaligned with work progress; late start;
DSFFLOW-4411 | In Progress | Network Management | Element Management & Reporting | Upgrade | 34 | 32 | 9 | 1 | 0% | 2 | 0% | Aug 06 2025 | Aug 06 2025 | Aug 11 2025 | Sep 30 2025 | Sep 30 2025 |  | 55 | 55 | 515.95 | 481.95 | 114 | 349.45 | 27% | 28% | 25% | 24% | Amber | [Assigned] with 5 days past due start date;
DSFFLOW-4230 | In Progress | Core Network | Cloud | Upgrade | 17 | 17 | 8 | 1 | 0% |  |  | Aug 03 2025 | Aug 03 2025 | Aug 04 2025 | Aug 21 2025 | Aug 21 2025 |  | 18 | 18 | 216 | 216 | 112 | 192 | 11% | 47% | 89% | 52% | Amber | [In Prog] time ticking without any work progress;
DSFFLOW-3127 | In Progress | Core Network | EPC | Upgrade | 57 | 57 | 0 | 2 | 0% | 2 | 0% | Jun 21 2025 | Jun 21 2025 | Jul 25 2025 | Aug 30 2025 | Aug 30 2025 |  | 70 | 70 | 638 | 638 | 112 | 622 | 3% | 0% | 85% | 18% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-2452 | On Hold | Network Management | Resource Orchestration | Maiden Installation | 44 | 44 | 2 | 1 | 0% | 1 | 0% | May 29 2025 | May 29 2025 | Jul 11 2025 | Feb 27 2026 | Feb 27 2026 |  | 274 | 274 | 1157 | 1157 | 111.58 | 1157 | 0% | 5% | 30% | 10% | Green | [On Hold] late start;
DSFFLOW-4198 | In Progress | Core Network | UDM | Upgrade | 16 | 16 | 4 | 1 | 0% |  |  | Jul 30 2025 | Aug 01 2025 | Aug 04 2025 | Sep 15 2025 | Sep 15 2025 |  | 47 | 45 | 506 | 506 | 110.5 | 471.5 | 7% | 25% | 41% | 22% | Amber | [In Prog] time ticking without any work progress;
DSFFLOW-3078 | In Progress | Core Network | UDM | Upgrade | 27 | 27 | 1 | 1 | 0% | 4 | 0% | Jul 02 2025 | Jul 03 2025 | Jul 03 2025 | Sep 01 2025 | Sep 19 2025 | Sep 19 2025 | 61 | 78 | 656 | 656 | 110.5 | 655.5 | 0% | 4% | 100% | 17% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress; actual End Date exceeds Today;
DSFFLOW-937 | Backlog | Core Network | IMS | Upgrade | 16 | 16 | 2 | 1 | 0% | 1 | 0% | May 06 2025 | May 06 2025 |  | Jun 29 2025 | Jun 29 2025 |  | 54 | 54 | 176 | 176 | 108 | 173 | 2% | 13% | 193% | 61% | Red | [Backlog] with wrong project state with work happening; efforts burning; 97 days past due start date;
DSFFLOW-4442 | In Progress | Network Management | Element Management & Reporting | Upgrade | 25 | 25 | 2 | 1 | 0% |  |  | Jul 27 2025 | Jul 27 2025 | Aug 06 2025 | Sep 18 2025 | Sep 18 2025 |  | 53 | 53 | 418.2 | 418.2 | 102 | 418.2 | 0% | 8% | 44% | 24% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-4245 | In Progress | Network Management | Activation, Element Management & Reporting, Resource Orchestration | Upgrade | 41 | 41 | 2 | 3 | 0% |  |  | Jul 21 2025 | Jul 21 2025 | Aug 06 2025 | Sep 30 2025 | Sep 30 2025 |  | 71 | 71 | 461.9 | 461.9 | 91.89 | 461.9 | 0% | 5% | 42% | 20% | Green | [In Prog] late start;
DSFFLOW-3611 | Closed | Core Network | Cloud | Upgrade | 17 | 17 | 15 | 1 | 100% |  |  | Jul 23 2025 | Jul 23 2025 | Jul 24 2025 | Aug 28 2025 | Aug 28 2025 | Aug 07 2025 | 36 | 36 | 106 | 106 | 88 | 88 | 17% | 88% | 43% | 83% | Red | [Closed] incomplete work; ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; feedback: opportunity for optimized effort baseline;
DSFFLOW-4055 | In Progress | Network Management | Element Management & Reporting | Upgrade | 26 | 19 | 10 | 2 | 0% |  |  | Aug 04 2025 | Aug 04 2025 | Aug 04 2025 | Sep 30 2025 | Sep 30 2025 |  | 57 | 57 | 328 | 328 | 86.02 | 318.02 | 3% | 53% | 28% | 26% | Red | [In Prog] projecting 5%+ EAC effort overrun;
DSFFLOW-1474 | Backlog | Core Network | IMS | Upgrade | 54 | 54 | 5 | 3 | 0% | 2 | 0% | Mar 24 2025 | Mar 24 2025 |  | Jun 30 2025 | Feb 02 2026 |  | 98 | 315 | 429.5 | 429.5 | 72 | 357.5 | 17% | 9% | 47% | 17% | Red | [Backlog] with wrong project state with work happening; efforts burning; 140 days past due start date;
DSFFLOW-3596 | In Progress | Core Network | UDM | Upgrade | 36 | 36 | 2 | 1 | 0% | 2 | 0% | Jul 21 2025 | Jul 21 2025 | Jul 24 2025 | Sep 12 2025 | Sep 12 2025 |  | 53 | 53 | 481.5 | 481.5 | 66 | 481.5 | 0% | 6% | 56% | 14% | Green | [In Prog]
DSFFLOW-2544 | In Progress | Core Network | Cloud-3PP/MPBN | Maiden Installation | 10 | 10 | 0 |  |  |  |  | Apr 19 2025 | Apr 19 2025 | Jun 26 2025 | Oct 31 2025 | Oct 31 2025 |  | 195 | 195 | 1340 | 1340 | 66 | 1274 | 5% | 0% | 63% | 5% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-3327 | In Progress | Network Management | Resource Orchestration | Upgrade | 26 | 26 | 4 | 1 | 0% |  |  | Jul 15 2025 | Jul 15 2025 | Jul 21 2025 | Oct 31 2025 | Oct 31 2025 |  | 108 | 108 | 334 | 334 | 58 | 334 | 0% | 15% | 33% | 17% | Amber | [In Prog] projecting 1%+ EAC effort overrun ;
DSFFLOW-4794 | In Progress | Network Management | Element Management & Reporting | Upgrade | 23 | 18 | 3 | 1 | 0% |  |  | Aug 11 2025 | Aug 11 2025 | Aug 15 2025 | Aug 28 2025 | Aug 29 2025 |  | 17 | 18 | 282 | 282 | 52 | 280 | 1% | 17% | 47% | 18%
DSFFLOW-4605 | In Progress | Core Network | Cloud | Upgrade | 127 | 127 | 0 | 3 | 0% | 12 | 0% | Jul 24 2025 | Jul 24 2025 | Aug 11 2025 | Dec 31 2026 | Dec 31 2026 |  | 525 | 525 | 2196 | 2196 | 48 | 2196 | 0% | 0% | 5% | 2%
DSFFLOW-4028 | In Progress | Core Network | Cloud | Maiden Installation | 33 | 33 | 0 | 1 | 0% |  |  | Jul 14 2025 | Jul 14 2025 | Jul 30 2025 | Sep 05 2025 | Sep 05 2025 |  | 53 | 53 | 1736 | 1736 | 42 | 1694 | 2% | 0% | 69% | 2% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-4379 | In Progress | Network Management | Element Management & Reporting | Upgrade | 69 | 69 | 3 | 1 | 0% | 2 | 0% | Aug 03 2025 | Aug 04 2025 | Aug 04 2025 | Dec 31 2025 | Dec 31 2025 |  | 150 | 149 | 1002.5 | 1002.5 | 41 | 995.5 | 1% | 4% | 11% | 4% | Green | [In Prog]
DSFFLOW-1679 | In Progress | Core Network | Cloud-3PP/MPBN | Maiden Installation | 11 | 11 | 0 |  |  |  |  | May 16 2025 | May 16 2025 | Jul 22 2025 | Dec 31 2026 | Dec 31 2026 |  | 594 | 594 | 216 | 216 | 35.25 | 216 | 0% | 0% | 16% | 16% | Green | [In Prog] late start;
DSFFLOW-2336 | In Progress | Core Network | Signaling | Upgrade | 26 | 26 | 0 | 2 | 0% |  |  | Jun 02 2025 | Jun 02 2025 | Jun 27 2025 | Jul 04 2025 | Aug 15 2025 |  | 32 | 74 | 364 | 364 | 35 | 359 | 1% | 0% | 105% | 10% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-1994 | In Progress | Network Management | Resource Orchestration | Upgrade | 39 | 38 | 4 | 1 | 0% |  |  | Jun 22 2025 | Jun 22 2025 | Jun 24 2025 | Jul 10 2025 | Jul 10 2025 |  | 18 | 18 | 313.5 | 305.5 | 28 | 289.5 | 5% | 11% | 311% | 9% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress;
DSFFLOW-4760 | In Progress | Network Management | Resource Orchestration | Upgrade | 46 | 46 | 3 | 2 | 0% | 2 | 0% | Aug 12 2025 | Aug 12 2025 | Aug 14 2025 | Sep 29 2025 | Sep 29 2025 |  | 48 | 48 | 200.08 | 200.08 | 17 | 200.08 | 0% | 7% | 16% | 8%
DSFFLOW-4694 | In Progress | Core Network | Cloud | Upgrade | 48 | 48 | 0 | 4 | 0% | 1 | 0% | Jul 13 2025 | Jul 13 2025 | Aug 12 2025 | Dec 30 2025 | Dec 30 2025 |  | 170 | 170 | 2298 | 2298 | 15 | 2283 | 1% | 0% | 22% | 1%
DSFFLOW-4498 | In Progress | Core Network | EPC, IMS, MSS, UDM | Upgrade | 210 | 210 | 0 | 9 | 0% | 8 | 0% | Jul 15 2025 | Jul 15 2025 | Aug 08 2025 | Jan 15 2026 | Jan 15 2026 |  | 184 | 184 | 3907 | 3907 | 8.5 | 3898.5 | 0% | 0% | 19% | 0% | Green | [In Prog] late start;
DSFFLOW-970 | In Progress | Core Network | Cloud-3PP/MPBN | Upgrade | 16 | 16 | 0 |  |  |  |  | May 08 2025 | May 08 2025 | Aug 07 2025 | Jul 29 2025 | Jul 29 2025 |  | 82 | 82 | 237.5 | 237.5 | 5 | 232.5 | 2% | 0% | 125% | 2% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-2765 | In Progress | Core Network | EPC, Cloud | Upgrade | 49 | 49 | 0 | 3 | 0% | 3 | 0% | Nov 11 2024 | Nov 11 2024 | Jul 07 2025 | Dec 20 2024 | Dec 20 2024 |  | 39 | 39 | 1560 | 1560 | 1 | 1560 | 0% | 0% | 705% | 0% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-4483 | In Progress | Core Network | EPC | Expansion | 12 | 12 | 8 |  |  |  |  | Aug 18 2025 | Aug 18 2025 | Aug 06 2025 | Sep 12 2025 | Sep 12 2025 |  | 25 | 25 | 161 | 161 | 1 | 161 | 0% | 67% | 8% | 1% | Green | [In Prog] early start;
DSFFLOW-4525 | Assigned | Core Network | UDM | Migration | 15 | 15 | 0 |  |  | 1 | 0% | Aug 11 2025 | Aug 11 2025 |  | Jan 30 2026 | Jan 30 2026 |  | 172 | 172 | 1277 | 1277 |  | 1277 | 0% | 0% | 5% | 0% | Amber | [Assigned] with 0 days past due start date;
DSFFLOW-2674 | In Progress | Core Network | EPC | Maiden Installation | 41 | 41 | 0 |  |  | 4 | 0% | May 01 2024 | May 01 2024 | Jul 10 2025 | Sep 30 2025 | Sep 30 2025 |  | 517 | 517 | 1454 | 1454 |  | 1454 | 0% | 0% | 92% | 0% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-4260 | In Progress | Core Network | Cloud | Upgrade | 84 | 84 | 6 | 2 | 50% | 10 | 0% | Jul 06 2025 | Jul 06 2025 | Aug 05 2025 | Nov 29 2025 | Nov 29 2025 |  | 146 | 146 | 1912 | 1912 |  | 1584 | 17% | 7% | 31% | 0% | Green | [In Prog] late start;
DSFFLOW-3294 | Assigned | Core Network | IMS | Upgrade | 65 | 65 | 0 | 1 | 0% | 4 | 0% | Jul 08 2025 | Jul 08 2025 |  | Sep 22 2025 | Sep 22 2025 |  | 76 | 76 | 312 | 312 |  | 312 | 0% | 0% | 56% | 0% | Amber | [Assigned] with 34 days past due start date;
DSFFLOW-3998 | Assigned | Core Network | MSS | Upgrade | 13 | 13 | 0 | 1 | 0% |  |  | Jul 25 2025 | Jul 25 2025 |  | Apr 15 2026 | Apr 15 2026 |  | 264 | 264 | 220 | 220 |  | 220 | 0% | 0% | 10% | 0% | Amber | [Assigned] with 17 days past due start date;
DSFFLOW-4013 | Assigned | Core Network | MSS | Maiden Installation | 38 | 38 | 0 | 1 | 0% | 1 | 0% | Jul 25 2025 | Jul 25 2025 |  | Apr 15 2026 | Apr 15 2026 |  | 264 | 264 | 2613 | 2613 |  | 2613 | 0% | 0% | 10% | 0% | Amber | [Assigned] with 17 days past due start date;
DSFFLOW-371 | Backlog | Core Network | MSS | Upgrade | 28 | 28 | 0 | 1 | 0% | 2 | 0% | Mar 24 2025 | Mar 24 2025 |  | Jul 25 2025 | Jul 25 2025 |  | 123 | 123 | 700 | 700 |  | 700 | 0% | 0% | 120% | 0% | Amber | [Backlog] with 140 days past due start date;
DSFFLOW-879 | Rejected | Network Management | Element Management & Reporting | Upgrade | 12 | 12 | 0 | 1 | 0% |  |  | May 09 2025 | May 09 2025 |  | Jun 29 2025 | Jun 29 2025 |  | 51 | 51 | 0 | 0 |  | 0 | 0% | 0% | 198% | 0%
DSFFLOW-4713 | Assigned | Core Network | MSS | Upgrade | 38 | 38 | 0 | 2 | 0% | 4 | 0% | Jul 25 2025 | Jul 25 2025 |  | Aug 30 2025 | Aug 30 2025 |  | 36 | 36 | 652 | 652 |  | 652 | 0% | 0% | 70% | 0%
DSFFLOW-4865 | Assigned | Core Network | MSS, Signaling | Upgrade | 23 | 23 | 0 | 2 | 0% | 2 | 0% | Jun 06 2024 | Jun 06 2024 |  | Aug 21 2025 | Aug 21 2025 |  | 441 | 441 | 282.5 | 282.5 |  | 282.5 | 0% | 0% | 100% | 0%
DSFFLOW-3411 | Assigned | Core Network | IMS | Upgrade | 46 | 46 | 0 | 1 | 0% | 2 | 0% | Jul 14 2025 | Jul 14 2025 |  | Aug 15 2025 | Aug 15 2025 |  | 32 | 32 | 542 | 542 |  | 542 | 0% | 0% | 112% | 0% | Amber | [Assigned] with 28 days past due start date;
DSFFLOW-3418 | Assigned | Core Network | IMS | Upgrade | 38 | 38 | 0 | 1 | 0% | 2 | 0% | Jul 14 2025 | Jul 14 2025 |  | Sep 12 2025 | Sep 12 2025 |  | 60 | 60 | 516 | 516 |  | 516 | 0% | 0% | 61% | 0% | Amber | [Assigned] with 28 days past due start date;
DSFFLOW-4955 | Assigned | Network Management | Element Management & Reporting | Maiden Installation | 77 | 77 | 0 | 2 | 0% | 2 | 0% | Aug 18 2025 | Aug 18 2025 |  | Nov 28 2025 | Nov 28 2025 |  | 102 | 102 | 2003.5 | 2003.5 |  | 2003.5 | 0% | 0% | 2% | 0%
DSFFLOW-356 | Backlog | Core Network | UDM | Expansion | 13 | 13 | 0 | 1 | 0% | 1 | 0% | Dec 18 2024 | Dec 18 2024 |  | Jul 31 2026 | Jul 31 2026 |  | 590 | 590 | 222 | 222 |  | 222 | 0% | 0% | 41% | 0% | Amber | [Backlog] with 236 days past due start date;
DSFFLOW-4729 | Assigned | Core Network | Cloud-3PP/MPBN | Upgrade | 10 | 10 | 0 |  |  |  |  | Aug 01 2025 | Aug 01 2025 |  | Oct 31 2025 | Oct 31 2025 |  | 91 | 91 | 14 | 14 |  | 14 | 0% | 0% | 21% | 0%
DSFFLOW-1809 | Assigned | Core Network | MSS, Signaling | Upgrade, Maiden Installation | 46 | 46 | 0 | 5 | 0% | 6 | 0% | Mar 03 2025 | Mar 03 2025 |  | Dec 15 2025 | Dec 15 2025 |  | 287 | 287 | 1202 | 1202 |  | 1202 | 0% | 0% | 59% | 0% | Amber | [Assigned] with 161 days past due start date;
DSFFLOW-3265 | Assigned | Core Network | EPC, UDM, IMS, Core Network Automation, Cloud | Migration | 88 | 88 | 0 | 14 | 0% | 5 | 0% | May 15 2025 | May 15 2025 |  | Nov 20 2025 | Nov 20 2025 |  | 189 | 189 | 8356.5 | 8356.5 |  | 8356.5 | 0% | 0% | 51% | 0% | Amber | [Assigned] with 88 days past due start date;
DSFFLOW-4850 | Assigned | Core Network | Core Network Automation, EPC, IMS, MSS, Signaling, UDM | Migration | 301 | 301 | 0 | 16 | 0% | 6 | 0% | Aug 11 2025 | Aug 11 2025 |  | Oct 25 2025 | Oct 25 2025 |  | 75 | 75 | 8332.6 | 8332.6 |  | 8332.6 | 0% | 0% | 12% | 0%
DSFFLOW-4624 | Assigned | Core Network | Signaling | Maiden Installation | 18 | 18 | 0 |  |  |  |  | Aug 09 2025 | Aug 09 2025 |  | Jun 29 2026 | Jun 29 2026 |  | 324 | 324 | 570 | 570 |  | 570 | 0% | 0% | 3% | 0%
DSFFLOW-4628 | Assigned | Core Network | Core Network Automation, UDM | Maiden Installation | 29 | 29 | 0 |  |  |  |  | Aug 09 2025 | Aug 09 2025 |  | Jun 29 2026 | Jun 29 2026 |  | 324 | 324 | 730 | 730 |  | 730 | 0% | 0% | 3% | 0%
DSFFLOW-4636 | Assigned | Core Network | Core Network Automation, EPC | Maiden Installation | 51 | 51 | 0 |  |  |  |  | Jun 30 2025 | Jun 30 2025 |  | Jun 29 2026 | Jun 29 2026 |  | 364 | 364 | 1716 | 1716 |  | 1716 | 0% | 0% | 14% | 0%
DSFFLOW-845 | Backlog | Core Network | MSS | Upgrade | 22 | 22 | 0 | 1 | 0% |  |  | Feb 24 2025 | Feb 24 2025 |  | Jun 30 2025 | Jun 30 2025 |  | 126 | 126 | 674 | 674 |  | 674 | 0% | 0% | 139% | 0% | Amber | [Backlog] with 168 days past due start date;
DSFFLOW-325 | Assigned | Core Network | MSS | Upgrade | 34 | 34 | 0 | 1 | 0% | 4 | 0% | Apr 22 2025 | Apr 22 2025 |  | Dec 31 2026 | Dec 31 2026 |  | 618 | 618 | 512 | 512 |  | 512 | 0% | 0% | 19% | 0% | Red | [Assigned] with wrong project state with efforts burning; 111 days past due start date;
DSFFLOW-4880 | Assigned | Core Network | Cloud-3PP/MPBN, IMS, MSS, Signaling, UDM | Migration | 127 | 127 | 0 | 15 | 0% | 15 | 0% | Aug 13 2025 | Aug 13 2025 |  | Dec 05 2025 | Dec 05 2025 |  | 114 | 114 | 2334.2 | 2334.2 |  | 2334.2 | 0% | 0% | 6% | 0%
DSFFLOW-2843 | In Progress | BOS | Common Services-Data Migration | Migration | 10 | 10 | 0 |  |  |  |  | Jun 16 2025 | Jun 16 2025 | Jun 17 2025 | Dec 31 2026 | Dec 31 2026 |  | 563 | 563 | 1 | 1 |  | 1 | 0% | 0% | 12% | 0% | Green | [In Prog]
DSFFLOW-4916 | Assigned | Network Management | Element Management & Reporting | Upgrade | 78 | 78 | 0 | 2 | 0% |  |  | Aug 18 2025 | Aug 18 2025 |  | Dec 15 2025 | Dec 15 2025 |  | 119 | 119 | 1231.8 | 1231.8 |  | 1231.8 | 0% | 0% | 2% | 0%
DSFFLOW-4361 | In Progress | Core Network | Cloud, EPC | Upgrade | 141 | 141 | 0 | 3 | 0% | 12 | 0% | Jun 19 2025 | Jun 19 2025 | Aug 10 2025 | Dec 19 2025 | Dec 19 2025 |  | 183 | 183 | 3597 | 3597 |  | 3597 | 0% | 0% | 34% | 0% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-3010 | Assigned | Core Network | Cloud | Upgrade | 47 | 47 | 0 | 1 | 0% | 4 | 0% | Jul 04 2025 | Jul 04 2025 |  | Dec 31 2025 | Dec 31 2025 |  | 180 | 180 | 1803 | 1803 |  | 1803 | 0% | 0% | 26% | 0% | Amber | [Assigned] with 38 days past due start date;
DSFFLOW-3528 | Assigned | Core Network | EPC | Upgrade | 130 | 130 | 0 | 1 | 0% | 7 | 0% | Jul 04 2025 | Jul 04 2025 |  | Dec 31 2025 | Dec 31 2025 |  | 180 | 180 | 1992 | 1992 |  | 1992 | 0% | 0% | 26% | 0% | Amber | [Assigned] with 38 days past due start date;
DSFFLOW-3630 | Assigned | Core Network | Cloud | Migration | 60 | 60 | 0 | 1 | 0% | 7 | 0% | Jul 04 2025 | Jul 04 2025 |  | Dec 31 2025 | Dec 31 2025 |  | 180 | 180 | 2549 | 2549 |  | 2549 | 0% | 0% | 26% | 0% | Amber | [Assigned] with 38 days past due start date;
DSFFLOW-2916 | Assigned | Core Network | MSS | Maiden Installation | 12 | 12 | 0 | 1 | 0% |  |  | May 15 2025 | May 15 2025 |  | Dec 21 2026 | Dec 21 2026 |  | 585 | 585 | 204 | 204 |  | 204 | 0% | 0% | 17% | 0% | Amber | [Assigned] with 88 days past due start date;
DSFFLOW-4540 | Assigned | Core Network | Cloud | Upgrade | 34 | 34 | 0 | 2 | 0% | 2 | 0% | Jul 28 2025 | Jul 28 2025 |  | Dec 31 2025 | Dec 31 2025 |  | 156 | 156 | 1364 | 1364 |  | 1364 | 0% | 0% | 15% | 0% | Amber | [Assigned] with 14 days past due start date;
DSFFLOW-4588 | In Progress | Core Network | Core Network Automation, EPC, UDM | Maiden Installation | 73 | 73 | 0 | 1 | 0% | 5 | 0% | Jul 30 2025 | Jul 30 2025 | Aug 08 2025 | Jun 30 2026 | Jun 30 2026 |  | 335 | 335 | 1961 | 1961 |  | 1956 | 0% | 0% | 6% | 0% | Green | [In Prog] late start;

## RAGStatus
DSF Project ID | Delivery State | Flow | Domain | Sub-Domain | Plan Work | Replan Work | Closed Work | Plan Start | Replan Start | Actual Start | Plan End | Replan End | Actual End | Plan Days | Replan Days | Plan Hr | Replan Hr | Logged Hr | EAC Hr | EAC Efficiency | Work Prog | Time Prog | Effort Prog | RAG | RAG Reason + Observations
DSFFLOW-4457 | Closed | Upgrade | Network Management | Element Management & Reporting | 38 | 14 | 14 | 2025-08-04 | 2025-07-08 | 2025-08-05 | 2025-12-26 | 2025-09-15 | 2025-08-13 | 144 | 69 | 946.5 | 505.5 | 405.5 | 405.5 | 20% | 100% | 53% | 80% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; feedback: opportunity for optimized effort baseline; late start;
DSFFLOW-3547 | Closed | Upgrade | Core Network | MSS | 13 | 13 | 13 | 2025-07-06 | 2025-07-08 | 2025-07-08 | 2025-08-14 | 2025-08-08 | 2025-08-18 | 39 | 31 | 220 | 220 | 210 | 210 | 5% | 100% | 131% | 95% | Red | [Closed] schedule overrun > 10%; efforts saved;
DSFFLOW-1135 | Closed | Upgrade | BOS | D&A Mediation | 34 | 34 | 34 | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-06-20 | 2025-06-20 | 2025-06-20 | 32 | 32 | 569.1 | 569.1 | 548 | 548 | 4% | 100% | 100% | 96% | Green | [Closed] efforts saved;
DSFFLOW-1879 | Closed | Maiden Installation | Network Management | Element Management & Reporting | 25 | 14 | 14 | 2025-05-26 | 2025-05-26 | 2025-05-26 | 2025-06-30 | 2025-06-30 | 2025-06-30 | 35 | 35 | 304.5 | 298 | 268.5 | 268.5 | 10% | 100% | 100% | 90% | Green | [Closed] efforts saved;
DSFFLOW-2625 | Closed | Upgrade | Core Network | IMS | 30 | 28 | 28 | 2025-06-29 | 2025-06-29 | 2025-06-30 | 2025-07-31 | 2025-07-25 | 2025-08-01 | 32 | 26 | 267 | 267 | 267.01 | 267.01 | 0% | 100% | 126% | 100% | Red | [Closed] schedule overrun > 10%;
DSFFLOW-340 | Closed | Upgrade | Core Network | UDM | 17 | 17 | 7 | 2025-03-04 | 2025-03-04 | 2025-03-04 | 2025-06-30 | 2025-06-30 | 2025-08-11 | 118 | 118 | 264 | 264 | 264 | 240 | 9% | 41% | 135% | 100% | Red | [Closed] incomplete work; effort budget spent; schedule overrun > 10%;
DSFFLOW-3649 | Closed | Upgrade | Core Network | IMS | 31 | 31 | 12 | 2025-07-03 | 2025-07-03 | 2025-07-24 | 2025-12-30 | 2025-12-30 | 2025-07-30 | 180 | 180 | 2715 | 2715 | 570 | 2615 | 4% | 39% | 15% | 21% | Red | [Closed] incomplete work; ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; feedback: opportunity for optimized effort baseline; late start;
DSFFLOW-97 | Closed | Upgrade | Network Management | Element Management & Reporting | 50 | 47 | 47 | 2025-03-12 | 2025-03-12 | 2025-03-13 | 2025-05-31 | 2025-07-31 | 2025-07-15 | 80 | 141 | 844 | 801.5 | 575 | 575 | 29% | 100% | 89% | 72% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; feedback: opportunity for optimized effort baseline;
DSFFLOW-1026 | Closed | Upgrade | Network Management | Resource Orchestration | 22 | 19 | 19 | 2025-04-20 | 2025-04-20 | 2025-06-13 | 2025-06-29 | 2025-06-29 | 2025-07-09 | 70 | 70 | 277.75 | 260.77 | 260.77 | 260.77 | 0% | 100% | 114% | 100% | Red | [Closed] schedule overrun > 10%; late start;
DSFFLOW-3700 | Closed | Upgrade | Core Network | Signaling | 20 | 19 | 18 | 2025-06-04 | 2025-06-04 | 2025-07-24 | 2026-07-31 | 2026-07-31 | 2025-07-25 | 422 | 422 | 138 | 138 | 138 | 137 | 1% | 95% | 12% | 100% | Red | [Closed] incomplete work; effort budget spent; ahead of schedule; feedback: opportunity for optimized time plan; late start;
DSFFLOW-386 | Closed | Maiden Installation | Core Network | EPC | 30 | 30 | 30 | 2024-11-10 | 2024-11-10 | 2025-01-01 | 2025-01-26 | 2025-01-26 | 2025-06-30 | 77 | 77 | 1773 | 1773 | 993 | 993 | 44% | 100% | 299% | 57% | Red | [Closed] schedule overrun > 10%; efforts saved; feedback: opportunity for optimized effort baseline; late start;
DSFFLOW-4427 | Closed | Upgrade | Network Management | Element Management & Reporting | 24 | 18 | 18 | 2025-07-28 | 2025-07-28 | 2025-08-06 | 2025-08-08 | 2025-08-08 | 2025-08-11 | 11 | 11 | 148 | 148 | 140 | 140 | 5% | 100% | 125% | 95% | Red | [Closed] schedule overrun > 10%; efforts saved; late start;
DSFFLOW-1383 | Closed | Upgrade | Core Network | EPC | 63 | 63 | 0 | 2024-12-31 | 2024-12-31 | 2025-01-01 | 2025-06-30 | 2025-06-30 | 2025-05-27 | 181 | 181 | 952 | 952 | 952 | 942 | 1% | 0% | 81% | 100% | Red | [Closed] incomplete work; effort budget spent; ahead of schedule; feedback: opportunity for optimized time plan;
DSFFLOW-1445 | Closed | Upgrade | Core Network | IMS | 78 | 59 | 59 | 2025-05-27 | 2025-05-27 | 2025-05-28 | 2025-07-18 | 2025-07-04 | 2025-07-04 | 52 | 38 | 801 | 639.5 | 600.2697 | 600.2697 | 6% | 100% | 100% | 94% | Green | [Closed] efforts saved;
DSFFLOW-1200 | Closed | Upgrade | Network Management | Element Management & Reporting | 192 | 35 | 35 | 2025-05-08 | 2025-02-10 | 2025-04-22 | 2026-08-31 | 2025-10-31 | 2025-06-19 | 480 | 263 | 3156 | 1055.5 | 605.5 | 605.5 | 43% | 100% | 49% | 57% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; feedback: opportunity for optimized effort baseline; late start;
DSFFLOW-3458 | Closed | Upgrade | Core Network | Cloud | 18 | 18 | 14 | 2025-07-22 | 2025-07-22 | 2025-07-29 | 2025-08-29 | 2025-08-29 | 2025-08-11 | 38 | 38 | 242 | 242 | 242 | 242 | 0% | 78% | 54% | 100% | Red | [Closed] incomplete work; effort budget spent; ahead of schedule; feedback: opportunity for optimized time plan;
DSFFLOW-3381 | Closed | Upgrade | Core Network | Signaling | 19 | 19 | 19 | 2025-06-10 | 2025-06-04 | 2025-06-04 | 2025-07-30 | 2025-07-22 | 2025-07-22 | 50 | 48 | 179 | 179 | 178.5 | 178.5 | 0% | 100% | 100% | 100% | Green | [Closed]
DSFFLOW-550 | Closed | Upgrade | Network Management | Element Management & Reporting | 43 | 43 | 43 | 2025-04-30 | 2025-04-07 | 2025-07-02 | 2026-02-27 | 2025-07-23 | 2025-07-18 | 303 | 107 | 624 | 624 | 618 | 618 | 1% | 100% | 95% | 99% | Green | [Closed] ahead of schedule; efforts saved; late start;
DSFFLOW-168 | Closed | Upgrade | BOS | Monetization Charging | 59 | 59 | 59 | 2025-03-21 | 2025-03-18 | 2025-03-18 | 2025-09-03 | 2025-09-03 | 2025-06-13 | 166 | 169 | 790.8 | 790.8 | 652.5 | 652.5 | 17% | 100% | 52% | 83% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; feedback: opportunity for optimized effort baseline;
DSFFLOW-2419 | Closed | Upgrade | Core Network | IMS | 52 | 52 | 52 | 2025-06-05 | 2025-06-05 | 2025-07-24 | 2025-06-26 | 2025-06-26 | 2025-07-24 | 21 | 21 | 322 | 322 | 200 | 200 | 38% | 100% | 227% | 62% | Red | [Closed] schedule overrun > 10%; efforts saved; feedback: opportunity for optimized effort baseline; late start;
DSFFLOW-3581 | Closed | Upgrade | Core Network | MSS | 13 | 13 | 13 | 2025-07-22 | 2025-07-03 | 2025-07-03 | 2025-08-15 | 2025-08-08 | 2025-08-18 | 24 | 36 | 220 | 220 | 204.5 | 204.5 | 8% | 100% | 127% | 93% | Red | [Closed] schedule overrun > 10%; efforts saved;
DSFFLOW-921 | Closed | Upgrade | Core Network | UDM | 23 | 23 | 23 | 2025-05-09 | 2025-05-09 | 2025-05-14 | 2025-07-31 | 2025-07-31 | 2025-07-04 | 83 | 83 | 202.5 | 202.5 | 232 | 232 | -15% | 100% | 68% | 115% | Red | [Closed] effort overrun > 1%; ahead of schedule; feedback: opportunity for optimized time plan;
DSFFLOW-1745 | Closed | Upgrade, Expansion | Core Network, Network Management | EPC, Exposure, Resource Orchestration, UDM | 101 | 101 | 89 | 2025-06-04 | 2025-06-04 | 2025-06-06 | 2025-08-30 | 2025-08-30 | 2025-07-28 | 87 | 87 | 1424 | 1424 | 1432 | 1432 | -1% | 88% | 63% | 101% | Red | [Closed] incomplete work; effort budget spent; effort overrun < 1%; ahead of schedule; feedback: opportunity for optimized time plan;
DSFFLOW-3611 | Closed | Upgrade | Core Network | Cloud | 17 | 17 | 15 | 2025-07-23 | 2025-07-23 | 2025-07-24 | 2025-08-28 | 2025-08-28 | 2025-08-07 | 36 | 36 | 106 | 106 | 88 | 88 | 17% | 88% | 43% | 83% | Red | [Closed] incomplete work; ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; feedback: opportunity for optimized effort baseline;
DSFFLOW-2560 | Closed | Upgrade | Network Management | Resource Orchestration | 24 | 18 | 18 | 2025-06-26 | 2025-06-26 | 2025-06-27 | 2025-07-08 | 2025-07-08 | 2025-07-07 | 12 | 12 | 222 | 222 | 222 | 222 | 0% | 100% | 92% | 100% | Green | [Closed] ahead of schedule;
DSFFLOW-401 | Closed | Upgrade, Expansion, Migration | Core Network | EPC | 152 | 152 | 62 | 2024-07-10 | 2024-07-10 | 2025-04-30 | 2025-12-12 | 2025-12-12 | 2025-06-23 | 520 | 520 | 2112 | 2112 | 1746.1 | 2112 | 0% | 41% | 67% | 83% | Red | [Closed] incomplete work; ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; feedback: opportunity for optimized effort baseline; late start;
DSFFLOW-2858 | Closed | Upgrade | BOS | Monetization Charging | 34 | 34 | 34 | 2025-05-09 | 2025-06-09 | 2025-07-16 | 2025-07-25 | 2025-07-25 | 2025-08-06 | 77 | 46 | 486 | 486 | 486 | 486 | 0% | 100% | 126% | 100% | Red | [Closed] schedule overrun > 10%; late start;
DSFFLOW-32 | Closed | Upgrade | Network Management | Element Management & Reporting | 57 | 31 | 31 | 2024-12-08 | 2024-12-08 | 2024-12-09 | 2025-02-17 | 2025-02-18 | 2025-02-17 | 71 | 72 | 910 | 459 | 457 | 457 | 0% | 100% | 99% | 100% | Green | [Closed] ahead of schedule;
DSFFLOW-1629 | Closed | Upgrade | Core Network | EPC, UDM, Signaling | 175 | 175 | 175 | 2025-04-01 | 2025-04-01 | 2025-06-03 | 2025-06-29 | 2025-06-29 | 2025-07-07 | 89 | 89 | 2725.1292 | 2725.1292 | 2134.05 | 2134.05 | 22% | 100% | 111% | 78% | Red | [Closed] schedule overrun > 10%; efforts saved; feedback: opportunity for optimized effort baseline; late start;
DSFFLOW-310 | Closed | Upgrade | Core Network | UDM | 19 | 19 | 19 | 2025-04-20 | 2025-04-20 | 2025-06-05 | 2025-05-31 | 2025-05-31 | 2025-06-05 | 41 | 41 | 267 | 267 | 315 | 315 | -18% | 100% | 113% | 118% | Red | [Closed] effort overrun > 1%; schedule overrun > 10%; late start;
DSFFLOW-2352 | Closed | Upgrade | Core Network | Signaling | 26 | 26 | 23 | 2025-06-02 | 2025-06-02 | 2025-06-27 | 2025-07-04 | 2025-07-30 | 2025-08-05 | 32 | 58 | 511 | 511 | 369 | 452 | 12% | 88% | 112% | 72% | Red | [Closed] incomplete work; schedule overrun > 10%; efforts saved; feedback: opportunity for optimized effort baseline; late start;
DSFFLOW-2947 | Closed | Upgrade | Core Network | MSS | 21 | 21 | 21 | 2025-03-18 | 2025-05-08 | 2025-05-08 | 2025-08-15 | 2025-07-15 | 2025-07-15 | 150 | 68 | 411.5 | 411.5 | 382.5 | 382.5 | 8% | 100% | 100% | 93% | Green | [Closed] efforts saved;
DSFFLOW-49 | Closed | Upgrade | Network Management | Element Management & Reporting | 30 | 30 | 30 | 2025-02-19 | 2025-02-20 | 2025-02-28 | 2025-08-29 | 2025-04-17 | 2025-03-27 | 191 | 56 | 488 | 488 | 430 | 430 | 12% | 100% | 63% | 88% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; feedback: opportunity for optimized effort baseline; late start;
DSFFLOW-2138 | Closed | Upgrade, Maiden Installation | Network Management | Resource Orchestration | 52 | 37 | 36 | 2025-06-12 | 2025-06-12 | 2025-06-18 | 2025-12-31 | 2025-08-31 | 2025-08-14 | 202 | 80 | 646.6497 | 559.9 | 412.9 | 425.65 | 24% | 97% | 79% | 74% | Red | [Closed] incomplete work; ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; feedback: opportunity for optimized effort baseline;
DSFFLOW-80 | Closed | Upgrade | Core Network | EPC, UDM, IMS | 176 | 150 | 150 | 2025-02-06 | 2025-02-06 | 2025-03-10 | 2025-06-06 | 2025-06-06 | 2025-06-05 | 120 | 120 | 1786 | 1786 | 1758 | 1758 | 2% | 100% | 99% | 98% | Green | [Closed] ahead of schedule; efforts saved; late start;
DSFFLOW-2813 | In Progress | Maiden Installation | Network Management | Resource Orchestration | 11 | 11 | 1 | 2025-05-04 | 2025-05-04 | 2025-07-10 | 2026-03-31 | 2026-03-31 |  | 331 | 331 | 1125 | 1125 | 241 | 1125 | 0% | 9% | 33% | 21% | Green | [In Prog] late start;
DSFFLOW-1864 | In Progress | Upgrade | Network Management | Element Management & Reporting | 35 | 35 | 35 | 2025-06-09 | 2025-06-09 | 2025-06-18 | 2025-12-31 | 2025-12-31 |  | 205 | 205 | 506 | 506 | 397 | 397 | 22% | 100% | 35% | 78% | Amber | [In Prog] efforts burnt misaligned with work progress; work progress misaligned with time progress; late start;
DSFFLOW-3730 | In Progress | Migration | Core Network | UDM | 16 | 15 | 0 | 2025-07-28 | 2025-07-28 | 2025-08-12 | 2025-10-31 | 2025-10-31 |  | 95 | 95 | 1283 | 1283 | 241.5 | 1283 | 0% | 0% | 24% | 19% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-1400 | In Progress | Maiden Installation | Core Network | EPC | 37 | 37 | 5 | 2023-05-22 | 2023-05-22 | 2025-05-27 | 2025-07-30 | 2025-07-30 |  | 800 | 800 | 1432 | 1432 | 376 | 1432 | 0% | 15% | 102% | 26% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-4396 | In Progress | Upgrade | Core Network | MSS | 43 | 43 | 7 | 2025-08-04 | 2025-08-04 | 2025-08-05 | 2025-10-06 | 2025-10-06 |  | 63 | 63 | 734 | 734 | 229.5 | 734 | 0% | 16% | 25% | 31% | Green | [In Prog]
DSFFLOW-1008 | In Progress | Upgrade | Network Management | Resource Orchestration | 26 | 25 | 22 | 2025-06-16 | 2025-06-03 | 2025-06-18 | 2025-08-30 | 2025-08-30 |  | 75 | 88 | 451 | 451 | 370.1 | 428 | 5% | 88% | 88% | 82% | Green | [In Prog] late start;
DSFFLOW-4124 | In Progress | Maiden Installation | Network Management | Element Management & Reporting | 113 | 113 | 6 | 2025-07-31 | 2025-07-31 | 2025-08-04 | 2026-01-30 | 2026-01-30 |  | 183 | 183 | 4680 | 4680 | 384 | 4664 | 0% | 5% | 11% | 8% | Green | [In Prog]
DSFFLOW-2901 | In Progress | Maiden Installation | Network Management | Resource Orchestration | 34 | 33 | 13 | 2025-06-01 | 2025-06-01 | 2025-07-08 | 2025-08-30 | 2025-08-30 |  | 90 | 90 | 777.75 | 777.75 | 248.75 | 742.75 | 5% | 39% | 88% | 32% | Amber | [In Prog] efforts burnt misaligned with time progress; late start;
DSFFLOW-1790 | In Progress | Upgrade | Core Network | Cloud | 85 | 85 | 35 | 2025-06-02 | 2025-06-02 | 2025-07-10 | 2026-03-31 | 2026-03-31 |  | 302 | 302 | 726 | 726 | 350 | 728 | 0% | 41% | 26% | 48% | Green | [In Prog] late start;
DSFFLOW-1614 | In Progress | Upgrade | Network Management | Resource Orchestration | 54 | 52 | 52 | 2025-05-28 | 2025-05-28 | 2025-06-04 | 2026-01-30 | 2026-01-30 |  | 247 | 247 | 299.7533 | 299.7533 | 300.12 | 300.12 | 0% | 100% | 34% | 100% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress;
DSFFLOW-2264 | In Progress | Upgrade, Maiden Installation | BOS | Monetization Charging | 571 | 571 | 3 | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2026-02-16 | 2026-02-16 |  | 245 | 245 | 5197.5 | 5197.5 | 341.5 | 5045 | 3% | 1% | 26% | 8% | Green | [In Prog]
DSFFLOW-3513 | In Progress | Maiden Installation | Network Management | Activation | 69 | 69 | 0 | 2025-07-11 | 2025-07-11 | 2025-07-24 | 2025-12-26 | 2025-12-26 |  | 168 | 168 | 3075.1 | 3075.1 | 255 | 3075.1 | 0% | 0% | 24% | 8% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-3311 | In Progress | Expansion | BOS | Monetization Charging | 415 | 415 | 50 | 2025-07-27 | 2025-07-27 | 2025-07-22 | 2025-09-30 | 2025-09-30 |  | 65 | 65 | 3078.6 | 3078.6 | 323.75 | 3028.1 | 2% | 12% | 36% | 11% | Green | [In Prog]
DSFFLOW-2610 | In Progress | Upgrade | Core Network | Signaling | 11 | 11 | 0 | 2025-06-27 | 2025-06-27 | 2025-07-02 | 2025-12-31 | 2025-12-31 |  | 187 | 187 | 605 | 605 | 320 | 605 | 0% | 0% | 29% | 53% | Red | [In Prog] efforts burning without any work progress; time ticking without any work progress;
DSFFLOW-662 | In Progress | Maiden Installation | Network Management | Resource Orchestration | 71 | 54 | 6 | 2025-03-04 | 2025-03-04 | 2025-06-05 | 2026-12-31 | 2026-12-31 |  | 667 | 667 | 914.7 | 515.0667 | 312.2167 | 847.7833 | -65% | 11% | 25% | 61% | Red | [In Prog] projecting 5%+ EAC effort overrun; efforts burnt outweighing work output; late start;
DSFFLOW-3562 | In Progress | Upgrade | Core Network | Cloud | 23 | 23 | 2 | 2025-07-23 | 2025-07-23 | 2025-07-23 | 2025-09-30 | 2025-09-30 |  | 69 | 69 | 844 | 844 | 312 | 872 | -3% | 9% | 40% | 37% | Amber | [In Prog] projecting 1%+ EAC effort overrun ; efforts burnt misaligned with work progress;
DSFFLOW-1697 | In Progress | Upgrade | Core Network | EPC | 30 | 21 | 20 | 2025-05-26 | 2025-05-26 | 2025-06-12 | 2025-08-31 | 2025-08-31 |  | 97 | 97 | 346 | 346 | 310 | 310 | 10% | 95% | 88% | 90% | Green | [In Prog] late start;
DSFFLOW-3836 | In Progress | Upgrade | Network Management | Activation | 48 | 48 | 18 | 2025-05-31 | 2025-05-31 | 2025-07-30 | 2025-09-29 | 2025-09-29 |  | 121 | 121 | 612 | 612 | 274 | 620 | -1% | 38% | 66% | 45% | Amber | [In Prog] projecting 1%+ EAC effort overrun ; late start;
DSFFLOW-3342 | In Progress | Upgrade | Network Management | Activation, Resource Orchestration | 145 | 140 | 15 | 2025-07-10 | 2025-07-10 | 2025-07-10 | 2025-11-21 | 2025-11-21 |  | 134 | 134 | 3933 | 3933 | 279.5 | 3864.5 | 2% | 11% | 30% | 8% | Green | [In Prog]
DSFFLOW-3060 | In Progress | Upgrade | Core Network | UDM | 71 | 71 | 10 | 2025-06-25 | 2025-06-25 | 2025-07-16 | 2025-11-28 | 2025-11-28 |  | 156 | 156 | 967 | 967 | 303 | 921 | 5% | 15% | 36% | 31% | Green | [In Prog] late start;
DSFFLOW-3498 | In Progress | Migration | Core Network | EPC, Signaling, UDM | 77 | 77 | 0 | 2025-06-18 | 2025-06-18 | 2025-07-23 | 2025-12-31 | 2025-12-31 |  | 196 | 196 | 1514.6 | 1514.6 | 292.5 | 1457.6 | 4% | 0% | 32% | 19% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-1151 | In Progress | Upgrade | BOS | Monetization Charging | 498 | 498 | 14 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2026-02-28 | 2026-02-28 |  | 272 | 272 | 3023 | 3023 | 368.5 | 2963 | 2% | 3% | 29% | 12% | Green | [In Prog]
DSFFLOW-3852 | In Progress | Migration | Core Network | Cloud | 118 | 118 | 0 | 2025-07-22 | 2025-07-22 | 2025-07-31 | 2025-12-31 | 2025-12-31 |  | 162 | 162 | 2002.5 | 2002.5 | 288 | 2002.5 | 0% | 0% | 18% | 15% | Green | [In Prog] late start;
DSFFLOW-245 | In Progress | Upgrade, Maiden Installation | Network Management | Element Management & Reporting | 869 | 573 | 36 | 2025-05-15 | 2025-04-07 |  | 2025-10-01 | 2025-10-01 |  | 139 | 177 | 24189 | 17322 | 11151 | 16314 | 6% | 6% | 76% | 64% | Red | [In Prog] efforts burnt outweighing work output; work progress misaligned with time progress;
DSFFLOW-4564 | In Progress | Upgrade | Core Network | Cloud | 32 | 32 | 0 | 2025-07-22 | 2025-07-22 | 2025-08-08 | 2026-01-15 | 2026-01-15 |  | 177 | 177 | 1211 | 1211 | 208 | 1193 | 1% | 0% | 16% | 17% | Green | [In Prog] late start;
DSFFLOW-2544 | In Progress | Maiden Installation | Core Network | Cloud-3PP/MPBN | 10 | 10 | 0 | 2025-04-19 | 2025-04-19 | 2025-06-26 | 2025-10-31 | 2025-10-31 |  | 195 | 195 | 1340 | 1340 | 66 | 1274 | 5% | 0% | 63% | 5% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-3327 | In Progress | Upgrade | Network Management | Resource Orchestration | 26 | 26 | 4 | 2025-07-15 | 2025-07-15 | 2025-07-21 | 2025-10-31 | 2025-10-31 |  | 108 | 108 | 334 | 334 | 58 | 334 | 0% | 15% | 33% | 17% | Green | [In Prog]
DSFFLOW-4794 | In Progress | Upgrade | Network Management | Element Management & Reporting | 23 | 18 | 3 | 2025-08-11 | 2025-08-11 | 2025-08-15 | 2025-08-28 | 2025-08-29 |  | 17 | 18 | 282 | 282 | 52 | 280 | 1% | 17% | 47% | 18% | Green | [In Prog]
DSFFLOW-4605 | In Progress | Upgrade | Core Network | Cloud | 127 | 127 | 0 | 2025-07-24 | 2025-07-24 | 2025-08-11 | 2026-12-31 | 2026-12-31 |  | 525 | 525 | 2196 | 2196 | 48 | 2196 | 0% | 0% | 5% | 2% | Green | [In Prog] late start;
DSFFLOW-4028 | In Progress | Maiden Installation | Core Network | Cloud | 33 | 33 | 0 | 2025-07-14 | 2025-07-14 | 2025-07-30 | 2025-09-05 | 2025-09-05 |  | 53 | 53 | 1736 | 1736 | 42 | 1694 | 2% | 0% | 69% | 2% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-4379 | In Progress | Upgrade | Network Management | Element Management & Reporting | 69 | 69 | 3 | 2025-08-03 | 2025-08-04 | 2025-08-04 | 2025-12-31 | 2025-12-31 |  | 150 | 149 | 1002.5 | 1002.5 | 41 | 995.5 | 1% | 4% | 11% | 4% | Green | [In Prog]
DSFFLOW-1679 | In Progress | Maiden Installation | Core Network | Cloud-3PP/MPBN | 11 | 11 | 0 | 2025-05-16 | 2025-05-16 | 2025-07-22 | 2026-12-31 | 2026-12-31 |  | 594 | 594 | 216 | 216 | 35.25 | 216 | 0% | 0% | 16% | 16% | Green | [In Prog] late start;
DSFFLOW-2336 | In Progress | Upgrade | Core Network | Signaling | 26 | 26 | 0 | 2025-06-02 | 2025-06-02 | 2025-06-27 | 2025-07-04 | 2025-08-15 |  | 32 | 74 | 364 | 364 | 35 | 359 | 1% | 0% | 105% | 10% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-1994 | In Progress | Upgrade | Network Management | Resource Orchestration | 39 | 38 | 4 | 2025-06-22 | 2025-06-22 | 2025-06-24 | 2025-07-10 | 2025-07-10 |  | 18 | 18 | 313.5 | 305.5 | 28 | 289.5 | 5% | 11% | 311% | 9% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress;
DSFFLOW-4760 | In Progress | Upgrade | Network Management | Resource Orchestration | 46 | 46 | 3 | 2025-08-12 | 2025-08-12 | 2025-08-14 | 2025-09-29 | 2025-09-29 |  | 48 | 48 | 200.08 | 200.08 | 17 | 200.08 | 0% | 8% | 16% | 8% | Green | [In Prog]
DSFFLOW-4694 | In Progress | Upgrade | Core Network | Cloud | 48 | 48 | 0 | 2025-07-13 | 2025-07-13 | 2025-08-12 | 2025-12-30 | 2025-12-30 |  | 170 | 170 | 2298 | 2298 | 15 | 2283 | 1% | 0% | 22% | 1% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-4498 | In Progress | Upgrade | Core Network | EPC, IMS, MSS, UDM | 210 | 210 | 0 | 2025-07-15 | 2025-07-15 | 2025-08-08 | 2026-01-15 | 2026-01-15 |  | 184 | 184 | 3907 | 3907 | 8.5 | 3898.5 | 0% | 0% | 19% | 0% | Green | [In Prog] late start;
DSFFLOW-970 | In Progress | Upgrade | Core Network | Cloud-3PP/MPBN | 16 | 16 | 0 | 2025-05-08 | 2025-05-08 | 2025-08-07 | 2025-07-29 | 2025-07-29 |  | 82 | 82 | 237.5 | 237.5 | 5 | 232.5 | 2% | 0% | 125% | 2% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-2765 | In Progress | Upgrade | Core Network | EPC, Cloud | 49 | 49 | 0 | 2024-11-11 | 2024-11-11 | 2025-07-07 | 2024-12-20 | 2024-12-20 |  | 39 | 39 | 1560 | 1560 | 1 | 1560 | 0% | 0% | 705% | 0% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-4483 | In Progress | Expansion | Core Network | EPC | 12 | 12 | 8 | 2025-08-18 | 2025-08-18 | 2025-08-06 | 2025-09-12 | 2025-09-12 |  | 25 | 25 | 161 | 161 | 1 | 161 | 0% | 67% | 8% | 1% | Green | [In Prog] work progress misaligned with time progress; early start;
DSFFLOW-2674 | In Progress | Maiden Installation | Core Network | EPC | 41 | 41 | 0 | 2024-05-01 | 2024-05-01 | 2025-07-10 | 2025-09-30 | 2025-09-30 |  | 517 | 517 | 1454 | 1454 |  | 1454 | 0% | 0% | 92% | 0% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-4260 | In Progress | Upgrade | Core Network | Cloud | 84 | 84 | 6 | 2025-07-06 | 2025-07-06 | 2025-08-05 | 2025-11-29 | 2025-11-29 |  | 146 | 146 | 1912 | 1912 |  | 1584 | 17% | 8% | 31% | 0% | Green | [In Prog] late start;
DSFFLOW-2843 | In Progress | Migration | BOS | Common Services-Data Migration | 10 | 10 | 0 | 2025-06-16 | 2025-06-16 | 2025-06-17 | 2026-12-31 | 2026-12-31 |  | 563 | 563 | 1 | 1 |  | 1 | 0% | 0% | 12% | 0% | Green | [In Prog]
DSFFLOW-4361 | In Progress | Upgrade | Core Network | Cloud, EPC | 141 | 141 | 0 | 2025-06-19 | 2025-06-19 | 2025-08-10 | 2025-12-19 | 2025-12-19 |  | 183 | 183 | 3597 | 3597 |  | 3597 | 0% | 0% | 34% | 0% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-3596 | In Progress | Upgrade | Core Network | UDM | 36 | 36 | 2 | 2025-07-21 | 2025-07-21 | 2025-07-24 | 2025-09-12 | 2025-09-12 |  | 53 | 53 | 481.5 | 481.5 | 66 | 481.5 | 0% | 6% | 57% | 15% | Green | [In Prog] work progress misaligned with time progress;
DSFFLOW-3029 | In Progress | Migration | Core Network | IMS | 20 | 20 | 2 | 2025-05-07 | 2025-05-07 | 2025-07-14 | 2025-12-31 | 2025-12-31 |  | 238 | 238 | 902 | 902 | 216 | 902 | 0% | 10% | 44% | 24% | Green | [In Prog] late start;
DSFFLOW-4055 | In Progress | Upgrade | Network Management | Element Management & Reporting | 26 | 19 | 10 | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-09-30 | 2025-09-30 |  | 57 | 57 | 328 | 328 | 86.02 | 318.02 | 3% | 53% | 29% | 26% | Amber | [In Prog] efforts burnt misaligned with work progress;
DSFFLOW-4442 | In Progress | Upgrade | Network Management | Element Management & Reporting | 25 | 25 | 2 | 2025-07-27 | 2025-07-27 | 2025-08-06 | 2025-09-18 | 2025-09-18 |  | 53 | 53 | 418.2 | 418.2 | 102 | 418.2 | 0% | 8% | 44% | 24% | Green | [In Prog] late start;
DSFFLOW-535 | In Progress | Maiden Installation | Core Network | EPC | 14 | 14 | 13 | 2025-01-01 | 2024-12-31 | 2025-01-01 | 2025-07-31 | 2025-05-29 | 2025-04-30 | 211 | 149 | 149 | 149 | 206 | 198 | -33% | 93% | 81% | 138% | Red | [In Prog] effort budget breached; projecting 5%+ EAC effort overrun; efforts burnt misaligned with work progress; efforts burnt misaligned with time progress;
DSFFLOW-3093 | In Progress | Expansion | Core Network | Cloud | 89 | 89 | 16 | 2025-06-04 | 2025-06-04 | 2025-07-15 | 2026-03-31 | 2026-03-31 |  | 300 | 300 | 2265.5 | 2265.5 | 397 | 2223.5 | 2% | 18% | 26% | 18% | Green | [In Prog] late start;
DSFFLOW-2962 | In Progress | Maiden Installation | Core Network | Cloud | 101 | 101 | 0 | 2025-07-07 | 2025-07-07 | 2025-08-05 | 2025-12-30 | 2025-12-30 |  | 176 | 176 | 1816 | 1816 | 192.0008 | 1816 | 0% | 0% | 25% | 11% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-2435 | In Progress | Upgrade | Core Network | EPC | 16 | 16 | 0 | 2025-06-16 | 2025-06-16 | 2025-07-07 | 2025-06-30 | 2025-06-30 |  | 14 | 14 | 558 | 558 | 192 | 558 | 0% | 0% | 433% | 34% | Amber | [In Prog] time ticking without any work progress; efforts burnt misaligned with work progress; late start;
DSFFLOW-4299 | In Progress | Upgrade | Core Network | Cloud, EPC, UDM | 88 | 88 | 0 | 2025-07-21 | 2025-07-21 | 2025-08-06 | 2025-10-31 | 2025-10-31 |  | 102 | 102 | 1686 | 1686 | 182.75 | 1677.5 | 1% | 0% | 29% | 11% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-4677 | In Progress | Maiden Installation | Core Network | EPC | 127 | 127 | 0 | 2025-08-11 | 2025-08-11 | 2025-08-11 | 2026-12-31 | 2026-12-31 |  | 507 | 507 | 10485.6 | 10485.6 | 178 | 10485.6 | 0% | 0% | 2% | 2% | Green | [In Prog]
DSFFLOW-4213 | In Progress | Upgrade | Core Network | IMS | 80 | 80 | 1 | 2025-07-25 | 2025-07-25 | 2025-08-01 | 2025-10-31 | 2025-10-31 |  | 98 | 98 | 1036 | 1036 | 173.45 | 1032 | 0% | 1% | 26% | 17% | Green | [In Prog]
DSFFLOW-4343 | In Progress | Upgrade | Core Network | Cloud, EPC | 141 | 141 | 0 | 2025-06-19 | 2025-06-19 | 2025-08-18 | 2025-12-19 | 2025-12-19 |  | 183 | 183 | 3597 | 3597 | 168 | 3481 | 3% | 0% | 34% | 5% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-591 | In Progress | Upgrade | Core Network | Cloud-3PP/MPBN | 15 | 15 | 1 | 2025-04-22 | 2025-04-22 | 2025-06-05 | 2025-06-30 | 2025-06-30 |  | 69 | 69 | 248 | 248 | 143 | 187.5 | 24% | 8% | 171% | 58% | Amber | [In Prog] efforts burnt misaligned with work progress; efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-3685 | In Progress | Upgrade | Core Network | MSS | 24 | 24 | 3 | 2025-06-30 | 2025-06-27 | 2025-06-27 | 2025-09-14 | 2025-09-14 | 2025-09-14 | 76 | 79 | 434.5 | 434.5 | 129 | 434.5 | 0% | 13% | 100% | 30% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress; actual End Date exceeds Today;
DSFFLOW-3812 | In Progress | Upgrade | Core Network | Cloud | 36 | 36 | 4 | 2025-05-05 | 2025-05-05 | 2025-07-28 | 2025-12-30 | 2025-12-30 |  | 239 | 239 | 785 | 785 | 129 | 776 | 1% | 11% | 45% | 16% | Green | [In Prog] late start;
DSFFLOW-3715 | In Progress | Upgrade | Core Network | MSS | 15 | 15 | 3 | 2025-06-10 | 2025-06-10 | 2025-07-25 | 2025-08-30 | 2025-08-30 |  | 81 | 81 | 187 | 187 | 127.5 | 187 | 0% | 20% | 87% | 68% | Amber | [In Prog] efforts burnt misaligned with work progress; work progress misaligned with time progress; late start;
DSFFLOW-4744 | In Progress | Maiden Installation | Core Network | EPC, UDM | 25 | 25 | 1 | 2025-02-11 | 2025-02-11 | 2025-08-14 | 2025-12-31 | 2025-12-31 |  | 323 | 323 | 1001 | 1001 | 124 | 1001 | 0% | 4% | 59% | 12% | Green | [In Prog] work progress misaligned with time progress; late start;
DSFFLOW-2708 | In Progress | Upgrade | Core Network | Cloud, Signaling | 14 | 14 | 3 | 2025-06-01 | 2025-06-01 | 2025-07-04 | 2025-10-31 | 2025-10-31 |  | 152 | 152 | 315 | 315 | 121 | 308 | 2% | 21% | 52% | 38% | Green | [In Prog] late start;
DSFFLOW-4411 | In Progress | Upgrade | Network Management | Element Management & Reporting | 34 | 32 | 9 | 2025-08-06 | 2025-08-06 | 2025-08-11 | 2025-09-30 | 2025-09-30 |  | 55 | 55 | 515.95 | 481.95 | 114 | 349.45 | 27% | 29% | 25% | 24% | Green | [In Prog]
DSFFLOW-4230 | In Progress | Upgrade | Core Network | Cloud | 17 | 17 | 8 | 2025-08-03 | 2025-08-03 | 2025-08-04 | 2025-08-21 | 2025-08-21 |  | 18 | 18 | 216 | 216 | 112 | 192 | 11% | 47% | 89% | 52% | Green | [In Prog]
DSFFLOW-3127 | In Progress | Upgrade | Core Network | EPC | 57 | 57 | 0 | 2025-06-21 | 2025-06-21 | 2025-07-25 | 2025-08-30 | 2025-08-30 |  | 70 | 70 | 638 | 638 | 112 | 622 | 3% | 0% | 85% | 18% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-4198 | In Progress | Upgrade | Core Network | UDM | 16 | 16 | 4 | 2025-07-30 | 2025-08-01 | 2025-08-04 | 2025-09-15 | 2025-09-15 |  | 47 | 45 | 506 | 506 | 110.5 | 471.5 | 8% | 25% | 41% | 22% | Green | [In Prog]
DSFFLOW-3078 | In Progress | Upgrade | Core Network | UDM | 27 | 27 | 1 | 2025-07-02 | 2025-07-03 | 2025-07-03 | 2025-09-01 | 2025-09-19 | 2025-09-19 | 61 | 78 | 656 | 656 | 110.5 | 655.5 | 0% | 4% | 100% | 17% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress; actual End Date exceeds Today;
DSFFLOW-4245 | In Progress | Upgrade | Network Management | Activation, Element Management & Reporting, Resource Orchestration | 41 | 41 | 2 | 2025-07-21 | 2025-07-21 | 2025-08-06 | 2025-09-30 | 2025-09-30 |  | 71 | 71 | 461.9 | 461.9 | 91.89 | 461.9 | 0% | 5% | 42% | 20% | Green | [In Prog] late start;
DSFFLOW-2575 | In Progress | Maiden Installation | Core Network | Cloud | 32 | 32 | 2 | 2025-06-23 | 2025-06-23 | 2025-07-14 | 2025-12-01 | 2025-12-01 |  | 161 | 161 | 1262 | 1262 | 200 | 1221 | 3% | 6% | 36% | 16% | Green | [In Prog] late start;
DSFFLOW-3745 | In Progress | Migration | Core Network | UDM | 15 | 14 | 0 | 2025-07-28 | 2025-07-28 | 2025-08-12 | 2025-12-26 | 2025-12-26 |  | 151 | 151 | 2080 | 2080 | 363.5 | 2080 | 0% | 0% | 15% | 17% | Green | [In Prog] late start;
DSFFLOW-4588 | In Progress | Maiden Installation | Core Network | Core Network Automation, EPC, UDM | 73 | 73 | 0 | 2025-07-30 | 2025-07-30 | 2025-08-08 | 2026-06-30 | 2026-06-30 |  | 335 | 335 | 1961 | 1961 |  | 1956 | 0% | 0% | 6% | 0% | Green | [In Prog] late start;
DSFFLOW-64 | In Progress | Upgrade | Network Management | Element Management & Reporting | 50 | 48 | 36 | 2025-03-02 | 2025-03-02 | 2025-03-13 | 2025-08-30 | 2025-08-30 |  | 181 | 181 | 1180.12 | 1180.12 | 1082.5097 | 1040.6197 | 12% | 75% | 94% | 92% | Green | [In Prog] late start;
DSFFLOW-677 | In Progress | Upgrade | Core Network | IMS | 101 | 101 | 67 | 2025-04-24 | 2025-04-24 | 2025-04-14 | 2025-12-31 | 2025-12-31 | 2025-09-30 | 251 | 251 | 1584 | 1584 | 1058 | 1504 | 5% | 66% | 63% | 67% | Green | [In Prog] early start; actual End Date exceeds Today;
DSFFLOW-993 | In Progress | Maiden Installation | Core Network | UDM | 40 | 40 | 10 | 2025-02-10 | 2025-02-10 | 2025-02-10 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 324 | 324 | 1955 | 1955 | 1025 | 1676 | 15% | 25% | 100% | 52% | Amber | [In Prog] efforts burnt misaligned with work progress; work progress misaligned with time progress; actual End Date exceeds Today;
DSFFLOW-2009 | In Progress | Upgrade | Core Network | Cloud, EPC, IMS, UDM | 172 | 172 | 120 | 2025-04-29 | 2025-04-29 | 2025-06-23 | 2026-03-31 | 2026-03-31 |  | 336 | 336 | 3200 | 3200 | 2637.5 | 3011 | 6% | 70% | 34% | 82% | Green | [In Prog] late start;
DSFFLOW-2882 | In Progress | Upgrade | BOS | D&A Mediation, Monetization Billing | 37 | 37 | 3 | 2025-05-10 | 2025-05-10 | 2025-07-10 | 2025-11-18 | 2025-11-18 |  | 192 | 192 | 2844.2497 | 2844.2497 | 1011.5 | 2750.8497 | 3% | 8% | 53% | 36% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-4140 | In Progress | Upgrade | Core Network | Cloud, EPC, IMS, UDM | 97 | 97 | 0 | 2025-04-16 | 2025-04-16 | 2025-08-01 | 2025-12-30 | 2025-12-30 |  | 258 | 258 | 2201 | 2201 | 980 | 2105 | 4% | 0% | 49% | 45% | Amber | [In Prog] time ticking without any work progress; efforts burnt misaligned with work progress; late start;
DSFFLOW-1278 | In Progress | Migration | Core Network | IMS | 353 | 341 | 139 | 2025-05-08 | 2025-05-08 | 2025-05-22 | 2025-09-15 | 2025-09-19 | 2025-09-19 | 130 | 134 | 4478.5 | 4478.5 | 2641.3458 | 4014.5758 | 10% | 41% | 100% | 59% | Green | [In Prog] work progress misaligned with time progress; late start; actual End Date exceeds Today;
DSFFLOW-1119 | In Progress | Upgrade | Network Management | Element Management & Reporting | 161 | 160 | 37 | 2025-05-15 | 2025-05-21 | 2025-06-02 | 2025-12-31 | 2025-12-31 |  | 230 | 224 | 3306 | 3298 | 1090.5 | 2875 | 13% | 23% | 40% | 33% | Green | [In Prog] late start;
DSFFLOW-3760 | In Progress | Maiden Installation | Core Network | Signaling, UDM | 29 | 29 | 0 | 2025-03-31 | 2025-03-31 | 2025-07-29 | 2026-03-31 | 2026-03-31 |  | 365 | 365 | 6752 | 6752 | 904 | 6752 | 0% | 0% | 39% | 13% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-1568 | In Progress | Upgrade | BOS | D&A Mediation | 33 | 33 | 9 | 2025-05-25 | 2025-05-25 | 2025-06-30 | 2025-08-28 | 2025-08-28 |  | 95 | 95 | 1614.5 | 1614.5 | 886.8933 | 1634.89 | -1% | 27% | 91% | 57% | Amber | [In Prog] projecting 1%+ EAC effort overrun ; efforts burnt misaligned with work progress; work progress misaligned with time progress; late start;
DSFFLOW-3109 | In Progress | Upgrade | Core Network | IMS | 150 | 148 | 33 | 2025-07-14 | 2025-07-14 | 2025-07-14 | 2025-08-29 | 2025-08-29 | 2025-08-29 | 46 | 46 | 2101 | 2101 | 881.76 | 1939.26 | 8% | 22% | 100% | 42% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress; actual End Date exceeds Today;
DSFFLOW-1103 | In Progress | Maiden Installation | Core Network, Network Management | EPC, Resource Orchestration | 44 | 44 | 33 | 2025-05-16 | 2025-05-16 | 2025-05-19 | 2025-08-30 | 2025-08-30 |  | 106 | 106 | 938 | 938 | 863 | 892 | 5% | 75% | 90% | 92% | Green | [In Prog]
DSFFLOW-1713 | In Progress | Upgrade | Core Network | UDM | 18 | 18 | 2 | 2025-03-15 | 2025-03-15 | 2025-07-21 | 2025-07-30 | 2025-07-30 |  | 137 | 137 | 2328 | 2328 | 858 | 2328 | 0% | 11% | 114% | 37% | Amber | [In Prog] efforts burnt misaligned with work progress; efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-4085 | In Progress | Upgrade | Core Network | Cloud | 206 | 206 | 11 | 2025-07-07 | 2025-07-07 | 2025-08-04 | 2025-11-14 | 2025-11-14 |  | 130 | 130 | 7116.98 | 7116.98 | 838.59 | 7021.91 | 1% | 5% | 34% | 12% | Green | [In Prog] late start;
DSFFLOW-4778 | In Progress | Upgrade | Core Network | EPC, IMS, Signaling | 70 | 70 | 49 | 2025-06-22 | 2025-06-22 | 2025-08-14 | 2025-08-30 | 2025-08-30 |  | 69 | 69 | 1167 | 1167 | 752 | 1030 | 12% | 70% | 84% | 64% | Green | [In Prog] late start;
DSFFLOW-576 | In Progress | Upgrade | BOS | Monetization Billing | 34 | 34 | 17 | 2025-03-03 | 2025-03-03 | 2025-05-13 | 2025-08-14 | 2025-10-10 |  | 164 | 221 | 8446.6 | 8446.6 | 4286.6 | 8237.3167 | 2% | 50% | 77% | 51% | Green | [In Prog] late start;
DSFFLOW-2656 | In Progress | Upgrade | Network Management | Element Management & Reporting | 98 | 98 | 39 | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-12-19 | 2025-12-19 |  | 171 | 171 | 2840 | 2840 | 903.7333 | 2817 | 1% | 40% | 29% | 32% | Green | [In Prog]
DSFFLOW-1662 | In Progress | Upgrade | Network Management | Element Management & Reporting | 67 | 67 | 36 | 2025-05-07 | 2025-07-14 | 2025-06-06 | 2025-07-31 | 2025-09-15 | 2025-09-15 | 85 | 63 | 1440 | 1440 | 738 | 1355 | 6% | 54% | 100% | 51% | Green | [In Prog] early start; actual End Date exceeds Today;
DSFFLOW-3044 | In Progress | Maiden Installation | Core Network, Network Management | Activation, Signaling, UDM | 263 | 263 | 42 | 2025-07-09 | 2025-07-09 | 2025-07-15 | 2025-12-31 | 2025-12-31 |  | 175 | 175 | 3496 | 3496 | 1105.1 | 3432 | 2% | 16% | 24% | 32% | Green | [In Prog]
DSFFLOW-1911 | In Progress | Migration | Core Network | EPC | 41 | 41 | 19 | 2025-04-03 | 2025-04-03 | 2025-06-13 | 2025-11-30 | 2025-11-30 |  | 241 | 241 | 3433 | 3433 | 1148 | 3433 | 0% | 46% | 57% | 33% | Green | [In Prog] late start;
DSFFLOW-2402 | In Progress | Upgrade | BOS | Monetization Charging | 169 | 169 | 24 | 2025-05-05 | 2025-05-05 | 2025-07-08 | 2026-06-29 | 2026-06-30 |  | 420 | 421 | 18647.44 | 18647.44 | 2017.5 | 17668 | 5% | 15% | 25% | 11% | Green | [In Prog] late start;
DSFFLOW-115 | In Progress | Upgrade | Network Management | Element Management & Reporting | 192 | 181 | 81 | 2025-03-16 | 2025-03-17 | 2025-03-27 | 2025-06-29 | 2025-08-29 |  | 105 | 165 | 3732 | 3580 | 1948 | 2722 | 24% | 45% | 94% | 54% | Green | [In Prog] late start;
DSFFLOW-1307 | In Progress | Expansion | BOS | Monetization Charging | 161 | 161 | 155 | 2025-05-11 | 2025-05-11 | 2025-05-11 | 2025-08-21 | 2025-08-21 |  | 102 | 102 | 3979.5 | 3979.5 | 1943.5167 | 2756.0167 | 31% | 96% | 98% | 49% | Amber | [In Prog] efforts burnt misaligned with work progress;
DSFFLOW-1584 | In Progress | Maiden Installation | Core Network, Network Management | Activation, Core Network Automation, EPC, IMS, Resource Orchestration, UDM | 53 | 53 | 39 | 2025-05-12 | 2025-05-12 | 2025-05-12 | 2025-09-15 | 2025-09-15 |  | 126 | 126 | 2633.99 | 2633.99 | 1933 | 2607.25 | 1% | 74% | 79% | 73% | Green | [In Prog]
DSFFLOW-2123 | In Progress | Maiden Installation | Core Network, Network Management | Activation, Core Network Automation, EPC, Exposure, UDM | 81 | 81 | 18 | 2025-05-07 | 2025-05-07 | 2025-06-20 | 2026-10-30 | 2026-10-30 |  | 541 | 541 | 5900 | 5900 | 1876 | 5735 | 3% | 22% | 19% | 32% | Green | [In Prog] late start;
DSFFLOW-3475 | In Progress | Upgrade | Core Network | EPC, IMS, Signaling, UDM | 190 | 190 | 20 | 2025-04-30 | 2025-04-30 | 2025-05-05 | 2025-09-29 | 2025-09-29 |  | 152 | 152 | 3427.5 | 3427.5 | 1781.25 | 3235.5 | 6% | 11% | 73% | 52% | Amber | [In Prog] efforts burnt misaligned with work progress; work progress misaligned with time progress;
DSFFLOW-2078 | In Progress | Upgrade, Maiden Installation | Core Network | EPC, IMS | 46 | 46 | 39 | 2025-04-03 | 2025-04-03 | 2025-06-17 | 2025-09-06 | 2025-09-06 |  | 156 | 156 | 1930 | 1930 | 2306 | 2434 | -26% | 85% | 89% | 119% | Red | [In Prog] effort budget breached; projecting 5%+ EAC effort overrun; efforts burnt misaligned with work progress; late start;
DSFFLOW-2641 | In Progress | Upgrade | Network Management | Element Management & Reporting | 24 | 24 | 9 | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-09-29 | 2025-09-29 |  | 90 | 90 | 850 | 850 | 405.7 | 804.8 | 5% | 38% | 57% | 48% | Green | [In Prog]
DSFFLOW-2513 | In Progress | Maiden Installation | Core Network | EPC, Signaling | 46 | 46 | 0 | 2024-07-25 | 2024-07-25 | 2025-07-24 | 2025-12-31 | 2025-12-31 |  | 524 | 524 | 1896 | 1896 | 1584 | 1736 | 8% | 0% | 74% | 84% | Red | [In Prog] efforts burning without any work progress; time ticking without any work progress; late start;
DSFFLOW-4070 | In Progress | Maiden Installation | BOS | Core Commerce, D&A Mediation, Monetization Billing | 60 | 60 | 0 | 2025-06-06 | 2025-06-06 | 2025-07-31 | 2027-12-31 | 2027-12-31 |  | 938 | 938 | 48905.4997 | 48905.4997 | 1384.75 | 48677.4997 | 0% | 0% | 8% | 3% | Green | [In Prog] late start; Delivery Manager not assigned
DSFFLOW-2047 | In Progress | Upgrade | Network Management | Element Management & Reporting | 360 | 360 | 40 | 2025-05-08 | 2025-05-08 | 2025-06-18 | 2026-08-31 | 2026-08-31 |  | 480 | 480 | 9297 | 9297 | 1333 | 9222 | 1% | 11% | 22% | 15% | Green | [In Prog] late start;
DSFFLOW-2724 | In Progress | Migration | Core Network, Network Management | Cloud, Core Network Automation, EPC, IMS, MSS, Resource Orchestration, UDM | 68 | 68 | 11 | 2025-06-01 | 2025-06-01 | 2025-07-07 | 2025-09-29 | 2025-09-29 |  | 120 | 120 | 10250 | 10250 | 2415 | 10170 | 1% | 16% | 66% | 24% | Green | [In Prog] work progress misaligned with time progress; late start;
DSFFLOW-862 | In Progress | Upgrade | Core Network | MSS | 63 | 63 | 18 | 2025-05-05 | 2025-05-05 | 2025-05-19 | 2025-12-31 | 2025-12-31 |  | 240 | 240 | 2474.75 | 2474.75 | 1252.1 | 2514.75 | -2% | 29% | 44% | 51% | Amber | [In Prog] projecting 1%+ EAC effort overrun ; efforts burnt misaligned with work progress; late start;
DSFFLOW-151 | In Progress | Upgrade | Network Management | Element Management & Reporting | 87 | 79 | 50 | 2025-04-13 | 2025-04-13 | 2025-04-13 | 2025-07-30 | 2025-08-31 |  | 108 | 140 | 1719 | 1637 | 1246 | 1487 | 9% | 63% | 91% | 76% | Green | [In Prog]
DSFFLOW-1416 | In Progress | Migration | Core Network, Network Management | Activation, EPC, IMS, MSS, UDM | 155 | 155 | 16 | 2025-04-23 | 2025-04-23 | 2025-05-27 | 2025-12-31 | 2025-12-31 |  | 252 | 252 | 8449.25 | 8449.25 | 2600.005 | 8234.75 | 3% | 10% | 47% | 31% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-2384 | In Progress | Upgrade | Network Management | Resource Orchestration | 12 | 12 | 4 | 2025-06-16 | 2025-06-01 | 2025-06-24 | 2026-06-30 | 2026-12-31 |  | 379 | 578 | 4016.25 | 4016.25 | 1236.75 | 4016.25 | 0% | 33% | 15% | 31% | Green | [In Prog] late start; Delivery Manager not assigned
DSFFLOW-2529 | In Progress | Maiden Installation | Core Network | Cloud, EPC, IMS, MSS, UDM | 15 | 15 | 4 | 2025-06-24 | 2025-06-24 | 2025-06-26 | 2025-08-29 | 2025-08-29 |  | 66 | 66 | 2325 | 2325 | 2322 | 2318 | 0% | 27% | 85% | 100% | Red | [In Prog] efforts burnt outweighing work output; work lagging as effort nears budget; work progress misaligned with time progress;
DSFFLOW-206 | In Progress | Upgrade | Core Network | IMS | 214 | 196 | 80 | 2025-02-16 | 2025-02-16 | 2025-04-22 | 2025-12-18 | 2025-12-18 | 2025-10-31 | 305 | 305 | 3892 | 3892 | 2134.5 | 3881.6 | 0% | 41% | 84% | 57% | Green | [In Prog] late start; actual End Date exceeds Today; Delivery Manager not assigned
DSFFLOW-1041 | In Progress | Maiden Installation | Core Network | IMS | 17 | 13 | 13 | 2025-05-14 | 2025-05-14 | 2025-05-16 | 2027-04-30 | 2027-04-30 | 2025-06-27 | 716 | 716 | 728 | 728 | 728 | 604 | 17% | 100% | 6% | 100% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress;
DSFFLOW-2482 | In Progress | Expansion | Core Network | EPC | 24 | 24 | 2 | 2025-06-09 | 2025-06-09 | 2025-06-24 | 2025-12-12 | 2025-12-12 |  | 186 | 186 | 816 | 816 | 707 | 763 | 6% | 8% | 39% | 87% | Red | [In Prog] efforts burnt outweighing work output; late start;
DSFFLOW-3396 | In Progress | Maiden Installation | BOS | Monetization Billing | 19 | 19 | 10 | 2025-06-15 | 2025-06-15 | 2025-07-28 | 2025-07-31 | 2025-10-10 |  | 46 | 117 | 620.5 | 620.5 | 527 | 561 | 10% | 53% | 57% | 85% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-3142 | In Progress | Maiden Installation | Core Network | Cloud | 115 | 115 | 0 | 2025-07-06 | 2025-07-06 | 2025-07-15 | 2025-09-14 | 2025-09-14 |  | 70 | 70 | 2441.85 | 2441.85 | 518 | 2403.85 | 2% | 0% | 63% | 21% | Amber | [In Prog] time ticking without any work progress; efforts burnt misaligned with work progress; late start;
DSFFLOW-741 | In Progress | Upgrade | Network Management | Element Management & Reporting | 159 | 159 | 148 | 2025-04-22 | 2025-04-22 | 2025-05-19 | 2025-08-31 | 2025-08-31 |  | 131 | 131 | 4986 | 4986 | 4740.8333 | 5211.8333 | -5% | 93% | 91% | 95% | Red | [In Prog] projecting 5%+ EAC effort overrun; late start;
DSFFLOW-2234 | In Progress | Upgrade | Network Management | Element Management & Reporting | 38 | 38 | 38 | 2025-06-17 | 2025-06-17 | 2025-06-30 | 2025-10-31 | 2025-10-31 |  | 136 | 136 | 652 | 652 | 501 | 501 | 23% | 100% | 47% | 77% | Amber | [In Prog] efforts burnt misaligned with work progress; work progress misaligned with time progress; late start;
DSFFLOW-798 | In Progress | Maiden Installation | Core Network | Cloud | 77 | 77 | 0 | 2025-05-05 | 2025-04-01 | 2025-06-03 | 2025-12-30 | 2026-03-20 |  | 239 | 353 | 6839 | 6839 | 487.75 | 7613.5 | -11% | 0% | 40% | 8% | Red | [In Prog] projecting 5%+ EAC effort overrun; time ticking without any work progress; late start;
DSFFLOW-1729 | In Progress | Upgrade | Network Management | Element Management & Reporting | 67 | 64 | 24 | 2025-05-07 | 2025-05-07 | 2025-06-09 | 2025-10-31 | 2025-10-31 |  | 177 | 177 | 1240 | 1200 | 487 | 1187 | 1% | 38% | 59% | 41% | Green | [In Prog] late start;
DSFFLOW-447 | In Progress | Upgrade | BOS | Monetization Billing | 37 | 37 | 15 | 2025-04-01 | 2025-04-01 | 2025-05-20 | 2025-12-05 | 2025-12-05 |  | 248 | 248 | 10676.2 | 10676.2 | 5801.8997 | 9951.2 | 8% | 41% | 57% | 54% | Green | [In Prog] late start;
DSFFLOW-1263 | In Progress | Maiden Installation | Core Network | EPC | 36 | 36 | 6 | 2025-05-11 | 2025-05-11 | 2025-07-11 | 2025-08-01 | 2025-08-01 |  | 82 | 82 | 871 | 871 | 527.25 | 823 | 6% | 17% | 122% | 61% | Amber | [In Prog] efforts burnt misaligned with work progress; efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-1840 | In Progress | Upgrade | Network Management | Element Management & Reporting | 1221 | 1221 | 521 | 2025-06-08 | 2025-06-08 | 2025-06-23 | 2025-11-29 | 2025-11-29 |  | 174 | 174 | 17146.71 | 17146.71 | 7383.3644 | 16921.5111 | 1% | 43% | 42% | 43% | Green | [In Prog] late start;
DSFFLOW-760 | In Progress | Upgrade | BOS | D&A Mediation, Monetization Charging | 2546 | 2546 | 608 | 2025-04-08 | 2025-04-08 | 2025-05-12 | 2026-04-20 | 2026-04-20 |  | 377 | 377 | 30976.4 | 30976.4 | 8298.6617 | 29533.8117 | 5% | 24% | 35% | 27% | Green | [In Prog] late start;
DSFFLOW-462 | In Progress | Upgrade | Core Network | MSS | 28 | 28 | 10 | 2025-03-17 | 2025-03-17 | 2025-04-30 | 2025-06-30 | 2025-06-30 |  | 105 | 105 | 469 | 469 | 469 | 831 | -77% | 36% | 147% | 100% | Red | [In Prog] projecting 5%+ EAC effort overrun; efforts burnt outweighing work output; work lagging as effort nears budget; work progress misaligned with time progress; late start;
DSFFLOW-1599 | In Progress | Upgrade | Network Management | Element Management & Reporting | 63 | 63 | 17 | 2025-05-15 | 2025-05-15 | 2025-06-24 | 2025-08-29 | 2025-09-30 |  | 106 | 138 | 1102 | 1102 | 458.5 | 918.5 | 17% | 27% | 70% | 42% | Green | [In Prog] late start;
DSFFLOW-3870 | In Progress | Expansion | Core Network | Cloud | 62 | 62 | 15 | 2025-07-14 | 2025-07-14 | 2025-07-29 | 2025-12-24 | 2025-12-24 |  | 163 | 163 | 727.94 | 727.94 | 458.2697 | 727.9397 | 0% | 24% | 23% | 63% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-952 | In Progress | Migration | Core Network | UDM | 18 | 17 | 4 | 2025-05-12 | 2025-05-12 | 2025-05-12 | 2025-06-29 | 2025-06-29 |  | 48 | 48 | 542.75 | 542.75 | 446.25 | 542.75 | 0% | 24% | 204% | 82% | Red | [In Prog] efforts burnt outweighing work output; efforts burnt misaligned with time progress; work progress misaligned with time progress;
DSFFLOW-3786 | In Progress | Maiden Installation | Core Network | EPC, UDM | 29 | 29 | 0 | 2025-03-31 | 2025-03-31 | 2025-07-29 | 2026-03-31 | 2026-03-31 |  | 365 | 365 | 10283 | 10283 | 440 | 10283 | 0% | 0% | 39% | 4% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-2593 | In Progress | Maiden Installation | Core Network | EPC | 16 | 16 | 2 | 2025-05-25 | 2025-05-25 | 2025-07-02 | 2025-12-31 | 2025-12-31 |  | 220 | 220 | 2581 | 2581 | 439 | 2551 | 1% | 13% | 39% | 17% | Green | [In Prog] late start;
DSFFLOW-2219 | In Progress | Expansion | Core Network | Cloud | 37 | 35 | 25 | 2025-06-09 | 2025-06-09 | 2025-06-18 | 2025-12-12 | 2025-12-12 |  | 186 | 186 | 517.35 | 502.35 | 476.35 | 498.85 | 1% | 71% | 39% | 95% | Red | [In Prog] work lagging as effort nears budget; efforts burnt misaligned with work progress; efforts burnt misaligned with time progress; late start;
DSFFLOW-611 | In Progress | Maiden Installation | Core Network | EPC | 58 | 58 | 0 | 2025-02-10 | 2025-02-10 | 2025-07-21 | 2025-12-31 | 2025-12-31 |  | 324 | 324 | 2055 | 2055 | 727 | 1899 | 8% | 0% | 59% | 35% | Amber | [In Prog] time ticking without any work progress; efforts burnt misaligned with work progress; late start;
DSFFLOW-2467 | In Progress | Upgrade | BOS | D&A Mediation | 25 | 25 | 3 | 2025-06-11 | 2025-06-11 | 2025-06-26 | 2025-11-30 | 2025-11-30 |  | 172 | 172 | 1232.5 | 1232.5 | 528 | 1155.35 | 6% | 12% | 40% | 43% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-2689 | In Progress | Upgrade | Network Management | Element Management & Reporting | 124 | 122 | 40 | 2025-06-23 | 2025-06-23 | 2025-07-14 | 2026-03-31 | 2026-03-31 |  | 281 | 281 | 1759.9 | 1759.9 | 529.8997 | 1720.3997 | 2% | 33% | 21% | 30% | Green | [In Prog] late start;
DSFFLOW-2750 | In Progress | Maiden Installation, Migration | Core Network | IMS | 189 | 189 | 7 | 2025-06-24 | 2025-06-24 | 2025-07-09 | 2025-12-26 | 2025-12-26 |  | 185 | 185 | 5869 | 5869 | 700.6 | 5749 | 2% | 4% | 31% | 12% | Green | [In Prog] late start;
DSFFLOW-1894 | In Progress | Upgrade | Core Network | EPC | 25 | 25 | 1 | 2024-12-31 | 2024-12-31 | 2025-06-26 | 2025-12-30 | 2025-12-30 |  | 364 | 364 | 1584 | 1584 | 688 | 1584 | 0% | 4% | 64% | 43% | Amber | [In Prog] efforts burnt misaligned with work progress; work progress misaligned with time progress; late start;
DSFFLOW-1368 | In Progress | Migration | Core Network | EPC | 21 | 21 | 0 | 2025-05-23 | 2025-05-23 | 2025-06-25 | 2025-12-31 | 2025-12-31 |  | 222 | 222 | 1214.8 | 1214.8 | 672.03 | 1214.8 | 0% | 0% | 40% | 57% | Red | [In Prog] efforts burning without any work progress; time ticking without any work progress; late start;
DSFFLOW-1247 | In Progress | Upgrade | Core Network | EPC, IMS, UDM | 168 | 168 | 0 | 2025-05-06 | 2025-05-06 | 2025-05-23 | 2025-12-31 | 2025-12-31 |  | 239 | 239 | 2729 | 2729 | 667.25 | 2643.25 | 3% | 0% | 44% | 24% | Amber | [In Prog] time ticking without any work progress; efforts burnt misaligned with work progress; late start;
DSFFLOW-2169 | In Progress | Maiden Installation | Core Network | EPC, Signaling, UDM | 327 | 327 | 0 | 2025-06-15 | 2025-06-15 | 2025-06-24 | 2027-08-20 | 2027-08-20 |  | 796 | 796 | 29308.1 | 29308.1 | 630.2 | 29302.09 | 0% | 0% | 8% | 2% | Green | [In Prog] late start;
DSFFLOW-2107 | In Progress | Maiden Installation | Core Network | UDM, IMS | 90 | 90 | 0 | 2025-05-29 | 2025-05-29 | 2025-06-30 | 2026-02-27 | 2026-02-27 |  | 274 | 274 | 4425.7 | 4425.7 | 606.5997 | 4382.2 | 1% | 0% | 30% | 15% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-2497 | In Progress | Migration | Core Network, Network Management | Activation, EPC, Resource Orchestration | 96 | 96 | 18 | 2025-05-29 | 2025-05-29 | 2025-06-27 | 2026-02-27 | 2026-02-27 |  | 274 | 274 | 2112 | 2112 | 606 | 2112 | 0% | 19% | 30% | 29% | Green | [In Prog] late start;
DSFFLOW-3233 | In Progress | Migration | Core Network | UDM | 16 | 15 | 1 | 2025-07-14 | 2025-07-14 | 2025-08-12 | 2025-08-15 | 2025-08-15 |  | 32 | 32 | 614 | 614 | 529 | 614 | 0% | 8% | 113% | 86% | Red | [In Prog] efforts burnt outweighing work output; work progress misaligned with time progress; late start;
DSFFLOW-1057 | In Progress | Upgrade, Maiden Installation | Core Network | EPC | 86 | 86 | 6 | 2025-05-07 | 2025-05-07 | 2025-05-16 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 268 | 268 | 3893.75 | 3893.75 | 589 | 3876.75 | 0% | 8% | 100% | 15% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress; late start; actual End Date exceeds Today;
DSFFLOW-2249 | In Progress | Upgrade, Expansion, Maiden Installation | BOS | Monetization Charging | 396 | 396 | 11 | 2025-06-22 | 2025-06-22 | 2025-06-27 | 2025-09-19 | 2025-09-19 |  | 89 | 89 | 3683.11 | 3683.11 | 579.73 | 3482.11 | 5% | 3% | 66% | 16% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress;
DSFFLOW-1166 | In Progress | Upgrade | Core Network | Cloud | 70 | 70 | 26 | 2025-05-19 | 2025-05-19 | 2025-06-06 | 2025-12-30 | 2025-12-30 |  | 225 | 225 | 1196 | 1196 | 567.6 | 1159.5 | 3% | 37% | 41% | 47% | Green | [In Prog] late start;
DSFFLOW-2321 | In Progress | Upgrade | Core Network | Exposure | 51 | 51 | 23 | 2025-06-02 | 2025-06-02 | 2025-06-19 | 2025-08-29 | 2025-08-29 |  | 88 | 88 | 881.75 | 881.75 | 558.55 | 841.75 | 5% | 45% | 89% | 63% | Green | [In Prog] late start;
DSFFLOW-507 | In Progress | Upgrade | Network Management | Element Management & Reporting | 527 | 527 | 460 | 2025-02-28 | 2025-03-01 | 2025-06-26 | 2025-07-30 | 2025-09-30 |  | 152 | 213 | 6628 | 6628 | 4524.6833 | 5137.1833 | 22% | 87% | 80% | 68% | Green | [In Prog] late start;
DSFFLOW-1926 | In Progress | Maiden Installation | Core Network | Cloud | 97 | 97 | 0 | 2025-05-26 | 2025-05-26 | 2025-07-10 | 2026-12-31 | 2026-12-31 |  | 584 | 584 | 2188.6 | 2188.6 | 557.6 | 2158.6 | 1% | 0% | 15% | 25% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-1087 | In Progress | Upgrade | Network Management | Element Management & Reporting | 58 | 56 | 17 | 2025-05-14 | 2025-05-14 | 2025-05-17 | 2025-11-29 | 2025-11-29 |  | 199 | 199 | 990 | 978 | 543.5 | 938 | 4% | 30% | 49% | 57% | Amber | [In Prog] efforts burnt misaligned with work progress;
DSFFLOW-1337 | In Progress | Upgrade, Expansion | BOS | Monetization Charging | 338 | 338 | 5 | 2025-04-14 | 2025-04-14 | 2025-05-30 | 2026-10-30 | 2026-10-30 |  | 564 | 564 | 5063 | 5063 | 537.25 | 4853 | 4% | 1% | 23% | 11% | Green | [In Prog] late start;
DSFFLOW-3669 | In Progress | Upgrade | Core Network | EPC, IMS, Signaling, UDM | 226 | 226 | 0 | 2025-06-09 | 2025-06-09 | 2025-07-28 | 2025-10-30 | 2025-10-30 |  | 143 | 143 | 4764 | 4764 | 588.75 | 4691.75 | 2% | 0% | 50% | 12% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-477 | In Progress | Upgrade, Maiden Installation | Core Network | EPC | 76 | 76 | 34 | 2024-11-08 | 2024-11-08 | 2025-04-29 | 2026-02-28 | 2026-02-28 |  | 477 | 477 | 2867.5 | 2867.5 | 2254 | 2797.5 | 2% | 45% | 60% | 79% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-2368 | On Hold | Upgrade | Network Management | Activation, Resource Orchestration | 34 | 34 | 15 | 2025-06-01 | 2025-06-01 | 2025-06-20 | 2033-08-31 | 2033-08-31 |  | 3013 | 3013 | 766.71 | 766.71 | 437.7 | 738.71 | 4% | 44% | 3% | 57% | Amber | [On Hold] efforts burnt misaligned with time progress; late start;
DSFFLOW-133 | On Hold | Upgrade | BOS | Core Commerce | 423 | 423 | 165 | 2025-03-17 | 2025-03-17 | 2025-04-09 | 2025-06-30 | 2025-08-15 |  | 105 | 151 | 3067 | 3067 | 1563.0008 | 3136.9992 | -2% | 39% | 103% | 51% | Amber | [On Hold] projecting 1%+ EAC effort overrun ; efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-2452 | On Hold | Maiden Installation | Network Management | Resource Orchestration | 44 | 44 | 2 | 2025-05-29 | 2025-05-29 | 2025-07-11 | 2026-02-27 | 2026-02-27 |  | 274 | 274 | 1157 | 1157 | 111.58 | 1157 | 0% | 5% | 30% | 10% | Green | [On Hold] late start;
DSFFLOW-3443 | On Hold | Upgrade | Network Management | Element Management & Reporting | 21 | 15 | 8 | 2025-07-14 | 2025-07-14 | 2025-07-14 | 2025-09-19 | 2025-09-19 | 2025-08-01 | 67 | 67 | 158.5 | 158.5 | 137 | 229 | -44% | 53% | 29% | 86% | Red | [On Hold] projecting 5%+ EAC effort overrun; efforts burnt misaligned with work progress; efforts burnt misaligned with time progress;
DSFFLOW-2931 | On Hold | Maiden Installation | Network Management | Activation | 46 | 46 | 4 | 2025-06-08 | 2025-06-08 | 2025-06-09 | 2025-12-30 | 2025-12-30 |  | 205 | 205 | 1061.25 | 1061.25 | 267.72 | 1027.07 | 3% | 9% | 35% | 25% | Green | [On Hold]
DSFFLOW-1646 | On Hold | Upgrade | Network Management | Element Management & Reporting | 67 | 67 | 24 | 2025-05-27 | 2025-07-21 | 2025-06-09 | 2025-08-29 | 2025-09-30 |  | 94 | 71 | 1440 | 1440 | 504.01 | 1424.01 | 1% | 36% | 42% | 35% | Green | [On Hold] early start;
DSFFLOW-3265 | Assigned | Migration | Core Network | EPC, UDM, IMS, Core Network Automation, Cloud | 88 | 88 | 0 | 2025-05-15 | 2025-05-15 |  | 2025-11-20 | 2025-11-20 |  | 189 | 189 | 8356.5 | 8356.5 |  | 8356.5 | 0% | 0% | 51% | 0% | Amber | [Assigned] with 96 days past due start date;
DSFFLOW-4850 | Assigned | Migration | Core Network | Core Network Automation, EPC, IMS, MSS, Signaling, UDM | 301 | 301 | 0 | 2025-08-11 | 2025-08-11 |  | 2025-10-25 | 2025-10-25 |  | 75 | 75 | 8332.6 | 8332.6 |  | 8332.6 | 0% | 0% | 12% | 0% | Amber | [Assigned] with 8 days past due start date;
DSFFLOW-4624 | Assigned | Maiden Installation | Core Network | Signaling | 18 | 18 | 0 | 2025-08-09 | 2025-08-09 |  | 2026-06-29 | 2026-06-29 |  | 324 | 324 | 570 | 570 |  | 570 | 0% | 0% | 3% | 0% | Amber | [Assigned] with 10 days past due start date;
DSFFLOW-4628 | Assigned | Maiden Installation | Core Network | Core Network Automation, UDM | 29 | 29 | 0 | 2025-08-09 | 2025-08-09 |  | 2026-06-29 | 2026-06-29 |  | 324 | 324 | 730 | 730 |  | 730 | 0% | 0% | 3% | 0% | Amber | [Assigned] with 10 days past due start date;
DSFFLOW-4636 | Assigned | Maiden Installation | Core Network | Core Network Automation, EPC | 51 | 51 | 0 | 2025-06-30 | 2025-06-30 |  | 2026-06-29 | 2026-06-29 |  | 364 | 364 | 1716 | 1716 |  | 1716 | 0% | 0% | 15% | 0% | Amber | [Assigned] with 50 days past due start date;
DSFFLOW-325 | Assigned | Upgrade | Core Network | MSS | 34 | 34 | 0 | 2025-04-22 | 2025-04-22 |  | 2026-12-31 | 2026-12-31 |  | 618 | 618 | 512 | 512 |  | 512 | 0% | 0% | 19% | 0% | Amber | [Assigned] with 119 days past due start date;
DSFFLOW-4540 | Assigned | Upgrade | Core Network | Cloud | 34 | 34 | 0 | 2025-07-28 | 2025-07-28 |  | 2025-12-31 | 2025-12-31 |  | 156 | 156 | 1364 | 1364 |  | 1364 | 0% | 0% | 15% | 0% | Amber | [Assigned] with 22 days past due start date;
DSFFLOW-4916 | Assigned | Upgrade | Network Management | Element Management & Reporting | 78 | 78 | 0 | 2025-08-18 | 2025-08-18 |  | 2025-12-15 | 2025-12-15 |  | 119 | 119 | 1231.8 | 1231.8 |  | 1231.8 | 0% | 0% | 2% | 0% | Amber | [Assigned] with 1 days past due start date;
DSFFLOW-1809 | Assigned | Upgrade, Maiden Installation | Core Network | MSS, Signaling | 46 | 46 | 0 | 2025-03-03 | 2025-03-03 |  | 2025-12-15 | 2025-12-15 |  | 287 | 287 | 1202 | 1202 |  | 1202 | 0% | 0% | 59% | 0% | Amber | [Assigned] with 169 days past due start date;
DSFFLOW-3010 | Assigned | Upgrade | Core Network | Cloud | 47 | 47 | 0 | 2025-07-04 | 2025-07-04 |  | 2025-12-31 | 2025-12-31 |  | 180 | 180 | 1803 | 1803 |  | 1803 | 0% | 0% | 26% | 0% | Amber | [Assigned] with 46 days past due start date;
DSFFLOW-3528 | Assigned | Upgrade | Core Network | EPC | 130 | 130 | 0 | 2025-07-04 | 2025-07-04 |  | 2025-12-31 | 2025-12-31 |  | 180 | 180 | 1992 | 1992 |  | 1992 | 0% | 0% | 26% | 0% | Amber | [Assigned] with 46 days past due start date;
DSFFLOW-3630 | Assigned | Migration | Core Network | Cloud | 60 | 60 | 0 | 2025-07-04 | 2025-07-04 |  | 2025-12-31 | 2025-12-31 |  | 180 | 180 | 2549 | 2549 |  | 2549 | 0% | 0% | 26% | 0% | Amber | [Assigned] with 46 days past due start date;
DSFFLOW-2916 | Assigned | Maiden Installation | Core Network | MSS | 12 | 12 | 0 | 2025-05-15 | 2025-05-15 |  | 2026-12-21 | 2026-12-21 |  | 585 | 585 | 204 | 204 |  | 204 | 0% | 0% | 17% | 0% | Amber | [Assigned] with 96 days past due start date;
DSFFLOW-4880 | Assigned | Migration | Core Network | Cloud-3PP/MPBN, IMS, MSS, Signaling, UDM | 127 | 127 | 0 | 2025-08-13 | 2025-08-13 |  | 2025-12-05 | 2025-12-05 |  | 114 | 114 | 2334.2 | 2334.2 |  | 2334.2 | 0% | 0% | 6% | 0% | Amber | [Assigned] with 6 days past due start date;
DSFFLOW-4729 | Assigned | Upgrade | Core Network | Cloud-3PP/MPBN | 10 | 10 | 0 | 2025-08-01 | 2025-08-01 |  | 2025-10-31 | 2025-10-31 |  | 91 | 91 | 14 | 14 |  | 14 | 0% | 0% | 21% | 0% | Amber | [Assigned] with 18 days past due start date;
DSFFLOW-4955 | Assigned | Maiden Installation | Network Management | Element Management & Reporting | 77 | 77 | 0 | 2025-08-18 | 2025-08-18 |  | 2025-11-28 | 2025-11-28 |  | 102 | 102 | 2003.5 | 2003.5 |  | 2003.5 | 0% | 0% | 2% | 0% | Amber | [Assigned] with 1 days past due start date;
DSFFLOW-3998 | Assigned | Upgrade | Core Network | MSS | 13 | 13 | 0 | 2025-07-25 | 2025-07-25 |  | 2026-04-15 | 2026-04-15 |  | 264 | 264 | 220 | 220 |  | 220 | 0% | 0% | 10% | 0% | Amber | [Assigned] with 25 days past due start date;
DSFFLOW-3418 | Assigned | Upgrade | Core Network | IMS | 38 | 38 | 0 | 2025-07-14 | 2025-07-14 |  | 2025-09-12 | 2025-09-12 |  | 60 | 60 | 516 | 516 |  | 516 | 0% | 0% | 61% | 0% | Amber | [Assigned] with 36 days past due start date;
DSFFLOW-3411 | Assigned | Upgrade | Core Network | IMS | 46 | 46 | 0 | 2025-07-14 | 2025-07-14 |  | 2025-08-15 | 2025-08-15 |  | 32 | 32 | 542 | 542 |  | 542 | 0% | 0% | 113% | 0% | Amber | [Assigned] with 36 days past due start date;
DSFFLOW-4865 | Assigned | Upgrade | Core Network | MSS, Signaling | 23 | 23 | 0 | 2024-06-06 | 2024-06-06 |  | 2025-08-21 | 2025-08-21 |  | 441 | 441 | 282.5 | 282.5 |  | 282.5 | 0% | 0% | 100% | 0% | Amber | [Assigned] with 439 days past due start date;
DSFFLOW-4713 | Assigned | Upgrade | Core Network | MSS | 38 | 38 | 0 | 2025-07-25 | 2025-07-25 |  | 2025-08-30 | 2025-08-30 |  | 36 | 36 | 652 | 652 |  | 652 | 0% | 0% | 70% | 0% | Amber | [Assigned] with 25 days past due start date;
DSFFLOW-4013 | Assigned | Maiden Installation | Core Network | MSS | 38 | 38 | 0 | 2025-07-25 | 2025-07-25 |  | 2026-04-15 | 2026-04-15 |  | 264 | 264 | 2613 | 2613 |  | 2613 | 0% | 0% | 10% | 0% | Amber | [Assigned] with 25 days past due start date;
DSFFLOW-4525 | Assigned | Migration | Core Network | UDM | 15 | 15 | 0 | 2025-08-11 | 2025-08-11 |  | 2026-01-30 | 2026-01-30 |  | 172 | 172 | 1277 | 1277 |  | 1277 | 0% | 0% | 5% | 0% | Amber | [Assigned] with 8 days past due start date;
DSFFLOW-2828 | Assigned | Migration | Core Network | UDM | 15 | 15 | 0 | 2025-07-14 | 2025-07-14 |  | 2025-11-28 | 2025-11-28 |  | 137 | 137 | 593 | 593 | 324 | 593 | 0% | 0% | 27% | 57% | Red | [Assigned] with wrong project state with efforts burning; 36 days past due start date;
DSFFLOW-3294 | Assigned | Upgrade | Core Network | IMS | 65 | 65 | 0 | 2025-07-08 | 2025-07-08 |  | 2025-09-22 | 2025-09-22 |  | 76 | 76 | 312 | 312 |  | 312 | 0% | 0% | 57% | 0% | Amber | [Assigned] with 42 days past due start date;
DSFFLOW-937 | Backlog | Upgrade | Core Network | IMS | 16 | 16 | 2 | 2025-05-06 | 2025-05-06 |  | 2025-06-29 | 2025-06-29 |  | 54 | 54 | 176 | 176 | 108 | 173 | 2% | 13% | 193% | 61% | Red | [Backlog] with wrong project state with work happening; efforts burning; 105 days past due start date;
DSFFLOW-626 | Backlog | Maiden Installation | Core Network | EPC | 34 | 34 | 0 | 2025-04-29 | 2025-04-29 | 2025-04-29 | 2025-08-31 | 2025-08-31 | 2025-09-15 | 124 | 124 | 2496 | 2496 | 904 | 2392 | 4% | 0% | 113% | 36% | Red | [Backlog] with wrong project state with efforts burning; 112 days past due start date; actual End Date exceeds Today;
DSFFLOW-1322 | Backlog | Upgrade | Core Network | EPC, Exposure, UDM | 88 | 88 | 22 | 2025-04-22 | 2025-04-22 |  | 2025-08-30 | 2025-08-30 |  | 130 | 130 | 981.5 | 981.5 | 748.5 | 981.5 | 0% | 25% | 92% | 76% | Red | [Backlog] with wrong project state with work happening; efforts burning; 119 days past due start date;
DSFFLOW-1474 | Backlog | Upgrade | Core Network | IMS | 54 | 54 | 5 | 2025-03-24 | 2025-03-24 |  | 2025-06-30 | 2026-02-02 |  | 98 | 315 | 429.5 | 429.5 | 72 | 357.5 | 17% | 9% | 47% | 17% | Red | [Backlog] with wrong project state with work happening; efforts burning; 148 days past due start date;
DSFFLOW-356 | Backlog | Expansion | Core Network | UDM | 13 | 13 | 0 | 2024-12-18 | 2024-12-18 |  | 2026-07-31 | 2026-07-31 |  | 590 | 590 | 222 | 222 |  | 222 | 0% | 0% | 41% | 0% | Amber | [Backlog] with 244 days past due start date;
DSFFLOW-845 | Backlog | Upgrade | Core Network | MSS | 22 | 22 | 0 | 2025-02-24 | 2025-02-24 |  | 2025-06-30 | 2025-06-30 |  | 126 | 126 | 674 | 674 |  | 674 | 0% | 0% | 139% | 0% | Amber | [Backlog] with 176 days past due start date;
DSFFLOW-371 | Backlog | Upgrade | Core Network | MSS | 28 | 28 | 0 | 2025-03-24 | 2025-03-24 |  | 2025-07-25 | 2025-07-25 |  | 123 | 123 | 700 | 700 |  | 700 | 0% | 0% | 120% | 0% | Amber | [Backlog] with 148 days past due start date;
DSFFLOW-894 | Backlog | Upgrade | Core Network | UDM | 23 | 23 | 0 | 2025-05-06 | 2025-05-06 |  | 2025-12-31 | 2025-12-31 |  | 239 | 239 | 924 | 924 | 480 | 924 | 0% | 0% | 44% | 52% | Red | [Backlog] with wrong project state with efforts burning; 105 days past due start date;
DSFFLOW-1223 | Backlog | Expansion | Core Network | EPC, UDM, Signaling | 166 | 166 | 1 | 2025-05-09 | 2025-05-09 |  | 2025-12-31 | 2025-12-31 |  | 236 | 236 | 33976 | 33976 | 1129 | 33976 | 0% | 1% | 43% | 3% | Red | [Backlog] with wrong project state with work happening; efforts burning; 102 days past due start date;
DSFFLOW-879 | Rejected | Upgrade | Network Management | Element Management & Reporting | 12 | 12 | 0 | 2025-05-09 | 2025-05-09 |  | 2025-06-29 | 2025-06-29 |  | 51 | 51 | 0 | 0 |  | 0 | 0% | 0% | 198% | 0%