## RAGStatus
DSF Project ID | Delivery State | Flow | Domain | Sub-Domain | Plan Work | Replan Work | Closed Work | Plan Start | Replan Start | Actual Start | Plan End | Replan End | Actual End | Plan Days | Replan Days | Plan Hr | Replan Hr | Logged Hr | EAC Hr | EAC Efficiency | Work Prog | Time Prog | Effort Prog | RAG | Reason
DSFFLOW-921 | Closed | Upgrade | Core Network | UDM | 23 | 23 | 23 | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-07-04 | 2025-07-04 | 2025-07-04 | 51 | 51 | 202.5 | 202.5 | 202.4 | 202.4 | 0% | 100% | 100% | 100% | Green | [Closed]
DSFFLOW-310 | Closed | Upgrade | Core Network | UDM | 19 | 19 | 19 | 2025-04-20 | 2025-04-22 | 2025-04-22 | 2025-05-31 | 2025-06-05 | 2025-06-05 | 41 | 44 | 267 | 267 | 267 | 267 | 0% | 100% | 100% | 100% | Green | [Closed]
DSFFLOW-2625 | Closed | Upgrade | Core Network | IMS | 30 | 28 | 28 | 2025-06-29 | 2025-06-30 | 2025-06-30 | 2025-07-31 | 2025-08-01 | 2025-08-01 | 32 | 32 | 267 | 267 | 267.01 | 267.01 | 0% | 100% | 100% | 100% | Green | [Closed]
DSFFLOW-4427 | Closed | Upgrade | Network Management | Element Management & Reporting | 24 | 18 | 18 | 2025-07-28 | 2025-07-28 | 2025-08-06 | 2025-08-08 | 2025-08-08 | 2025-08-11 | 11 | 11 | 148 | 148 | 140 | 140 | 5% | 100% | 125% | 95% | Red | [Closed] schedule overrun > 10%; efforts saved; late start;
DSFFLOW-3700 | Closed | Upgrade | Core Network | Signaling | 20 | 19 | 19 | 2025-06-04 | 2025-06-04 | 2025-07-24 | 2026-07-31 | 2026-07-31 | 2025-07-25 | 422 | 422 | 138 | 138 | 138 | 138 | 0% | 100% | 12% | 100% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; late start;
DSFFLOW-550 | Closed | Upgrade | Network Management | Element Management & Reporting | 42 | 43 | 43 | 2025-04-30 | 2025-04-07 | 2025-07-02 | 2026-02-27 | 2025-07-23 | 2025-07-18 | 303 | 107 | 624 | 624 | 618 | 618 | 1% | 100% | 95% | 99% | Green | [Closed] ahead of schedule; efforts saved; late start;
DSFFLOW-1879 | Closed | Maiden Installation | Network Management | Element Management & Reporting | 25 | 14 | 14 | 2025-05-26 | 2025-05-26 | 2025-05-26 | 2025-06-30 | 2025-06-30 | 2025-06-30 | 35 | 35 | 304.5 | 298 | 268.5 | 268.5 | 10% | 100% | 100% | 90% | Green | [Closed] efforts saved;
DSFFLOW-2321 | Closed | Upgrade | Core Network | Exposure | 51 | 31 | 31 | 2025-06-02 | 2025-06-19 | 2025-06-19 | 2025-08-29 | 2025-09-05 | 2025-09-05 | 88 | 78 | 881.75 | 693 | 607.7667 | 607.7667 | 12% | 100% | 100% | 88% | Green | [Closed] efforts saved; feedback: opportunity for optimized effort baseline;
DSFFLOW-1200 | Closed | Upgrade | Network Management | Element Management & Reporting | 192 | 35 | 35 | 2025-05-08 | 2025-02-10 | 2025-04-22 | 2026-08-31 | 2025-10-31 | 2025-06-19 | 480 | 263 | 3156 | 1055.5 | 605.5 | 605.5 | 43% | 100% | 49% | 57% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; feedback: opportunity for optimized effort baseline; late start;
DSFFLOW-4778 | Closed | Upgrade | Core Network | EPC, IMS, Signaling | 70 | 70 | 66 | 2025-06-22 | 2025-06-23 | 2025-06-23 | 2025-08-30 | 2025-08-29 | 2025-08-29 | 69 | 67 | 1231 | 1231 | 1173 | 1070 | 13% | 94% | 100% | 95% | Red | [Closed] incomplete work; efforts saved;
DSFFLOW-64 | Closed | Upgrade | Network Management | Element Management | 58 | 56 | 56 | 2025-03-02 | 2025-03-02 | 2025-03-13 | 2025-08-30 | 2025-09-12 | 2025-09-19 | 181 | 194 | 1350.91 | 1350.91 | 1231.6597 | 1231.6597 | 9% | 100% | 104% | 91% | Amber | [Closed] schedule overrun < 10%; efforts saved; late start;
DSFFLOW-4411 | Closed | Upgrade | Network Management | Element Management | 34 | 31 | 31 | 2025-08-06 | 2025-08-06 | 2025-08-11 | 2025-09-30 | 2025-09-30 | 2025-09-10 | 55 | 55 | 515.95 | 456.45 | 284.45 | 284.45 | 38% | 100% | 64% | 62% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; feedback: opportunity for optimized effort baseline;
DSFFLOW-1445 | Closed | Upgrade | Core Network | IMS | 78 | 59 | 59 | 2025-05-27 | 2025-05-27 | 2025-05-28 | 2025-07-18 | 2025-07-04 | 2025-07-04 | 52 | 38 | 801 | 639.5 | 600.2697 | 600.2697 | 6% | 100% | 100% | 94% | Green | [Closed] efforts saved;
DSFFLOW-97 | Closed | Upgrade | Network Management | Element Management & Reporting | 50 | 47 | 47 | 2025-03-12 | 2025-03-12 | 2025-03-13 | 2025-05-31 | 2025-07-31 | 2025-07-15 | 80 | 141 | 844 | 801.5 | 575 | 575 | 29% | 100% | 89% | 72% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; feedback: opportunity for optimized effort baseline;
DSFFLOW-1790 | Closed | Upgrade | Core Network | Cloud | 85 | 85 | 85 | 2025-06-02 | 2025-06-02 | 2025-07-10 | 2026-03-31 | 2026-03-31 | 2025-08-26 | 302 | 302 | 726 | 726 | 726 | 726 | 0% | 100% | 29% | 100% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; late start;
DSFFLOW-1614 | Closed | Upgrade | Network Management | Resource Orchestration | 54 | 52 | 52 | 2025-05-28 | 2025-05-28 | 2025-06-04 | 2026-01-30 | 2026-01-30 | 2025-09-15 | 247 | 247 | 299.7533 | 299.7533 | 300.12 | 300.12 | 0% | 100% | 45% | 100% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan;
DSFFLOW-340 | Closed | Upgrade | Core Network | UDM | 17 | 17 | 17 | 2025-03-04 | 2025-03-04 | 2025-03-04 | 2025-06-30 | 2025-08-11 | 2025-08-11 | 118 | 160 | 264 | 264 | 264 | 264 | 0% | 100% | 100% | 100% | Green | [Closed]
DSFFLOW-5461 | Closed | Upgrade | Core Network | Cloud | 18 | 18 | 18 | 2025-06-08 | 2025-06-08 | 2025-06-08 | 2026-08-14 | 2026-08-14 | 2025-08-14 | 432 | 432 | 305 | 305 | 305 | 305 | 0% | 100% | 16% | 100% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan;
DSFFLOW-168 | Closed | Upgrade | BOS | Monetization Charging | 59 | 59 | 59 | 2025-03-21 | 2025-03-18 | 2025-03-18 | 2025-09-03 | 2025-09-03 | 2025-06-13 | 166 | 169 | 790.8 | 790.8 | 652.5 | 652.5 | 17% | 100% | 52% | 83% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; feedback: opportunity for optimized effort baseline;
DSFFLOW-1383 | Closed | Upgrade | Core Network | EPC | 63 | 63 | 63 | 2024-12-31 | 2024-12-31 | 2025-01-01 | 2025-06-30 | 2025-06-30 | 2025-05-27 | 181 | 181 | 952 | 952 | 952 | 952 | 0% | 100% | 81% | 100% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan;
DSFFLOW-4230 | Closed | Upgrade | Core Network | Cloud | 17 | 17 | 17 | 2025-08-03 | 2025-08-04 | 2025-08-04 | 2025-08-21 | 2025-08-21 | 2025-08-21 | 18 | 17 | 272 | 272 | 243 | 243 | 11% | 100% | 100% | 89% | Green | [Closed] efforts saved; feedback: opportunity for optimized effort baseline;
DSFFLOW-4794 | Closed | Upgrade | Network Management | Element Management & Reporting | 23 | 17 | 17 | 2025-08-11 | 2025-08-11 | 2025-08-15 | 2025-08-28 | 2025-08-29 | 2025-09-01 | 17 | 18 | 282 | 282 | 248 | 248 | 12% | 100% | 116% | 88% | Red | [Closed] schedule overrun > 10%; efforts saved; feedback: opportunity for optimized effort baseline;
DSFFLOW-2560 | Closed | Upgrade | Network Management | Resource Orchestration | 24 | 18 | 18 | 2025-06-26 | 2025-06-26 | 2025-06-27 | 2025-07-08 | 2025-07-08 | 2025-07-07 | 12 | 12 | 222 | 222 | 222 | 222 | 0% | 100% | 92% | 100% | Green | [Closed] ahead of schedule;
DSFFLOW-4865 | Closed | Upgrade | Core Network | MSS, Signaling | 23 | 23 | 23 | 2024-06-06 | 2024-06-06 | 2025-08-19 | 2025-08-21 | 2025-08-21 | 2025-08-21 | 441 | 441 | 280.5 | 280.5 | 255 | 255 | 9% | 100% | 100% | 91% | Green | [Closed] efforts saved; late start;
DSFFLOW-2482 | Closed | Expansion | Core Network | EPC | 24 | 24 | 16 | 2025-06-09 | 2025-06-09 | 2025-06-24 | 2025-12-12 | 2025-12-12 | 2025-09-12 | 186 | 186 | 816 | 816 | 804 | 716 | 12% | 67% | 51% | 99% | Red | [Closed] incomplete work; ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; late start;
DSFFLOW-3547 | Closed | Upgrade | Core Network | MSS | 13 | 13 | 13 | 2025-07-06 | 2025-07-08 | 2025-07-08 | 2025-08-14 | 2025-08-08 | 2025-08-08 | 39 | 31 | 220 | 220 | 210 | 210 | 5% | 100% | 100% | 95% | Green | [Closed] efforts saved;
DSFFLOW-3396 | Closed | Maiden Installation | BOS | Monetization Billing | 19 | 11 | 11 | 2025-06-11 | 2025-06-11 | 2025-06-16 | 2025-07-23 | 2025-07-23 | 2025-08-07 | 42 | 42 | 760 | 760 | 680 | 680 | 11% | 100% | 135% | 89% | Red | [Closed] schedule overrun > 10%; efforts saved; feedback: opportunity for optimized effort baseline;
DSFFLOW-3581 | Closed | Upgrade | Core Network | MSS | 13 | 13 | 13 | 2025-07-22 | 2025-07-03 | 2025-07-03 | 2025-08-15 | 2025-08-08 | 2025-08-08 | 24 | 36 | 220 | 220 | 204.5 | 204.5 | 8% | 100% | 100% | 93% | Green | [Closed] efforts saved;
DSFFLOW-49 | Closed | Upgrade | Network Management | Element Management & Reporting | 30 | 30 | 30 | 2025-02-19 | 2025-02-20 | 2025-02-28 | 2025-08-29 | 2025-04-17 | 2025-03-27 | 191 | 56 | 488 | 488 | 430 | 430 | 12% | 100% | 63% | 88% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; feedback: opportunity for optimized effort baseline; late start;
DSFFLOW-2419 | Closed | Upgrade | Core Network | IMS | 52 | 52 | 52 | 2025-06-05 | 2025-06-09 | 2025-06-09 | 2025-06-26 | 2025-07-16 | 2025-07-16 | 21 | 37 | 322 | 322 | 200 | 200 | 38% | 100% | 100% | 62% | Green | [Closed] efforts saved; feedback: opportunity for optimized effort baseline;
DSFFLOW-1322 | Closed | Upgrade | Core Network | EPC, Exposure, UDM | 88 | 33 | 33 | 2025-04-22 | 2025-04-22 | 2025-08-21 | 2025-08-30 | 2025-08-30 | 2025-08-21 | 130 | 130 | 940.5 | 884.5 | 869.5 | 869.5 | 2% | 100% | 93% | 98% | Green | [Closed] ahead of schedule; efforts saved; late start;
DSFFLOW-1026 | Closed | Upgrade | Network Management | Resource Orchestration | 22 | 19 | 19 | 2025-04-20 | 2025-04-20 | 2025-06-13 | 2025-06-29 | 2025-06-29 | 2025-07-09 | 70 | 70 | 277.75 | 260.77 | 260.77 | 260.77 | 0% | 100% | 114% | 100% | Red | [Closed] schedule overrun > 10%; late start;
DSFFLOW-1103 | Closed | Maiden Installation | Core Network, Network Management | EPC, Resource Orchestration | 44 | 44 | 44 | 2025-05-16 | 2025-05-16 | 2025-05-19 | 2025-08-30 | 2025-09-08 | 2025-09-04 | 106 | 115 | 938 | 938 | 907 | 907 | 3% | 100% | 97% | 97% | Green | [Closed] ahead of schedule; efforts saved;
DSFFLOW-3381 | Closed | Upgrade | Core Network | Signaling | 19 | 19 | 19 | 2025-06-10 | 2025-06-04 | 2025-06-04 | 2025-07-30 | 2025-07-22 | 2025-07-22 | 50 | 48 | 179 | 179 | 178.5 | 178.5 | 0% | 100% | 100% | 100% | Green | [Closed]
DSFFLOW-937 | Closed | Upgrade | Core Network | IMS | 16 | 16 | 16 | 2025-05-06 | 2025-05-06 | 2025-05-06 | 2025-06-29 | 2025-09-29 | 2025-09-12 | 54 | 146 | 176 | 176 | 172 | 172 | 2% | 100% | 88% | 98% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; efforts saved;
DSFFLOW-386 | Closed | Maiden Installation | Core Network | EPC | 30 | 30 | 30 | 2024-11-10 | 2024-11-10 | 2025-01-01 | 2025-01-26 | 2025-01-26 | 2025-06-30 | 77 | 77 | 1773 | 1773 | 993 | 993 | 44% | 100% | 299% | 57% | Red | [Closed] schedule overrun > 10%; efforts saved; feedback: opportunity for optimized effort baseline; late start;
DSFFLOW-1135 | Closed | Upgrade | BOS | D&A Mediation | 34 | 34 | 34 | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-06-20 | 2025-06-20 | 2025-06-20 | 32 | 32 | 569.1 | 569.1 | 548 | 548 | 4% | 100% | 100% | 96% | Green | [Closed] efforts saved;
DSFFLOW-3611 | Closed | Upgrade | Core Network | Cloud | 17 | 17 | 17 | 2025-07-23 | 2025-07-23 | 2025-07-24 | 2025-08-28 | 2025-08-28 | 2025-08-07 | 36 | 36 | 106 | 106 | 88 | 88 | 17% | 100% | 43% | 83% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; feedback: opportunity for optimized effort baseline;
DSFFLOW-1745 | Closed | Upgrade, Expansion | Core Network, Network Management | EPC, Exposure, Resource Orchestration, UDM | 101 | 101 | 101 | 2025-06-04 | 2025-06-04 | 2025-06-06 | 2025-08-30 | 2025-08-30 | 2025-07-28 | 87 | 87 | 1432 | 1432 | 1432 | 1432 | 0% | 100% | 63% | 100% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan;
DSFFLOW-2138 | Closed | Upgrade, Maiden Installation | Network Management | Resource Orchestration | 52 | 37 | 37 | 2025-06-12 | 2025-06-12 | 2025-06-18 | 2025-08-15 | 2025-08-31 | 2025-08-14 | 64 | 80 | 646.6497 | 559.9 | 425.65 | 425.65 | 24% | 100% | 79% | 76% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; feedback: opportunity for optimized effort baseline;
DSFFLOW-5716 | Closed | Upgrade | Core Network | EPC | 24 | 24 | 24 | 2025-05-05 | 2025-07-07 | 2025-07-07 | 2025-09-05 | 2025-08-29 | 2025-08-28 | 123 | 53 | 422.5 | 422.5 | 423 | 423 | 0% | 100% | 98% | 100% | Green | [Closed] ahead of schedule;
DSFFLOW-4457 | Closed | Upgrade | Network Management | Element Management & Reporting | 38 | 14 | 14 | 2025-08-04 | 2025-07-08 | 2025-08-05 | 2025-12-26 | 2025-09-15 | 2025-08-13 | 144 | 69 | 946.5 | 505.5 | 405.5 | 405.5 | 20% | 100% | 53% | 80% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; feedback: opportunity for optimized effort baseline; late start;
DSFFLOW-2352 | Closed | Upgrade | Core Network | Signaling | 26 | 26 | 26 | 2025-06-02 | 2025-06-02 | 2025-06-02 | 2025-07-04 | 2025-07-30 | 2025-07-30 | 32 | 58 | 511 | 511 | 452 | 452 | 12% | 100% | 100% | 88% | Green | [Closed] efforts saved; feedback: opportunity for optimized effort baseline;
DSFFLOW-2529 | Closed | Maiden Installation | Core Network | Cloud, EPC, IMS, MSS, UDM | 15 | 15 | 15 | 2025-06-24 | 2025-06-24 | 2025-06-26 | 2025-08-29 | 2025-08-29 | 2025-09-04 | 66 | 66 | 3284 | 3284 | 3284 | 3284 | 0% | 100% | 111% | 100% | Red | [Closed] schedule overrun > 10%;
DSFFLOW-3685 | Closed | Upgrade | Core Network | MSS | 24 | 24 | 24 | 2025-06-30 | 2025-06-27 | 2025-06-27 | 2025-09-14 | 2025-09-01 | 2025-09-01 | 76 | 66 | 434.5 | 434.5 | 386 | 386 | 11% | 100% | 100% | 89% | Green | [Closed] efforts saved; feedback: opportunity for optimized effort baseline;
DSFFLOW-32 | Closed | Upgrade | Network Management | Element Management & Reporting | 57 | 31 | 31 | 2024-12-08 | 2024-12-08 | 2024-12-09 | 2025-02-17 | 2025-02-18 | 2025-02-17 | 71 | 72 | 910 | 459 | 457 | 457 | 0% | 100% | 99% | 100% | Green | [Closed] ahead of schedule;
DSFFLOW-462 | Closed | Upgrade | Core Network | MSS | 28 | 28 | 28 | 2025-03-17 | 2025-04-30 | 2025-04-30 | 2025-06-30 | 2025-09-03 | 2025-09-03 | 105 | 126 | 469 | 469 | 468.7 | 468.7 | 0% | 100% | 100% | 100% | Green | [Closed]
DSFFLOW-2947 | Closed | Upgrade | Core Network | MSS | 21 | 21 | 21 | 2025-03-18 | 2025-05-08 | 2025-05-08 | 2025-08-15 | 2025-07-15 | 2025-07-15 | 150 | 68 | 411.5 | 411.5 | 382.5 | 382.5 | 8% | 100% | 100% | 93% | Green | [Closed] efforts saved;
DSFFLOW-1894 | Closed | Upgrade | Core Network | EPC | 25 | 23 | 23 | 2024-12-31 | 2024-12-31 | 2025-06-26 | 2025-12-30 | 2025-12-30 | 2025-08-30 | 364 | 364 | 1584 | 1424 | 1424 | 1424 | 0% | 100% | 67% | 100% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; late start;
DSFFLOW-477 | Closed | Upgrade, Maiden Installation | Core Network | EPC | 49 | 49 | 34 | 2024-11-08 | 2024-11-08 | 2025-04-29 | 2026-02-28 | 2026-02-28 | 2025-09-18 | 477 | 477 | 2564 | 2564 | 2254 | 2494 | 3% | 69% | 66% | 88% | Red | [Closed] incomplete work; ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; feedback: opportunity for optimized effort baseline; late start;
DSFFLOW-1629 | Closed | Upgrade | Core Network | EPC, Signaling, UDM | 175 | 175 | 175 | 2025-04-01 | 2025-04-02 | 2025-04-02 | 2025-06-29 | 2025-06-30 | 2025-06-30 | 89 | 89 | 2725.1292 | 2725.1292 | 2238.05 | 2238.05 | 18% | 100% | 100% | 82% | Green | [Closed] efforts saved; feedback: opportunity for optimized effort baseline;
DSFFLOW-2858 | Closed | Upgrade | BOS | Monetization Charging | 34 | 34 | 34 | 2025-05-09 | 2025-06-09 | 2025-07-16 | 2025-07-25 | 2025-07-25 | 2025-08-06 | 77 | 46 | 486 | 486 | 486 | 486 | 0% | 100% | 126% | 100% | Red | [Closed] schedule overrun > 10%; late start;
DSFFLOW-2336 | Closed | Upgrade | Core Network | Signaling | 26 | 26 | 26 | 2025-06-02 | 2025-06-02 | 2025-06-02 | 2025-07-04 | 2025-08-15 | 2025-08-14 | 32 | 74 | 446 | 446 | 356 | 356 | 20% | 100% | 99% | 80% | Green | [Closed] ahead of schedule; efforts saved; feedback: opportunity for optimized effort baseline;
DSFFLOW-952 | Closed | Migration | Core Network | UDM | 18 | 16 | 6 | 2025-05-12 | 2025-05-12 | 2025-05-12 | 2025-06-29 | 2025-06-29 | 2025-08-29 | 48 | 48 | 491.25 | 491.25 | 491.25 | 491.25 | 0% | 38% | 225% | 100% | Red | [Closed] incomplete work; effort budget spent; schedule overrun > 10%;
DSFFLOW-3458 | Closed | Upgrade | Core Network | Cloud | 18 | 18 | 18 | 2025-07-22 | 2025-07-22 | 2025-07-29 | 2025-08-29 | 2025-08-29 | 2025-08-11 | 38 | 38 | 242 | 242 | 242 | 242 | 0% | 100% | 54% | 100% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan;
DSFFLOW-1166 | Closed | Upgrade | Core Network | Cloud | 70 | 70 | 70 | 2025-05-19 | 2025-05-19 | 2025-06-06 | 2025-12-30 | 2025-12-30 | 2025-09-02 | 225 | 225 | 1875 | 1875 | 1874.5 | 1874.5 | 0% | 100% | 47% | 100% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; late start;
DSFFLOW-2219 | Closed | Expansion | Core Network | Cloud | 37 | 35 | 28 | 2025-06-09 | 2025-06-09 | 2025-06-18 | 2025-12-12 | 2025-12-12 | 2025-09-12 | 186 | 186 | 517.35 | 502.35 | 494.85 | 494.85 | 1% | 80% | 51% | 99% | Red | [Closed] incomplete work; ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; late start;
DSFFLOW-80 | Closed | Upgrade | Core Network | EPC, IMS, UDM | 176 | 150 | 150 | 2025-02-06 | 2025-02-06 | 2025-03-10 | 2025-06-06 | 2025-06-06 | 2025-06-05 | 120 | 120 | 1786 | 1786 | 1758 | 1758 | 2% | 100% | 99% | 98% | Green | [Closed] ahead of schedule; efforts saved; late start;
DSFFLOW-1697 | Closed | Upgrade | Core Network | EPC | 30 | 21 | 21 | 2025-05-26 | 2025-06-12 | 2025-06-12 | 2025-08-31 | 2025-09-04 | 2025-09-04 | 97 | 84 | 346 | 346 | 310 | 310 | 10% | 100% | 100% | 90% | Green | [Closed] efforts saved;
DSFFLOW-401 | Closed | Upgrade, Expansion, Migration | Core Network | EPC | 152 | 150 | 150 | 2024-07-10 | 2024-07-10 | 2025-04-30 | 2025-12-12 | 2025-12-12 | 2025-06-23 | 520 | 520 | 2112 | 1932 | 1908.1 | 1908.1 | 1% | 100% | 67% | 99% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; late start;
DSFFLOW-3078 | In Progress | Upgrade | Core Network | UDM | 27 | 27 | 4 | 2025-07-02 | 2025-07-03 | 2025-07-03 | 2025-09-01 | 2025-10-17 |  | 61 | 106 | 656 | 656 | 306 | 651 | 1% | 15% | 77% | 47% | Amber | [In Prog] efforts burnt misaligned with work progress; work progress misaligned with time progress;
DSFFLOW-4760 | In Progress | Upgrade | Network Management | Resource Orchestration | 52 | 52 | 37 | 2025-08-12 | 2025-08-12 | 2025-08-14 | 2025-09-29 | 2025-09-29 |  | 48 | 48 | 217.08 | 276.58 | 245.32 | 241.58 | 13% | 71% | 86% | 89% | Green | [In Prog]
DSFFLOW-5938 | In Progress | Maiden Installation | Core Network | MSS | 40 | 40 | 1 | 2025-07-24 | 2025-07-24 | 2025-09-15 | 2026-03-31 | 2026-03-31 |  | 250 | 250 | 2280 | 2280 | 249.75 | 2228 | 2% | 3% | 24% | 11% | Green | [In Prog] late start;
DSFFLOW-6605 | In Progress | Maiden Installation | Core Network | UDM | 18 | 18 | 1 | 2025-08-20 | 2025-08-20 | 2025-09-16 | 2028-12-31 | 2028-12-31 |  | 1229 | 1229 | 1060.5 | 1060.5 | 421 | 996 | 6% | 6% | 3% | 40% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-5773 | In Progress | Maiden Installation | Core Network | MSS | 41 | 41 | 7 | 2025-07-07 | 2025-07-07 | 2025-09-02 | 2025-10-31 | 2025-09-30 |  | 116 | 85 | 518 | 518 | 332.5 | 438 | 15% | 17% | 91% | 64% | Amber | [In Prog] efforts burnt misaligned with work progress; work progress misaligned with time progress; late start;
DSFFLOW-1864 | In Progress | Upgrade | Network Management | Element Management & Reporting | 35 | 35 | 35 | 2025-06-09 | 2025-06-09 | 2025-06-18 | 2025-12-31 | 2025-12-31 |  | 205 | 205 | 506 | 506 | 397 | 397 | 22% | 100% | 51% | 78% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-5229 | In Progress | Upgrade | Network Management | Element Management | 106 | 106 | 3 | 2025-08-17 | 2025-08-17 | 2025-08-25 | 2026-03-30 | 2026-03-30 |  | 225 | 225 | 4286.9667 | 4286.9667 | 395.25 | 4138.2167 | 3% | 3% | 16% | 9% | Green | [In Prog] late start;
DSFFLOW-591 | In Progress | Upgrade | Core Network | Cloud-3PP/MPBN | 30 | 30 | 10 | 2025-04-22 | 2025-04-22 | 2025-06-05 | 2025-06-30 | 2025-06-30 |  | 69 | 69 | 850 | 850 | 387 | 789.5 | 8% | 33% | 221% | 46% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-3029 | In Progress | Migration | Core Network | IMS | 20 | 20 | 3 | 2025-05-07 | 2025-05-07 | 2025-07-14 | 2025-12-31 | 2025-12-31 |  | 238 | 238 | 902 | 902 | 336 | 902 | 0% | 15% | 58% | 37% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-4525 | In Progress | Migration | Core Network | UDM | 15 | 15 | 0 | 2025-08-11 | 2025-08-11 | 2025-08-29 | 2026-01-30 | 2026-01-30 |  | 172 | 172 | 1277 | 1277 | 297.5 | 1277 | 0% | 0% | 25% | 23% | Amber | [In Prog] time ticking without any work progress; efforts burnt misaligned with work progress; late start;
DSFFLOW-5245 | In Progress | Expansion, Maiden Installation | Core Network | Cloud | 72 | 72 | 0 | 2025-08-18 | 2025-08-18 | 2025-08-29 | 2026-06-30 | 2026-06-30 |  | 316 | 316 | 1478 | 1478 | 339.5 | 1448 | 2% | 0% | 11% | 23% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-5544 | In Progress | Maiden Installation | Core Network | Cloud-3PP/MPBN | 57 | 57 | 0 | 2025-05-26 | 2025-05-26 | 2025-08-28 | 2025-12-13 | 2025-12-13 |  | 201 | 201 | 3635.2 | 3635.2 | 260.75 | 3498.2 | 4% | 0% | 59% | 8% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-4605 | In Progress | Upgrade | Core Network | Cloud | 127 | 127 | 26 | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-12-31 | 2025-12-31 |  | 160 | 160 | 2196 | 2196 | 386 | 2196 | 0% | 20% | 38% | 18% | Green | [In Prog]
DSFFLOW-3127 | In Progress | Upgrade | Core Network | EPC | 57 | 57 | 8 | 2025-06-21 | 2025-06-23 | 2025-06-23 | 2025-08-30 | 2025-12-31 |  | 70 | 191 | 638 | 638 | 384 | 600 | 6% | 15% | 48% | 60% | Amber | [In Prog] efforts burnt misaligned with work progress;
DSFFLOW-5827 | In Progress | Upgrade | Core Network | UDM | 24 | 16 | 11 | 2025-07-27 | 2025-07-27 | 2025-07-26 | 2025-10-30 | 2025-10-30 |  | 95 | 95 | 376 | 376 | 340 | 340 | 10% | 69% | 60% | 90% | Amber | [In Prog] efforts burnt misaligned with work progress;
DSFFLOW-4379 | In Progress | Upgrade | Network Management | Element Management | 69 | 69 | 28 | 2025-08-03 | 2025-08-04 | 2025-08-04 | 2025-12-31 | 2025-12-31 |  | 150 | 149 | 1002.5 | 1002.5 | 383 | 925.5 | 8% | 41% | 33% | 38% | Green | [In Prog]
DSFFLOW-4628 | In Progress | Maiden Installation | Core Network | Core Network Automation, UDM | 29 | 29 | 0 | 2025-08-09 | 2025-08-09 | 2025-08-22 | 2026-06-29 | 2026-06-29 |  | 324 | 324 | 730 | 730 | 263 | 710 | 3% | 0% | 15% | 36% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-5079 | In Progress | Expansion | BOS | Monetization Charging | 67 | 67 | 39 | 2025-07-28 | 2025-07-28 | 2025-08-20 | 2025-09-30 | 2025-09-30 |  | 64 | 64 | 674.8 | 674.8 | 343.45 | 644.55 | 4% | 58% | 88% | 51% | Green | [In Prog] late start;
DSFFLOW-1400 | In Progress | Maiden Installation | Core Network | EPC | 37 | 37 | 5 | 2023-05-22 | 2023-05-22 | 2025-05-27 | 2025-07-30 | 2025-07-30 |  | 800 | 800 | 1432 | 1432 | 376 | 1432 | 0% | 15% | 107% | 26% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-3836 | In Progress | Upgrade | Network Management | Activation | 48 | 48 | 18 | 2025-05-31 | 2025-05-31 | 2025-07-30 | 2025-09-29 | 2025-09-29 |  | 121 | 121 | 612 | 612 | 354 | 540 | 12% | 38% | 94% | 58% | Green | [In Prog] work progress misaligned with time progress; late start;
DSFFLOW-4299 | In Progress | Upgrade | Core Network | Cloud, EPC, UDM | 88 | 88 | 11 | 2025-07-21 | 2025-07-28 | 2025-07-28 | 2025-10-31 | 2025-10-31 |  | 102 | 95 | 1686 | 1686 | 374.5 | 1617 | 4% | 13% | 59% | 22% | Green | [In Prog]
DSFFLOW-4992 | In Progress | Maiden Installation | Core Network | UDM | 16 | 16 | 4 | 2025-07-13 | 2025-07-13 | 2025-08-22 | 2025-12-31 | 2025-12-31 |  | 171 | 171 | 308 | 308 | 280 | 308 | 0% | 25% | 42% | 91% | Red | [In Prog] efforts burnt outweighing work output; late start;
DSFFLOW-4955 | In Progress | Maiden Installation | Network Management | Element Management | 77 | 77 | 8 | 2025-08-18 | 2025-08-18 | 2025-08-25 | 2025-11-28 | 2025-11-28 |  | 102 | 102 | 2003.5 | 2003.5 | 278 | 2003.5 | 0% | 10% | 35% | 15% | Green | [In Prog]
DSFFLOW-3342 | In Progress | Upgrade | Network Management | Activation, Resource Orchestration | 145 | 140 | 26 | 2025-07-10 | 2025-07-10 | 2025-07-10 | 2025-11-21 | 2026-06-12 |  | 134 | 337 | 3933 | 3933 | 295.5 | 3876 | 1% | 19% | 22% | 8% | Green | [In Prog]
DSFFLOW-4245 | In Progress | Upgrade | Network Management | Activation, Element Management, Resource Orchestration | 41 | 41 | 22 | 2025-07-21 | 2025-07-21 | 2025-08-06 | 2025-09-30 | 2025-09-30 |  | 71 | 71 | 461.9 | 461.9 | 374.79 | 462.65 | 0% | 54% | 89% | 81% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-1840 | In Progress | Upgrade | Network Management | Element Management | 1221 | 1221 | 888 | 2025-06-08 | 2025-06-08 | 2025-06-23 | 2025-11-06 | 2025-11-29 |  | 151 | 174 | 17146.71 | 17146.71 | 12375.8642 | 16834.0108 | 2% | 73% | 61% | 72% | Green | [In Prog] late start;
DSFFLOW-4713 | In Progress | Upgrade | Core Network | MSS | 38 | 38 | 15 | 2025-07-25 | 2025-08-25 | 2025-08-25 | 2025-08-30 | 2025-12-31 |  | 36 | 128 | 652 | 652 | 241 | 652 | 0% | 39% | 22% | 37% | Green | [In Prog]
DSFFLOW-6305 | In Progress | Upgrade | Core Network | EPC | 42 | 42 | 2 | 2025-09-08 | 2025-09-08 | 2025-09-19 | 2025-09-29 | 2025-10-19 |  | 21 | 41 | 378 | 378 | 64 | 378 | 0% | 5% | 36% | 17% | Green | [In Prog] late start;
DSFFLOW-5699 | In Progress | Upgrade | Network Management | Element Management | 55 | 51 | 5 | 2025-08-31 | 2025-08-31 | 2025-09-01 | 2025-11-18 | 2025-11-18 |  | 79 | 79 | 637.5 | 637.5 | 59.5 | 637.5 | 0% | 10% | 29% | 9% | Green | [In Prog]
DSFFLOW-4971 | In Progress | Expansion | Core Network | Cloud-3PP/MPBN | 44 | 44 | 3 | 2025-07-29 | 2025-07-29 | 2025-08-19 | 2025-11-30 | 2025-11-30 |  | 124 | 124 | 636 | 636 | 53.5 | 636 | 0% | 8% | 45% | 8% | Green | [In Prog] late start;
DSFFLOW-6689 | In Progress | Expansion | Core Network | Cloud | 61 | 61 | 1 | 2025-09-03 | 2025-09-03 | 2025-09-19 | 2025-12-31 | 2025-12-31 |  | 119 | 119 | 690 | 690 | 48 | 690 | 0% | 2% | 17% | 8% | Green | [In Prog] late start;
DSFFLOW-4028 | In Progress | Maiden Installation | Core Network | Cloud | 33 | 33 | 0 | 2025-07-14 | 2025-07-14 | 2025-07-30 | 2025-09-05 | 2025-09-05 |  | 53 | 53 | 1736 | 1736 | 42 | 1694 | 2% | 0% | 131% | 2% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-3411 | In Progress | Upgrade | Core Network | IMS | 46 | 46 | 0 | 2025-07-14 | 2025-07-14 | 2025-07-14 | 2025-08-15 | 2025-10-17 |  | 32 | 95 | 560 | 560 | 42 | 536 | 4% | 0% | 74% | 8% | Amber | [In Prog] time ticking without any work progress;
DSFFLOW-6356 | In Progress | Upgrade | Core Network | MSS | 28 | 28 | 0 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-12-19 | 2025-12-19 |  | 99 | 99 | 720 | 720 | 40 | 720 | 0% | 0% | 12% | 6% | Green | [In Prog]
DSFFLOW-6660 | In Progress | Upgrade, Expansion | Network Management | Element Management | 41 | 41 | 0 | 2025-09-16 | 2025-09-16 | 2025-09-18 | 2025-10-30 | 2025-10-30 |  | 44 | 44 | 830.5 | 830.5 | 35 | 812.5 | 2% | 0% | 16% | 4% | Green | [In Prog]
DSFFLOW-5918 | In Progress | Maiden Installation | Core Network | EPC | 94 | 94 | 0 | 2025-08-31 | 2025-08-31 | 2025-09-09 | 2026-12-31 | 2026-12-31 |  | 487 | 487 | 6447 | 6447 | 31 | 6442 | 0% | 0% | 5% | 0% | Green | [In Prog] late start;
DSFFLOW-5045 | In Progress | Maiden Installation | Core Network | Cloud, Core Network Automation, IMS | 40 | 40 | 0 | 2025-08-07 | 2025-08-07 | 2025-08-19 | 2025-12-19 | 2025-12-19 |  | 134 | 134 | 1139 | 1139 | 21.3 | 1139 | 0% | 0% | 35% | 2% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-3418 | In Progress | Upgrade | Core Network | IMS | 38 | 38 | 0 | 2025-07-14 | 2025-07-14 | 2025-07-14 | 2025-09-12 | 2025-09-22 |  | 60 | 70 | 515 | 515 | 20 | 495 | 4% | 0% | 100% | 4% | Amber | [In Prog] time ticking without any work progress;
DSFFLOW-5755 | In Progress | Upgrade | Core Network | IMS | 50 | 50 | 0 | 2025-08-17 | 2025-09-02 | 2025-09-02 | 2025-10-30 | 2025-10-30 |  | 74 | 58 | 476 | 476 | 8.8333 | 467.1667 | 2% | 0% | 36% | 2% | Amber | [In Prog] time ticking without any work progress;
DSFFLOW-5085 | In Progress | Expansion | BOS | Monetization Charging | 80 | 80 | 3 | 2025-08-04 | 2025-08-04 | 2025-08-20 | 2025-11-30 | 2025-11-30 |  | 118 | 118 | 794.9 | 794.9 | 65.5 | 797.2 | 0% | 4% | 42% | 8% | Green | [In Prog] late start;
DSFFLOW-2765 | In Progress | Upgrade | Core Network | Cloud, EPC | 49 | 49 | 2 | 2024-11-11 | 2024-11-11 | 2025-07-07 | 2024-12-20 | 2024-12-20 |  | 39 | 39 | 1560 | 1560 | 1 | 1534 | 2% | 4% | 790% | 0% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-6032 | In Progress | Maiden Installation, Migration | Core Network | Cloud, EPC | 795 | 795 | 0 | 2025-03-25 | 2025-03-25 | 2025-09-10 | 2026-12-30 | 2026-12-30 |  | 645 | 645 | 14876.5 | 14876.5 |  | 14876.5 | 0% | 0% | 29% | 0% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-2674 | In Progress | Maiden Installation | Core Network | EPC | 41 | 41 | 0 | 2024-05-01 | 2024-05-01 | 2025-07-10 | 2025-09-30 | 2025-09-30 |  | 517 | 517 | 1454 | 1454 |  | 1454 | 0% | 0% | 98% | 0% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-5903 | In Progress | Upgrade | Core Network | MSS | 22 | 22 | 0 | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2026-09-29 | 2026-09-29 |  | 425 | 425 | 195 | 195 |  | 195 | 0% | 0% | 13% | 0% | Green | [In Prog]
DSFFLOW-5135 | In Progress | Upgrade | Network Management | Element Management & Reporting | 300 | 300 | 0 | 2025-08-18 | 2025-08-18 | 2025-08-25 | 2025-12-31 | 2025-12-31 |  | 135 | 135 | 3521 | 3521 |  | 3521 | 0% | 0% | 26% | 0% | Amber | [In Prog] time ticking without any work progress;
DSFFLOW-6491 | In Progress | Expansion | Core Network | EPC, IMS | 70 | 70 | 0 | 2025-08-12 | 2025-08-12 | 2025-09-12 | 2025-10-31 | 2025-10-31 |  | 80 | 80 | 1120 | 1120 |  | 1120 | 0% | 0% | 52% | 0% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-6543 | In Progress | Expansion | Core Network | UDM | 46 | 46 | 0 | 2025-08-12 | 2025-08-12 | 2025-09-12 | 2025-12-19 | 2025-12-19 |  | 129 | 129 | 559 | 559 |  | 559 | 0% | 0% | 32% | 0% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-2843 | In Progress | Migration | BOS | Common Services-Data Migration | 10 | 10 | 0 | 2025-06-16 | 2025-06-16 | 2025-06-17 | 2026-12-31 | 2026-12-31 |  | 563 | 563 | 1 | 1 |  | 1 | 0% | 0% | 18% | 0% | Green | [In Prog]
DSFFLOW-3630 | In Progress | Migration | Core Network | Cloud | 60 | 60 | 0 | 2025-07-04 | 2025-07-04 | 2025-09-16 | 2025-12-31 | 2025-12-31 |  | 180 | 180 | 2549 | 2549 |  | 2549 | 0% | 0% | 45% | 0% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-6446 | In Progress | Upgrade | Core Network | UDM | 22 | 22 | 0 | 2025-08-07 | 2025-08-07 | 2025-09-12 | 2025-12-12 | 2025-12-12 |  | 127 | 127 | 587.5 | 587.5 |  | 587.5 | 0% | 0% | 37% | 0% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-5812 | In Progress | Upgrade | Core Network | MSS | 216 | 216 | 0 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-11-20 | 2025-11-20 |  | 70 | 70 | 1368 | 1368 |  | 1368 | 0% | 0% | 17% | 0% | Green | [In Prog]
DSFFLOW-5981 | In Progress | Business Configuration | BOS | Monetization Charging | 32 | 32 | 0 | 2025-08-03 | 2025-08-03 | 2025-09-12 | 2025-12-30 | 2025-12-30 |  | 149 | 149 | 798.4 | 798.4 |  | 798.4 | 0% | 0% | 34% | 0% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-5621 | In Progress | Upgrade | Core Network | MSS | 36 | 36 | 0 | 2025-08-29 | 2025-08-29 | 2025-08-29 | 2026-12-30 | 2026-12-30 |  | 488 | 488 | 319 | 319 |  | 319 | 0% | 0% | 5% | 0% | Green | [In Prog]
DSFFLOW-4483 | In Progress | Expansion | Core Network | EPC | 12 | 12 | 8 | 2025-08-18 | 2025-08-18 | 2025-08-06 | 2025-09-12 | 2025-09-12 |  | 25 | 25 | 161 | 161 | 1 | 161 | 0% | 67% | 138% | 1% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress; early start;
DSFFLOW-3596 | In Progress | Upgrade | Core Network | UDM | 36 | 36 | 2 | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-10-31 | 2025-10-31 |  | 99 | 99 | 481.5 | 481.5 | 66 | 481.5 | 0% | 6% | 61% | 15% | Green | [In Prog] work progress misaligned with time progress;
DSFFLOW-1474 | In Progress | Upgrade | Core Network | IMS | 54 | 54 | 5 | 2025-03-24 | 2025-03-20 | 2025-03-20 | 2025-08-30 | 2025-07-15 |  | 159 | 117 | 461.5 | 461.5 | 72 | 393.5 | 15% | 9% | 158% | 16% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress;
DSFFLOW-6349 | In Progress | Upgrade | Core Network | MSS | 24 | 24 | 1 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-12-31 | 2025-12-31 |  | 111 | 111 | 474 | 474 | 80 | 474 | 0% | 4% | 11% | 17% | Green | [In Prog]
DSFFLOW-5797 | In Progress | Upgrade | Core Network | IMS | 30 | 30 | 10 | 2025-08-03 | 2025-08-03 | 2025-08-03 | 2025-11-29 | 2025-11-29 |  | 118 | 118 | 746 | 746 | 240 | 746 | 0% | 33% | 43% | 32% | Green | [In Prog]
DSFFLOW-4343 | In Progress | Upgrade | Core Network | Cloud, EPC | 141 | 141 | 4 | 2025-06-19 | 2025-06-19 | 2025-08-18 | 2025-12-19 | 2025-12-19 |  | 183 | 183 | 3597 | 3597 | 239 | 3597 | 0% | 3% | 52% | 8% | Green | [In Prog] late start;
DSFFLOW-4916 | In Progress | Upgrade | Network Management | Element Management | 78 | 78 | 12 | 2025-08-18 | 2025-08-18 | 2025-08-25 | 2025-12-15 | 2025-12-15 |  | 119 | 119 | 1231.8 | 1231.8 | 238.01 | 1231.81 | 0% | 15% | 30% | 19% | Green | [In Prog]
DSFFLOW-4198 | In Progress | Upgrade | Core Network | UDM | 16 | 16 | 5 | 2025-07-30 | 2025-08-04 | 2025-08-04 | 2025-09-30 | 2025-10-31 |  | 62 | 88 | 460 | 460 | 237.5 | 377.5 | 18% | 31% | 57% | 52% | Amber | [In Prog] efforts burnt misaligned with work progress;
DSFFLOW-5060 | In Progress | Maiden Installation | Core Network | IMS | 50 | 50 | 3 | 2025-08-07 | 2025-08-07 | 2025-08-19 | 2025-12-19 | 2025-12-19 |  | 134 | 134 | 2379 | 2379 | 214 | 2369 | 0% | 6% | 35% | 9% | Green | [In Prog] late start;
DSFFLOW-535 | In Progress | Maiden Installation | Core Network | EPC | 14 | 14 | 13 | 2025-01-01 | 2024-12-31 | 2025-01-01 | 2025-07-31 | 2025-05-29 | 2025-04-30 | 211 | 149 | 149 | 149 | 206 | 198 | -33% | 93% | 81% | 138% | Red | [In Prog] effort budget breached; projecting 5%+ EAC effort overrun; efforts burnt misaligned with work progress; efforts burnt misaligned with time progress;
DSFFLOW-2962 | In Progress | Maiden Installation | Core Network | Cloud | 101 | 101 | 0 | 2025-07-07 | 2025-07-07 | 2025-08-05 | 2025-12-30 | 2025-12-30 |  | 176 | 176 | 1816 | 1816 | 192.0008 | 1816 | 0% | 0% | 44% | 11% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-5401 | In Progress | Upgrade | Core Network | Exposure, IMS | 102 | 102 | 8 | 2025-08-22 | 2025-07-22 | 2025-07-22 | 2025-12-31 | 2026-01-23 |  | 131 | 185 | 1405.4 | 1405.4 | 184.13 | 1397.3867 | 1% | 8% | 34% | 13% | Green | [In Prog]
DSFFLOW-3265 | In Progress | Migration | Core Network | Cloud, Core Network Automation, EPC, IMS, UDM | 88 | 88 | 1 | 2025-05-15 | 2025-05-15 | 2025-09-12 | 2025-11-20 | 2025-11-20 |  | 189 | 189 | 8395 | 8395 | 162 | 8395 | 0% | 1% | 69% | 2% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-5029 | In Progress | Upgrade | Core Network | UDM | 28 | 28 | 3 | 2025-07-29 | 2025-07-14 | 2025-07-14 | 2025-11-03 | 2025-10-31 |  | 97 | 109 | 608 | 608 | 160 | 608 | 0% | 11% | 65% | 26% | Green | [In Prog] work progress misaligned with time progress;
DSFFLOW-5888 | In Progress | Maiden Installation | Core Network | IMS | 19 | 19 | 0 | 2025-09-01 | 2025-09-01 | 2025-09-08 | 2025-09-29 | 2025-09-29 |  | 28 | 28 | 595.2 | 595.2 | 157.6 | 545.6 | 8% | 0% | 76% | 26% | Amber | [In Prog] time ticking without any work progress; efforts burnt misaligned with work progress;
DSFFLOW-5200 | In Progress | Upgrade | Core Network | Cloud | 52 | 52 | 6 | 2025-08-31 | 2025-08-11 | 2025-08-11 | 2025-10-23 | 2025-10-23 |  | 53 | 73 | 691 | 691 | 152 | 651 | 6% | 12% | 58% | 22% | Green | [In Prog]
DSFFLOW-5446 | In Progress | Maiden Installation | Core Network | UDM | 20 | 20 | 0 | 2025-08-25 | 2025-08-25 | 2025-08-28 | 2025-10-31 | 2025-10-31 |  | 67 | 67 | 521 | 521 | 144 | 521 | 0% | 0% | 43% | 29% | Amber | [In Prog] time ticking without any work progress; efforts burnt misaligned with work progress;
DSFFLOW-5843 | In Progress | Upgrade | Core Network | MSS | 27 | 23 | 3 | 2025-09-02 | 2025-09-08 | 2025-09-16 | 2025-12-31 | 2025-12-31 |  | 120 | 114 | 588.5 | 588.5 | 137.5 | 563 | 4% | 13% | 13% | 23% | Green | [In Prog] late start;
DSFFLOW-6166 | In Progress | Upgrade | Core Network | Cloud | 17 | 17 | 5 | 2025-08-25 | 2025-08-25 | 2025-09-09 | 2025-09-10 | 2025-09-10 |  | 16 | 16 | 158 | 158 | 134 | 158 | 0% | 29% | 171% | 85% | Red | [In Prog] efforts burnt outweighing work output; efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-6252 | In Progress | Upgrade | Network Management | Element Management | 111 | 111 | 2 | 2025-09-13 | 2025-09-13 | 2025-09-10 | 2026-06-29 | 2026-06-29 |  | 289 | 289 | 2239 | 2239 | 133.5 | 2194 | 2% | 2% | 3% | 6% | Green | [In Prog]
DSFFLOW-1679 | In Progress | Maiden Installation | Core Network | Cloud-3PP/MPBN | 30 | 30 | 1 | 2025-05-16 | 2025-05-16 | 2025-07-22 | 2026-12-31 | 2026-12-31 |  | 594 | 594 | 1088.5 | 1088.5 | 128.5 | 1073 | 1% | 3% | 22% | 12% | Green | [In Prog] late start;
DSFFLOW-6379 | In Progress | Upgrade | Core Network | EPC | 22 | 22 | 2 | 2025-09-09 | 2025-09-09 | 2025-09-19 | 2025-09-23 | 2025-09-23 |  | 14 | 14 | 216 | 216 | 112 | 216 | 0% | 9% | 93% | 52% | Amber | [In Prog] efforts burnt misaligned with work progress; work progress misaligned with time progress; late start;
DSFFLOW-4624 | In Progress | Maiden Installation | Core Network | Signaling | 18 | 18 | 0 | 2025-08-09 | 2025-08-09 | 2025-08-22 | 2026-06-29 | 2026-06-29 |  | 324 | 324 | 570 | 570 | 111 | 559 | 2% | 0% | 15% | 19% | Green | [In Prog] late start;
DSFFLOW-6271 | In Progress | Upgrade | Network Management | Resource Orchestration | 28 | 25 | 11 | 2025-03-03 | 2025-03-03 | 2025-09-09 | 2025-10-09 | 2025-10-10 |  | 220 | 221 | 310 | 310 | 110.4167 | 294.1667 | 5% | 44% | 92% | 36% | Amber | [In Prog] efforts burnt misaligned with time progress; late start;
DSFFLOW-5683 | In Progress | Maiden Installation | Core Network | Cloud, EPC, UDM | 131 | 131 | 1 | 2025-08-25 | 2025-08-25 | 2025-09-04 | 2025-12-22 | 2025-12-22 |  | 119 | 119 | 2340 | 2372 | 102 | 2372 | 0% | 1% | 24% | 4% | Green | [In Prog] late start;
DSFFLOW-5578 | In Progress | Upgrade | Core Network | Cloud | 20 | 20 | 1 | 2025-08-27 | 2025-09-04 | 2025-09-04 | 2025-10-30 | 2025-10-30 |  | 64 | 56 | 286 | 286 | 96 | 286 | 0% | 5% | 33% | 34% | Amber | [In Prog] efforts burnt misaligned with work progress;
DSFFLOW-662 | In Progress | Maiden Installation | Network Management | Resource Orchestration | 63 | 50 | 8 | 2025-03-04 | 2025-03-04 | 2025-06-05 | 2026-12-31 | 2026-12-31 |  | 667 | 667 | 576.2 | 206.3 | 92.9667 | 538.7833 | -161% | 16% | 30% | 45% | Red | [In Prog] projecting 5%+ EAC effort overrun; efforts burnt misaligned with work progress; late start;
DSFFLOW-4880 | In Progress | Migration | Core Network | Cloud-3PP/MPBN, IMS, MSS, Signaling, UDM | 135 | 135 | 0 | 2025-08-13 | 2025-08-13 | 2025-09-05 | 2025-12-05 | 2025-12-05 |  | 114 | 114 | 2814.2 | 2814.2 | 88.1 | 2814.1 | 0% | 0% | 36% | 3% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-6398 | In Progress | Expansion | Core Network | MSS, Signaling | 67 | 67 | 0 | 2025-08-12 | 2025-08-12 | 2025-09-12 | 2025-08-29 | 2025-10-31 |  | 17 | 80 | 1525 | 1525 | 85 | 1440 | 6% | 0% | 52% | 6% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-970 | In Progress | Upgrade | Core Network | Cloud-3PP/MPBN | 27 | 27 | 2 | 2025-05-08 | 2025-05-08 | 2025-08-07 | 2025-07-29 | 2025-07-29 |  | 82 | 82 | 660.75 | 660.75 | 81.5 | 658.25 | 0% | 8% | 166% | 12% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-6286 | In Progress | Upgrade | Core Network | EPC | 18 | 18 | 2 | 2025-08-25 | 2025-08-25 | 2025-09-10 | 2025-09-18 | 2025-10-20 |  | 24 | 56 | 141 | 141 | 80 | 141 | 0% | 11% | 51% | 57% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-4442 | In Progress | Upgrade | Network Management | Element Management | 25 | 24 | 10 | 2025-07-27 | 2025-07-27 | 2025-08-06 | 2025-09-18 | 2025-09-18 |  | 53 | 53 | 418.2 | 418.2 | 242.5 | 415.7 | 1% | 42% | 107% | 58% | Green | [In Prog] work progress misaligned with time progress; late start;
DSFFLOW-6476 | In Progress | Upgrade | Core Network | MSS | 12 | 12 | 0 | 2025-08-01 | 2025-08-01 | 2025-09-18 | 2025-10-15 | 2025-10-15 |  | 75 | 75 | 220 | 220 |  | 220 | 0% | 0% | 70% | 0% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-5417 | In Progress | Maiden Installation, Business Configuration | BOS | Core Commerce | 39 | 39 | 1 | 2025-05-20 | 2025-05-20 | 2025-08-28 | 2026-07-30 | 2026-07-30 |  | 436 | 436 | 20355 | 20355 | 428 | 19931 | 2% | 3% | 29% | 2% | Green | [In Prog] late start;
DSFFLOW-3060 | In Progress | Upgrade | Core Network | UDM | 71 | 44 | 20 | 2025-06-25 | 2025-07-16 | 2025-07-16 | 2025-11-28 | 2025-11-28 |  | 156 | 135 | 1032 | 832 | 428 | 756 | 9% | 45% | 51% | 51% | Green | [In Prog]
DSFFLOW-2750 | In Progress | Maiden Installation, Migration | Core Network | IMS | 189 | 189 | 12 | 2025-06-24 | 2025-06-24 | 2025-07-09 | 2025-12-26 | 2025-12-26 |  | 185 | 185 | 5869 | 5869 | 1400.7 | 5469 | 8% | 6% | 49% | 24% | Green | [In Prog] late start;
DSFFLOW-3044 | In Progress | Maiden Installation | Core Network, Network Management | Activation, Signaling, UDM | 263 | 289 | 134 | 2025-07-09 | 2025-07-09 | 2025-07-15 | 2025-12-31 | 2025-12-31 |  | 175 | 175 | 3496 | 4277 | 1380.1 | 3464.1 | 19% | 46% | 43% | 32% | Green | [In Prog]
DSFFLOW-151 | In Progress | Upgrade | Network Management | Element Management | 87 | 75 | 60 | 2025-04-13 | 2025-04-13 | 2025-04-13 | 2025-09-26 | 2025-09-26 |  | 166 | 166 | 1719 | 1545 | 1379.5 | 1418.0167 | 8% | 80% | 98% | 89% | Green | [In Prog]
DSFFLOW-2882 | In Progress | Upgrade | BOS | D&A Mediation, Monetization Billing | 37 | 37 | 10 | 2025-05-10 | 2025-05-10 | 2025-07-10 | 2025-11-18 | 2025-11-18 |  | 192 | 192 | 2844.2497 | 2844.2497 | 1360.1 | 2748.7997 | 3% | 27% | 70% | 48% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-4124 | In Progress | Maiden Installation | Network Management | Element Management | 113 | 113 | 40 | 2025-07-31 | 2025-07-31 | 2025-08-04 | 2026-01-30 | 2026-01-30 |  | 183 | 183 | 4680 | 4680 | 1356 | 4676 | 0% | 35% | 29% | 29% | Green | [In Prog]
DSFFLOW-2656 | In Progress | Upgrade | Network Management | Element Management | 96 | 98 | 63 | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-12-19 | 2025-12-19 |  | 171 | 171 | 2840 | 2544 | 1350.7333 | 2492.8333 | 2% | 64% | 49% | 53% | Green | [In Prog]
DSFFLOW-1713 | In Progress | Upgrade | Core Network | UDM | 18 | 18 | 8 | 2025-03-15 | 2025-03-15 | 2025-03-15 | 2025-10-30 | 2025-10-30 |  | 229 | 229 | 2328 | 2328 | 1341 | 2336 | 0% | 44% | 83% | 58% | Green | [In Prog]
DSFFLOW-4085 | In Progress | Upgrade | Core Network | Cloud | 206 | 206 | 27 | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-11-14 | 2025-11-14 |  | 130 | 130 | 7116.98 | 7116.98 | 1283.96 | 7008.54 | 2% | 13% | 60% | 18% | Green | [In Prog]
DSFFLOW-1568 | In Progress | Upgrade | BOS | D&A Mediation | 33 | 33 | 17 | 2025-05-25 | 2025-05-25 | 2025-06-30 | 2025-09-19 | 2025-09-19 |  | 117 | 117 | 1614.5 | 1614.5 | 1169.0133 | 1503.14 | 8% | 52% | 103% | 72% | Green | [In Prog] work progress misaligned with time progress; late start;
DSFFLOW-2544 | In Progress | Maiden Installation | Core Network | Cloud-3PP/MPBN | 78 | 78 | 2 | 2025-04-19 | 2025-04-19 | 2025-06-26 | 2025-10-31 | 2025-10-31 |  | 195 | 195 | 8854.5 | 8854.5 | 1160.5 | 8738 | 1% | 3% | 80% | 13% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-2249 | In Progress | Upgrade, Expansion, Maiden Installation | BOS | Monetization Charging | 396 | 396 | 42 | 2025-06-22 | 2025-06-22 | 2025-06-27 | 2025-09-19 | 2025-11-28 |  | 89 | 159 | 3683.11 | 3683.11 | 1154.2 | 3173.29 | 15% | 11% | 58% | 31% | Amber | [In Prog] efforts burnt misaligned with work progress;
DSFFLOW-3649 | In Progress | Upgrade | Core Network | IMS | 31 | 31 | 16 | 2025-07-03 | 2025-07-03 | 2025-07-03 | 2025-12-30 | 2025-12-30 |  | 180 | 180 | 2715 | 2715 | 1150 | 2595 | 4% | 52% | 45% | 42% | Green | [In Prog]
DSFFLOW-4677 | In Progress | Maiden Installation | Core Network | EPC | 127 | 127 | 2 | 2025-08-11 | 2025-08-11 | 2025-08-11 | 2026-12-31 | 2026-12-31 |  | 507 | 507 | 10485.6 | 10485.6 | 1120.75 | 10435.6 | 0% | 2% | 8% | 11% | Green | [In Prog]
DSFFLOW-2435 | In Progress | Upgrade | Core Network | EPC | 16 | 16 | 10 | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-10-30 | 2025-10-30 |  | 136 | 136 | 558 | 558 | 428 | 542 | 3% | 63% | 72% | 77% | Green | [In Prog]
DSFFLOW-4498 | In Progress | Upgrade | Core Network | EPC, IMS, MSS, UDM | 210 | 206 | 21 | 2025-07-15 | 2025-07-15 | 2025-07-15 | 2026-01-15 | 2026-01-15 |  | 184 | 184 | 3907 | 3907 | 1021.1667 | 3895.8333 | 0% | 10% | 38% | 26% | Green | [In Prog]
DSFFLOW-3669 | In Progress | Upgrade | Core Network | EPC, IMS, Signaling, UDM | 226 | 226 | 19 | 2025-06-09 | 2025-06-19 | 2025-06-19 | 2025-10-30 | 2025-11-30 |  | 143 | 164 | 4764 | 4764 | 1013.25 | 4630 | 3% | 8% | 58% | 21% | Green | [In Prog]
DSFFLOW-1662 | In Progress | Upgrade | Network Management | Element Management | 67 | 67 | 45 | 2025-05-07 | 2025-05-07 | 2025-06-06 | 2025-07-31 | 2025-09-30 |  | 85 | 146 | 1440 | 1440 | 1010 | 1355 | 6% | 67% | 95% | 70% | Green | [In Prog] late start;
DSFFLOW-2169 | In Progress | Maiden Installation | Core Network | EPC, Signaling, UDM | 327 | 327 | 1 | 2025-06-15 | 2025-06-15 | 2025-06-24 | 2027-08-20 | 2027-08-20 |  | 796 | 796 | 29308.1 | 29308.1 | 998.7 | 29302.09 | 0% | 0% | 13% | 3% | Green | [In Prog] late start;
DSFFLOW-4140 | In Progress | Upgrade | Core Network | Cloud, EPC, IMS, UDM | 97 | 97 | 21 | 2025-04-16 | 2025-04-16 | 2025-04-16 | 2025-12-30 | 2025-12-30 |  | 258 | 258 | 2201 | 2201 | 996 | 2121 | 4% | 22% | 62% | 45% | Amber | [In Prog] efforts burnt misaligned with work progress;
DSFFLOW-3311 | In Progress | Expansion | BOS | Monetization Charging | 415 | 415 | 171 | 2025-07-27 | 2025-07-27 | 2025-07-22 | 2025-09-30 | 2025-09-30 |  | 65 | 65 | 3533.6 | 3533.6 | 946.55 | 3015.1 | 15% | 41% | 88% | 27% | Amber | [In Prog] efforts burnt misaligned with time progress;
DSFFLOW-3498 | In Progress | Migration | Core Network | EPC, Signaling, UDM | 77 | 77 | 37 | 2025-06-18 | 2025-06-18 | 2025-07-23 | 2025-12-31 | 2025-12-31 |  | 196 | 196 | 1514.6 | 1514.6 | 936.5 | 1474.6 | 3% | 48% | 49% | 62% | Green | [In Prog] late start;
DSFFLOW-3745 | In Progress | Migration | Core Network | UDM | 15 | 14 | 0 | 2025-07-28 | 2025-07-28 | 2025-08-12 | 2025-12-26 | 2025-12-26 |  | 151 | 151 | 2080 | 2080 | 911.5 | 2080 | 0% | 0% | 38% | 44% | Amber | [In Prog] time ticking without any work progress; efforts burnt misaligned with work progress; late start;
DSFFLOW-4694 | In Progress | Upgrade | Core Network | Cloud | 48 | 48 | 11 | 2025-07-13 | 2025-07-14 | 2025-07-14 | 2025-12-30 | 2025-12-30 |  | 170 | 169 | 2298 | 2298 | 875 | 2263 | 2% | 23% | 42% | 38% | Green | [In Prog]
DSFFLOW-6590 | In Progress | Maiden Installation | Core Network | IMS | 23 | 23 | 0 | 2025-08-25 | 2025-08-25 | 2025-09-16 | 2028-12-31 | 2028-12-31 |  | 1224 | 1224 | 1559.99 | 1559.99 | 836 | 1559.99 | 0% | 0% | 2% | 54% | Red | [In Prog] efforts burning without any work progress; late start;
DSFFLOW-3528 | In Progress | Upgrade | Core Network | EPC | 130 | 130 | 14 | 2025-07-04 | 2025-07-07 | 2025-07-07 | 2025-12-31 | 2025-12-31 |  | 180 | 177 | 1992 | 1992 | 820 | 1912 | 4% | 11% | 44% | 41% | Amber | [In Prog] efforts burnt misaligned with work progress;
DSFFLOW-677 | In Progress | Upgrade | Core Network | IMS | 102 | 102 | 88 | 2025-04-24 | 2025-04-14 | 2025-04-14 | 2025-12-31 | 2025-09-30 |  | 251 | 169 | 1792 | 1800 | 1402 | 1720 | 4% | 86% | 95% | 78% | Green | [In Prog]
DSFFLOW-4070 | In Progress | Maiden Installation | BOS | Core Commerce, D&A Mediation, Monetization Billing | 60 | 60 | 0 | 2025-06-06 | 2025-06-06 | 2025-07-31 | 2027-12-31 | 2027-12-31 |  | 938 | 938 | 48905.4997 | 48905.4997 | 1410.25 | 48677.4997 | 0% | 0% | 12% | 3% | Green | [In Prog] late start; Delivery Manager not assigned
DSFFLOW-862 | In Progress | Upgrade | Core Network | MSS | 63 | 63 | 22 | 2025-05-05 | 2025-05-19 | 2025-05-19 | 2025-12-31 | 2025-12-31 |  | 240 | 226 | 2474.75 | 2474.75 | 1468.1 | 2474.75 | 0% | 35% | 57% | 59% | Amber | [In Prog] efforts burnt misaligned with work progress;
DSFFLOW-1119 | In Progress | Upgrade | Network Management | Element Management | 161 | 160 | 53 | 2025-05-15 | 2025-05-21 | 2025-06-02 | 2025-12-31 | 2025-12-31 |  | 230 | 224 | 3306 | 3298 | 1469 | 2716.5 | 18% | 33% | 57% | 45% | Green | [In Prog] late start;
DSFFLOW-245 | In Progress | Upgrade, Maiden Installation | Network Management | Element Management | 853 | 545 | 107 | 2025-05-15 | 2025-04-07 |  | 2025-10-01 | 2025-12-31 |  | 139 | 268 | 24189 | 16930 | 12088.5 | 15530.5 | 8% | 20% | 63% | 71% | Red | [In Prog] efforts burnt outweighing work output;
DSFFLOW-760 | In Progress | Upgrade | BOS | D&A Mediation, Monetization Charging | 2546 | 2546 | 796 | 2025-05-05 | 2025-05-05 | 2025-05-12 | 2026-04-20 | 2026-04-20 |  | 350 | 350 | 33240.9 | 33240.9 | 11333.7017 | 32190.8117 | 3% | 31% | 40% | 34% | Green | [In Prog]
DSFFLOW-447 | In Progress | Upgrade | BOS | Monetization Billing | 37 | 37 | 19 | 2025-04-01 | 2025-04-01 | 2025-05-20 | 2025-12-05 | 2025-12-05 |  | 248 | 248 | 10676.2 | 10676.2 | 7670.6097 | 9687.71 | 9% | 51% | 70% | 72% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-5109 | In Progress | Maiden Installation, Migration | Core Network, Network Management | Cloud, Core Network Automation, EPC, IMS, MSS, Resource Orchestration, UDM | 248 | 248 | 203 | 2025-06-01 | 2025-06-01 | 2025-08-22 | 2025-09-29 | 2025-09-29 |  | 120 | 120 | 8622.5 | 8622.5 | 7252.16 | 8162.5 | 5% | 82% | 94% | 84% | Green | [In Prog] late start;
DSFFLOW-507 | In Progress | Upgrade | Network Management | Element Management & Reporting | 527 | 1464 | 468 | 2025-02-28 | 2025-03-01 | 2025-06-26 | 2025-07-30 | 2025-09-29 |  | 152 | 212 | 6628 | 18453 | 5450.6833 | 16611.6833 | 10% | 32% | 97% | 30% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-576 | In Progress | Upgrade | BOS | Monetization Billing | 34 | 34 | 22 | 2025-03-03 | 2025-03-03 | 2025-05-13 | 2025-08-14 | 2025-10-10 |  | 164 | 221 | 7946.6 | 7946.6 | 5055.2 | 7691.4 | 3% | 65% | 92% | 64% | Green | [In Prog] late start;
DSFFLOW-741 | In Progress | Upgrade | Network Management | Element Management | 159 | 159 | 146 | 2025-04-22 | 2025-04-22 | 2025-05-19 | 2025-09-19 | 2025-10-10 |  | 150 | 171 | 5800 | 5800 | 4740.8333 | 6025.8333 | -4% | 92% | 90% | 82% | Amber | [In Prog] projecting 1%+ EAC effort overrun ; late start;
DSFFLOW-1278 | In Progress | Migration | Core Network | IMS | 353 | 340 | 289 | 2025-05-08 | 2025-05-08 | 2025-05-22 | 2025-09-15 | 2025-09-19 |  | 130 | 134 | 4478.5 | 4478.5 | 4006.0758 | 4337.0758 | 3% | 85% | 102% | 89% | Green | [In Prog] late start;
DSFFLOW-5184 | In Progress | Upgrade | Core Network, Network Management | Activation, Core Network Automation, EPC, Exposure, Signaling, UDM | 127 | 127 | 66 | 2025-06-15 | 2025-08-25 | 2025-08-25 | 2025-10-31 | 2025-10-31 |  | 138 | 67 | 5333 | 5333 | 3233 | 5116 | 4% | 52% | 43% | 61% | Green | [In Prog]
DSFFLOW-1416 | In Progress | Migration | Core Network, Network Management | Activation, EPC, IMS, MSS, UDM | 139 | 155 | 23 | 2025-04-23 | 2025-04-23 | 2025-05-27 | 2025-12-31 | 2025-12-31 |  | 252 | 252 | 8449.25 | 8449.25 | 3050.255 | 8234.75 | 3% | 15% | 60% | 36% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-2078 | In Progress | Upgrade, Maiden Installation | Core Network | EPC, IMS | 46 | 55 | 50 | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-09-26 | 2025-09-26 |  | 101 | 101 | 1930 | 3252 | 2924 | 3228 | 1% | 91% | 96% | 90% | Green | [In Prog]
DSFFLOW-3475 | In Progress | Upgrade | Core Network | EPC, IMS, Signaling, UDM | 190 | 190 | 118 | 2025-04-30 | 2025-05-05 | 2025-05-05 | 2025-09-29 | 2025-09-29 |  | 152 | 147 | 3427.5 | 3427.5 | 2866.25 | 3314.5 | 3% | 62% | 95% | 84% | Amber | [In Prog] efforts burnt misaligned with work progress;
DSFFLOW-1926 | In Progress | Maiden Installation | Core Network | Cloud | 97 | 97 | 15 | 2025-05-26 | 2025-05-26 | 2025-07-10 | 2026-12-31 | 2026-12-31 |  | 584 | 584 | 2188.6 | 2188.6 | 817.6 | 2098.6 | 4% | 15% | 21% | 37% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-2123 | In Progress | Maiden Installation | Core Network, Network Management | Activation, Core Network Automation, EPC, Exposure, UDM | 82 | 82 | 21 | 2025-05-07 | 2025-05-07 | 2025-06-20 | 2026-10-30 | 2026-10-30 |  | 541 | 541 | 6272 | 6272 | 2819 | 6027 | 4% | 26% | 26% | 45% | Green | [In Prog] late start;
DSFFLOW-2402 | In Progress | Upgrade | BOS | Monetization Charging | 169 | 169 | 24 | 2025-05-05 | 2025-05-05 | 2025-07-08 | 2026-06-29 | 2026-06-30 |  | 420 | 421 | 18647.44 | 18647.44 | 2646.5 | 17668 | 5% | 15% | 33% | 15% | Green | [In Prog] late start;
DSFFLOW-206 | In Progress | Upgrade | Core Network | IMS | 214 | 188 | 93 | 2025-02-16 | 2025-04-15 | 2025-04-15 | 2025-12-18 | 2025-10-30 |  | 305 | 198 | 3892 | 3892 | 2456.5 | 3362.75 | 15% | 49% | 81% | 63% | Green | [In Prog]
DSFFLOW-1307 | In Progress | Expansion | BOS | Monetization Charging | 161 | 161 | 160 | 2025-05-11 | 2025-05-11 | 2025-05-11 | 2025-08-21 | 2025-09-30 |  | 102 | 142 | 4315.75 | 4315.75 | 2405.2667 | 2746.0167 | 36% | 99% | 94% | 57% | Amber | [In Prog] efforts burnt misaligned with work progress;
DSFFLOW-2047 | In Progress | Upgrade | Network Management | Element Management | 368 | 402 | 50 | 2025-05-08 | 2025-05-08 | 2025-06-18 | 2026-08-31 | 2026-08-31 |  | 480 | 480 | 9297 | 11569 | 2279 | 11475 | 1% | 12% | 29% | 20% | Green | [In Prog] late start;
DSFFLOW-1584 | In Progress | Maiden Installation | Core Network, Network Management | Activation, Core Network Automation, EPC, IMS, Resource Orchestration, UDM | 43 | 53 | 45 | 2025-05-12 | 2025-05-12 | 2025-05-12 | 2025-09-15 | 2025-09-15 |  | 126 | 126 | 2549.99 | 2549.99 | 2148.99 | 2532.99 | 1% | 85% | 106% | 84% | Green | [In Prog]
DSFFLOW-115 | In Progress | Upgrade | Network Management | Element Management | 192 | 181 | 81 | 2025-03-16 | 2025-03-17 | 2025-03-27 | 2025-06-29 | 2025-09-30 |  | 105 | 197 | 3902 | 3750 | 2100 | 2740 | 27% | 45% | 96% | 57% | Green | [In Prog] work progress misaligned with time progress; late start;
DSFFLOW-1911 | In Progress | Migration | Core Network | EPC | 41 | 53 | 27 | 2025-04-03 | 2025-04-03 | 2025-06-13 | 2025-11-30 | 2025-11-29 |  | 241 | 240 | 3433 | 4421 | 2097 | 4388 | 1% | 51% | 72% | 47% | Green | [In Prog] late start;
DSFFLOW-2384 | In Progress | Upgrade | Network Management | Resource Orchestration | 12 | 12 | 5 | 2025-06-16 | 2025-06-01 | 2025-06-24 | 2026-06-30 | 2026-12-31 |  | 379 | 578 | 4016.35 | 4016.35 | 1772.25 | 2892.85 | 29% | 42% | 20% | 44% | Green | [In Prog] late start;
DSFFLOW-5732 | In Progress | Upgrade | Core Network | Cloud, UDM | 149 | 143 | 119 | 2025-07-27 | 2025-07-28 | 2025-07-28 | 2025-10-30 | 2025-10-30 |  | 95 | 94 | 2596 | 2540 | 1754 | 2456 | 3% | 83% | 60% | 69% | Green | [In Prog]
DSFFLOW-3109 | In Progress | Upgrade | Core Network | IMS | 153 | 169 | 102 | 2025-07-14 | 2025-07-14 | 2025-07-14 | 2025-08-29 | 2025-09-29 |  | 46 | 77 | 2101 | 2411 | 1709.26 | 2192.01 | 9% | 60% | 91% | 71% | Green | [In Prog]
DSFFLOW-3760 | In Progress | Maiden Installation | Core Network | Signaling, UDM | 29 | 29 | 0 | 2025-03-31 | 2025-03-31 | 2025-07-29 | 2026-03-31 | 2026-03-31 |  | 365 | 365 | 6752 | 6752 | 1680 | 6752 | 0% | 0% | 48% | 25% | Amber | [In Prog] time ticking without any work progress; efforts burnt misaligned with work progress; late start;
DSFFLOW-2513 | In Progress | Maiden Installation | Core Network | EPC, Signaling | 46 | 46 | 0 | 2024-07-25 | 2024-07-25 | 2025-07-24 | 2025-12-31 | 2025-12-31 |  | 524 | 524 | 1896 | 1896 | 1584 | 1736 | 8% | 0% | 81% | 84% | Red | [In Prog] efforts burning without any work progress; time ticking without any work progress; late start;
DSFFLOW-2009 | In Progress | Upgrade | Core Network | Cloud, EPC, IMS, UDM | 172 | 172 | 150 | 2025-04-29 | 2025-04-29 | 2025-04-29 | 2026-03-31 | 2026-03-31 |  | 336 | 336 | 3164 | 3164 | 2696 | 2975 | 6% | 87% | 44% | 85% | Green | [In Prog]
DSFFLOW-2689 | In Progress | Upgrade | Network Management | Element Management | 130 | 128 | 58 | 2025-06-23 | 2025-07-14 | 2025-07-14 | 2026-03-31 | 2025-11-30 |  | 281 | 139 | 1759.9 | 1805.4 | 813.3997 | 1722.3997 | 5% | 45% | 51% | 45% | Green | [In Prog]
DSFFLOW-993 | In Progress | Maiden Installation | Core Network | UDM | 40 | 40 | 10 | 2025-02-10 | 2025-02-10 | 2025-02-10 | 2025-12-31 | 2025-12-31 |  | 324 | 324 | 1955 | 1955 | 1045 | 1676 | 15% | 25% | 69% | 53% | Amber | [In Prog] efforts burnt misaligned with work progress;
DSFFLOW-1057 | In Progress | Upgrade, Maiden Installation | Core Network | EPC | 86 | 86 | 9 | 2025-05-07 | 2025-05-16 | 2025-05-16 | 2026-01-30 | 2026-01-30 |  | 268 | 259 | 3893.75 | 3893.75 | 802.5 | 3876.75 | 0% | 10% | 50% | 21% | Green | [In Prog]
DSFFLOW-4850 | In Progress | Migration | Core Network | Core Network Automation, EPC, IMS, MSS, Signaling, UDM | 301 | 301 | 10 | 2025-08-11 | 2025-08-11 | 2025-09-01 | 2025-10-25 | 2025-10-25 |  | 75 | 75 | 8332.6 | 8332.6 | 604 | 8332.6 | 0% | 3% | 57% | 8% | Green | [In Prog] work progress misaligned with time progress; late start;
DSFFLOW-5367 | In Progress | Maiden Installation | Core Network | Cloud | 79 | 79 | 8 | 2025-08-08 | 2025-08-08 | 2025-08-26 | 2028-12-31 | 2028-12-31 |  | 1241 | 1241 | 2541 | 2541 | 601 | 2493 | 2% | 10% | 4% | 24% | Green | [In Prog] late start;
DSFFLOW-4361 | In Progress | Upgrade | Core Network | Cloud, EPC | 141 | 141 | 15 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-12-19 | 2025-12-19 |  | 183 | 183 | 3597 | 3597 | 571 | 3597 | 0% | 11% | 52% | 16% | Green | [In Prog]
DSFFLOW-4540 | In Progress | Upgrade | Core Network | Cloud | 34 | 34 | 0 | 2025-07-28 | 2025-07-14 | 2025-07-14 | 2025-12-31 | 2026-02-21 |  | 156 | 222 | 1364 | 1364 | 570 | 1108 | 19% | 0% | 32% | 42% | Amber | [In Prog] time ticking without any work progress; efforts burnt misaligned with work progress;
DSFFLOW-845 | In Progress | Upgrade | Core Network | MSS | 22 | 22 | 7 | 2025-02-24 | 2025-09-15 | 2025-09-09 | 2025-06-30 | 2025-12-31 |  | 126 | 107 | 674 | 674 | 558 | 673 | 0% | 32% | 8% | 83% | Red | [In Prog] efforts burnt outweighing work output; efforts burnt misaligned with time progress;
DSFFLOW-5636 | In Progress | Maiden Installation, Migration, Business Configuration | BOS | Common Services-Data Migration, Core Commerce, Monetization Charging | 107 | 107 | 0 | 2025-07-24 | 2025-07-24 | 2025-09-08 | 2026-04-16 | 2026-04-16 |  | 266 | 266 | 15668.1 | 15668.1 | 555.29 | 15651.06 | 0% | 0% | 23% | 4% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-5597 | In Progress | Upgrade | Core Network | Cloud | 34 | 34 | 5 | 2025-08-10 | 2025-08-11 | 2025-08-11 | 2025-10-30 | 2025-10-30 |  | 81 | 80 | 1828 | 1906 | 540 | 1810 | 5% | 15% | 53% | 29% | Green | [In Prog]
DSFFLOW-1087 | In Progress | Upgrade | Network Management | Element Management | 60 | 58 | 34 | 2025-05-14 | 2025-05-14 | 2025-05-17 | 2025-11-29 | 2025-11-29 |  | 199 | 199 | 1160 | 1175 | 811.5 | 1050.5 | 11% | 59% | 66% | 69% | Green | [In Prog]
DSFFLOW-4564 | In Progress | Upgrade | Core Network | Cloud | 32 | 32 | 10 | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2026-01-15 | 2026-01-15 |  | 177 | 177 | 1211 | 1211 | 527 | 1183 | 2% | 31% | 35% | 44% | Green | [In Prog]
DSFFLOW-1646 | In Progress | Upgrade | Network Management | Element Management | 67 | 67 | 26 | 2025-05-27 | 2025-07-21 | 2025-06-09 | 2025-08-29 | 2025-10-17 |  | 94 | 88 | 1440 | 1440 | 520.01 | 1424.01 | 1% | 39% | 72% | 36% | Green | [In Prog] early start;
DSFFLOW-4588 | In Progress | Maiden Installation | Core Network | Core Network Automation, EPC, UDM | 83 | 83 | 0 | 2025-07-30 | 2025-07-30 | 2025-08-08 | 2026-06-30 | 2026-06-30 |  | 335 | 335 | 2284 | 2284 | 519.3997 | 2279 | 0% | 0% | 16% | 23% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-5858 | In Progress | Upgrade, Maiden Installation | Core Network | EPC | 62 | 62 | 2 | 2025-08-28 | 2025-09-01 | 2025-09-01 | 2026-06-30 | 2025-10-31 |  | 306 | 60 | 1370 | 1370 | 510 | 1328 | 3% | 3% | 36% | 37% | Amber | [In Prog] efforts burnt misaligned with work progress;
DSFFLOW-2234 | In Progress | Upgrade | Network Management | Element Management & Reporting | 38 | 38 | 38 | 2025-06-17 | 2025-06-17 | 2025-06-30 | 2025-10-31 | 2025-10-31 |  | 136 | 136 | 652 | 652 | 501 | 501 | 23% | 100% | 72% | 77% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-2107 | In Progress | Maiden Installation | Core Network | IMS, UDM | 90 | 90 | 0 | 2025-05-29 | 2025-05-29 | 2025-06-30 | 2026-02-27 | 2026-02-27 |  | 274 | 274 | 4087.7 | 4087.7 | 606.5997 | 4044.2 | 1% | 0% | 43% | 15% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-798 | In Progress | Maiden Installation | Core Network | Cloud | 77 | 77 | 0 | 2025-05-05 | 2025-04-01 | 2025-06-03 | 2025-12-30 | 2026-03-20 |  | 239 | 353 | 6839 | 6839 | 487.75 | 7613.5 | -11% | 0% | 49% | 8% | Red | [In Prog] projecting 5%+ EAC effort overrun; time ticking without any work progress; late start;
DSFFLOW-2610 | In Progress | Upgrade | Core Network | Signaling | 11 | 11 | 8 | 2025-06-27 | 2025-06-27 | 2025-06-27 | 2025-12-31 | 2025-12-31 |  | 187 | 187 | 605 | 605 | 480 | 605 | 0% | 73% | 47% | 79% | Green | [In Prog]
DSFFLOW-4396 | In Progress | Upgrade | Core Network | MSS | 43 | 41 | 23 | 2025-08-04 | 2025-08-04 | 2025-08-05 | 2025-10-06 | 2025-10-06 |  | 63 | 63 | 734 | 734 | 476.9167 | 691.0833 | 6% | 57% | 78% | 65% | Green | [In Prog]
DSFFLOW-3870 | In Progress | Expansion | Core Network | Cloud | 62 | 62 | 29 | 2025-07-14 | 2025-07-14 | 2025-07-29 | 2025-12-24 | 2025-12-24 |  | 163 | 163 | 727.94 | 727.94 | 473.2697 | 712.9397 | 2% | 47% | 43% | 65% | Green | [In Prog] late start;
DSFFLOW-2575 | In Progress | Maiden Installation | Core Network | Cloud | 32 | 32 | 7 | 2025-06-23 | 2025-06-23 | 2025-07-14 | 2025-12-01 | 2025-12-01 |  | 161 | 161 | 1262 | 1262 | 472 | 1221 | 3% | 22% | 57% | 37% | Green | [In Prog] late start;
DSFFLOW-2264 | In Progress | Upgrade, Maiden Installation | BOS | Monetization Charging | 571 | 571 | 11 | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2026-02-16 | 2026-02-16 |  | 245 | 245 | 5197.5 | 5197.5 | 462 | 4958.5 | 5% | 2% | 40% | 9% | Green | [In Prog]
DSFFLOW-3562 | In Progress | Upgrade | Core Network | Cloud | 23 | 23 | 12 | 2025-07-23 | 2025-07-23 | 2025-07-23 | 2025-09-30 | 2025-09-30 |  | 69 | 69 | 844 | 844 | 460 | 804 | 5% | 52% | 89% | 57% | Green | [In Prog]
DSFFLOW-4744 | In Progress | Maiden Installation | Core Network | EPC, UDM | 25 | 17 | 7 | 2025-02-11 | 2025-02-11 | 2025-08-14 | 2025-12-31 | 2025-12-31 |  | 323 | 323 | 1001 | 1001 | 456 | 1001 | 0% | 41% | 69% | 46% | Green | [In Prog] late start;
DSFFLOW-1008 | In Progress | Upgrade | Network Management | Resource Orchestration | 26 | 25 | 22 | 2025-06-16 | 2025-06-03 | 2025-06-18 | 2025-09-30 | 2025-09-30 |  | 106 | 119 | 507.1 | 507.1 | 451 | 484.1 | 5% | 88% | 93% | 89% | Green | [In Prog] late start;
DSFFLOW-3513 | In Progress | Maiden Installation | Network Management | Activation | 69 | 69 | 3 | 2025-07-11 | 2025-07-11 | 2025-07-24 | 2025-12-26 | 2025-12-26 |  | 168 | 168 | 3075.0867 | 3075.0867 | 445 | 3032.5867 | 1% | 4% | 44% | 15% | Green | [In Prog] late start;
DSFFLOW-3786 | In Progress | Maiden Installation | Core Network | EPC, UDM | 29 | 29 | 0 | 2025-03-31 | 2025-03-31 | 2025-07-29 | 2026-03-31 | 2026-03-31 |  | 365 | 365 | 10283 | 10283 | 440 | 10283 | 0% | 0% | 48% | 4% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-2593 | In Progress | Maiden Installation | Core Network | EPC | 16 | 16 | 2 | 2025-05-25 | 2025-05-25 | 2025-07-02 | 2025-12-31 | 2025-12-31 |  | 220 | 220 | 2581 | 2581 | 439 | 2551 | 1% | 13% | 57% | 17% | Green | [In Prog] late start;
DSFFLOW-2813 | In Progress | Maiden Installation | Network Management | Resource Orchestration | 11 | 11 | 5 | 2025-05-04 | 2025-05-04 | 2025-07-10 | 2026-03-31 | 2026-03-31 |  | 331 | 331 | 1125 | 1125 | 434.75 | 1125 | 0% | 45% | 43% | 39% | Green | [In Prog] late start;
DSFFLOW-5335 | In Progress | Migration | Core Network | UDM | 14 | 14 | 2 | 2025-08-19 | 2025-08-19 | 2025-08-26 | 2025-12-30 | 2025-12-30 |  | 133 | 133 | 811 | 811 | 432.5 | 811 | 0% | 15% | 26% | 53% | Amber | [In Prog] efforts burnt misaligned with work progress;
DSFFLOW-3093 | In Progress | Expansion | Core Network | Cloud | 89 | 89 | 17 | 2025-06-04 | 2025-06-04 | 2025-07-15 | 2026-03-31 | 2026-03-31 |  | 300 | 300 | 2335.5 | 2335.5 | 481 | 2293.5 | 2% | 19% | 37% | 21% | Green | [In Prog] late start;
DSFFLOW-3852 | In Progress | Migration | Core Network | Cloud | 118 | 118 | 22 | 2025-07-22 | 2025-07-22 | 2025-07-31 | 2025-12-31 | 2025-12-31 |  | 162 | 162 | 2002.5 | 2002.5 | 618 | 1936.5 | 3% | 19% | 39% | 31% | Green | [In Prog] late start;
DSFFLOW-3233 | In Progress | Migration | Core Network | UDM | 16 | 15 | 1 | 2025-07-14 | 2025-07-14 | 2025-08-12 | 2025-08-15 | 2025-08-15 |  | 32 | 32 | 614 | 614 | 529 | 614 | 0% | 8% | 215% | 86% | Red | [In Prog] efforts burnt outweighing work output; efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-2641 | In Progress | Upgrade | Network Management | Element Management | 24 | 24 | 18 | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-09-29 | 2025-09-29 |  | 90 | 90 | 850 | 850 | 705.95 | 830.45 | 2% | 75% | 92% | 83% | Green | [In Prog]
DSFFLOW-4260 | In Progress | Upgrade | Core Network | Cloud | 86 | 86 | 20 | 2025-07-06 | 2025-07-06 | 2025-07-06 | 2025-11-29 | 2025-11-29 |  | 146 | 146 | 2248 | 2248 | 732 | 1920 | 15% | 23% | 54% | 33% | Green | [In Prog]
DSFFLOW-1041 | In Progress | Maiden Installation | Core Network | IMS | 17 | 13 | 13 | 2025-05-14 | 2025-05-14 | 2025-05-16 | 2027-04-30 | 2027-04-30 | 2025-06-27 | 716 | 716 | 728 | 728 | 728 | 604 | 17% | 100% | 6% | 100% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress;
DSFFLOW-1337 | In Progress | Upgrade, Expansion | BOS | Monetization Charging | 338 | 338 | 18 | 2025-04-14 | 2025-04-14 | 2025-05-30 | 2026-10-30 | 2026-10-30 |  | 564 | 564 | 5063 | 5063 | 786.25 | 4796.75 | 5% | 5% | 29% | 16% | Green | [In Prog] late start;
DSFFLOW-5303 | In Progress | Maiden Installation | Core Network | Cloud | 68 | 68 | 7 | 2025-08-12 | 2025-08-12 | 2025-08-26 | 2028-12-31 | 2028-12-31 |  | 1237 | 1237 | 2709.5 | 2709.5 | 728 | 2619.5 | 3% | 10% | 3% | 27% | Green | [In Prog] late start;
DSFFLOW-2497 | In Progress | Migration | Core Network, Network Management | Activation, EPC, Resource Orchestration | 96 | 98 | 18 | 2025-05-29 | 2025-06-30 | 2025-06-27 | 2026-02-27 | 2025-08-30 |  | 274 | 61 | 2110 | 2488 | 788 | 2486 | 0% | 18% | 137% | 32% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress;
DSFFLOW-611 | In Progress | Maiden Installation | Core Network | EPC | 58 | 58 | 0 | 2025-02-10 | 2025-02-10 | 2025-07-21 | 2025-12-31 | 2025-12-31 |  | 324 | 324 | 2055 | 2055 | 727 | 1899 | 8% | 0% | 69% | 35% | Amber | [In Prog] time ticking without any work progress; efforts burnt misaligned with work progress; late start;
DSFFLOW-5480 | In Progress | Upgrade | Core Network | Cloud | 140 | 140 | 1 | 2025-08-25 | 2025-08-25 | 2025-08-25 | 2026-08-31 | 2026-08-31 |  | 371 | 371 | 8499.5 | 8760.5 | 722.5 | 8760.5 | 0% | 1% | 8% | 8% | Green | [In Prog]
DSFFLOW-4213 | In Progress | Upgrade | Core Network | IMS | 80 | 80 | 40 | 2025-07-25 | 2025-07-30 | 2025-07-30 | 2025-10-31 | 2025-10-31 |  | 98 | 93 | 1036 | 1036 | 702.6475 | 1022.7708 | 1% | 50% | 59% | 68% | Green | [In Prog]
DSFFLOW-1599 | In Progress | Upgrade | Network Management | Element Management | 63 | 62 | 51 | 2025-05-15 | 2025-05-15 | 2025-06-24 | 2025-08-29 | 2025-09-30 |  | 106 | 138 | 1102 | 1094 | 697.5 | 771.5 | 29% | 82% | 94% | 64% | Green | [In Prog] late start;
DSFFLOW-4636 | In Progress | Maiden Installation | Core Network | Core Network Automation, EPC | 51 | 51 | 0 | 2025-06-30 | 2025-06-30 | 2025-08-22 | 2026-06-29 | 2026-06-29 |  | 364 | 364 | 1716 | 1716 | 795 | 1660 | 3% | 0% | 23% | 46% | Amber | [In Prog] time ticking without any work progress; efforts burnt misaligned with work progress; late start;
DSFFLOW-1263 | In Progress | Maiden Installation | Core Network | EPC | 36 | 36 | 11 | 2025-05-11 | 2025-05-11 | 2025-07-11 | 2025-08-01 | 2025-08-01 |  | 82 | 82 | 871 | 871 | 687.75 | 809 | 8% | 31% | 163% | 79% | Amber | [In Prog] efforts burnt misaligned with work progress; efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-1368 | In Progress | Migration | Core Network | EPC | 21 | 21 | 1 | 2025-05-23 | 2025-05-23 | 2025-06-25 | 2025-12-31 | 2025-12-31 |  | 222 | 222 | 1214.8 | 1214.8 | 672.03 | 1214.8 | 0% | 5% | 57% | 57% | Red | [In Prog] efforts burnt outweighing work output; work progress misaligned with time progress; late start;
DSFFLOW-1151 | In Progress | Upgrade | BOS | Monetization Charging | 498 | 498 | 78 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2026-02-28 | 2026-02-28 |  | 272 | 272 | 3023 | 3023 | 783.05 | 2908 | 4% | 16% | 42% | 26% | Green | [In Prog]
DSFFLOW-3142 | In Progress | Maiden Installation | Core Network | Cloud | 100 | 100 | 7 | 2025-07-06 | 2025-07-06 | 2025-07-15 | 2025-09-14 | 2025-09-14 |  | 70 | 70 | 1766.6 | 1766.6 | 670 | 1688.6 | 4% | 8% | 113% | 38% | Amber | [In Prog] efforts burnt misaligned with work progress; efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-3730 | In Progress | Migration | Core Network | UDM | 16 | 15 | 0 | 2025-07-28 | 2025-07-28 | 2025-08-12 | 2025-10-31 | 2025-10-31 |  | 95 | 95 | 1283 | 1283 | 634.5 | 1283 | 0% | 0% | 59% | 49% | Amber | [In Prog] time ticking without any work progress; efforts burnt misaligned with work progress; late start;
DSFFLOW-894 | In Progress | Upgrade | Core Network | UDM | 23 | 23 | 6 | 2025-05-06 | 2025-05-06 | 2025-05-06 | 2025-12-31 | 2025-12-31 |  | 239 | 239 | 940 | 940 | 643 | 940 | 0% | 26% | 58% | 68% | Amber | [In Prog] efforts burnt misaligned with work progress;
DSFFLOW-1729 | In Progress | Upgrade | Network Management | Element Management | 67 | 64 | 26 | 2025-05-07 | 2025-05-07 | 2025-06-09 | 2025-10-31 | 2025-10-31 |  | 177 | 177 | 1240 | 1200 | 651 | 1187 | 1% | 41% | 78% | 54% | Green | [In Prog] late start;
DSFFLOW-2467 | In Progress | Upgrade | BOS | D&A Mediation | 25 | 25 | 6 | 2025-06-11 | 2025-06-11 | 2025-06-26 | 2025-11-30 | 2025-11-30 |  | 172 | 172 | 1232.5 | 1232.5 | 669.31 | 1082.84 | 12% | 24% | 60% | 54% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-2708 | On Hold | Upgrade | Core Network | Cloud, Signaling | 14 | 14 | 3 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2025-10-31 | 2025-10-31 |  | 152 | 152 | 315 | 315 | 121 | 308 | 2% | 21% | 75% | 38% | Green | [On Hold] work progress misaligned with time progress;
DSFFLOW-5319 | On Hold | Upgrade | Core Network | Cloud | 16 | 16 | 15 | 2025-08-25 | 2025-08-25 | 2025-08-26 | 2025-09-11 | 2025-09-11 |  | 17 | 17 | 102.5 | 102.5 | 94.0167 | 102.5167 | 0% | 94% | 161% | 92% | Amber | [On Hold] efforts burnt misaligned with time progress; work progress misaligned with time progress;
DSFFLOW-1247 | On Hold | Upgrade | Core Network | EPC, IMS, UDM | 168 | 168 | 0 | 2025-05-06 | 2025-05-23 | 2025-05-23 | 2025-12-31 | 2025-12-31 |  | 239 | 222 | 2729 | 2729 | 581.5 | 2643.25 | 3% | 0% | 57% | 21% | Amber | [On Hold] time ticking without any work progress; efforts burnt misaligned with work progress;
DSFFLOW-5960 | On Hold | Maiden Installation | BOS | D&A Mediation | 27 | 27 | 3 | 2025-08-13 | 2025-08-13 | 2025-09-09 | 2026-03-31 | 2026-03-31 |  | 230 | 230 | 473.3 | 473.3 | 91.2 | 441.5 | 8% | 11% | 18% | 19% | Green | [On Hold] late start;
DSFFLOW-3715 | On Hold | Upgrade | Core Network | MSS | 15 | 15 | 3 | 2025-06-10 | 2025-07-25 | 2025-07-25 | 2025-08-30 | 2025-10-31 |  | 81 | 98 | 187 | 187 | 127.5 | 187 | 0% | 20% | 61% | 68% | Amber | [On Hold] efforts burnt misaligned with work progress;
DSFFLOW-2368 | On Hold | Upgrade | Network Management | Activation, Resource Orchestration | 34 | 34 | 15 | 2025-06-01 | 2025-06-01 | 2025-06-20 | 2033-08-31 | 2033-08-31 |  | 3013 | 3013 | 766.71 | 766.71 | 437.7 | 738.71 | 4% | 44% | 4% | 57% | Amber | [On Hold] efforts burnt misaligned with time progress; late start;
DSFFLOW-2931 | On Hold | Maiden Installation | Network Management | Activation | 46 | 46 | 4 | 2025-06-08 | 2025-06-08 | 2025-06-09 | 2025-12-30 | 2025-12-30 |  | 205 | 205 | 1061.25 | 1061.25 | 267.72 | 1027.07 | 3% | 9% | 52% | 25% | Green | [On Hold]
DSFFLOW-2452 | On Hold | Maiden Installation | Network Management | Resource Orchestration | 44 | 44 | 2 | 2025-05-29 | 2025-05-29 | 2025-07-11 | 2026-02-27 | 2026-02-27 |  | 274 | 274 | 1157 | 1157 | 111.58 | 1157 | 0% | 5% | 43% | 10% | Green | [On Hold] late start;
DSFFLOW-3443 | On Hold | Upgrade | Network Management | Element Management & Reporting | 21 | 15 | 9 | 2025-07-14 | 2025-07-14 | 2025-07-14 | 2025-09-19 | 2025-09-19 | 2025-08-01 | 67 | 67 | 158.5 | 158.5 | 149 | 229 | -44% | 60% | 29% | 94% | Red | [On Hold] projecting 5%+ EAC effort overrun; efforts burnt misaligned with work progress; efforts burnt misaligned with time progress;
DSFFLOW-4055 | On Hold | Upgrade | Network Management | Element Management & Reporting | 26 | 19 | 12 | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-09-30 | 2025-09-30 |  | 57 | 57 | 328 | 328 | 134.02 | 286.02 | 13% | 63% | 86% | 41% | Amber | [On Hold] efforts burnt misaligned with work progress;
DSFFLOW-133 | On Hold | Upgrade | BOS | Core Commerce | 423 | 423 | 165 | 2025-03-17 | 2025-03-17 | 2025-04-09 | 2025-06-30 | 2025-09-29 |  | 105 | 196 | 3067 | 3067 | 1563.0008 | 3136.9992 | -2% | 39% | 96% | 51% | Amber | [On Hold] projecting 1%+ EAC effort overrun ; work progress misaligned with time progress; late start;
DSFFLOW-2828 | On Hold | Migration | Core Network | UDM | 15 | 15 | 1 | 2025-07-14 | 2025-07-14 |  | 2025-11-28 | 2025-11-28 |  | 137 | 137 | 593 | 593 | 383.5 | 542 | 9% | 8% | 51% | 65% | Red | [On Hold] efforts burnt outweighing work output;
DSFFLOW-2901 | On Hold | Maiden Installation | Network Management | Resource Orchestration | 34 | 33 | 13 | 2025-06-01 | 2025-06-01 | 2025-07-08 | 2025-08-30 | 2025-08-30 |  | 90 | 90 | 777.75 | 777.75 | 248.75 | 742.75 | 5% | 39% | 125% | 32% | Amber | [On Hold] efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-3812 | On Hold | Upgrade | Core Network | Cloud | 36 | 36 | 4 | 2025-05-05 | 2025-07-28 | 2025-07-28 | 2025-12-30 | 2025-12-30 |  | 239 | 155 | 785 | 879 | 305 | 854 | 3% | 11% | 37% | 35% | Amber | [On Hold] efforts burnt misaligned with work progress;
DSFFLOW-3327 | Block | Upgrade | Network Management | Resource Orchestration | 26 | 26 | 14 | 2025-07-15 | 2025-07-15 | 2025-07-21 | 2025-10-31 | 2025-10-31 |  | 108 | 108 | 334 | 334 | 166.05 | 319.5 | 4% | 54% | 64% | 50% | Green | [Block]
DSFFLOW-2916 | Assigned | Maiden Installation | Core Network | MSS | 12 | 12 | 0 | 2025-05-15 | 2025-05-15 |  | 2026-12-21 | 2026-12-21 |  | 585 | 585 | 204 | 204 |  | 204 | 0% | 0% | 22% | 0% | Amber | [Assigned] with 130 days past due start date;
DSFFLOW-6627 | Assigned | Upgrade | Network Management | Element Management | 76 | 76 | 0 | 2025-09-04 | 2025-09-04 |  | 2025-12-31 | 2025-12-31 |  | 118 | 118 | 897.5 | 897.5 |  | 897.5 | 0% | 0% | 16% | 0% | Amber | [Assigned] with 18 days past due start date;
DSFFLOW-6003 | Assigned | Upgrade, Continuous Adaptation | BOS | Monetization Billing | 60 | 60 | 0 | 2025-07-31 | 2025-07-31 |  | 2026-03-29 | 2026-03-29 |  | 241 | 241 | 15277.75 | 15277.75 |  | 15277.75 | 0% | 0% | 22% | 0% | Amber | [Assigned] with 53 days past due start date;
DSFFLOW-5009 | Assigned | Maiden Installation | Core Network | UDM | 14 | 14 | 0 | 2025-08-18 | 2025-08-18 |  | 2028-12-31 | 2028-12-31 |  | 1231 | 1231 | 220 | 220 |  | 220 | 0% | 0% | 3% | 0% | Amber | [Assigned] with 35 days past due start date;
DSFFLOW-5559 | Assigned | Upgrade | Core Network | UDM | 13 | 13 | 0 | 2025-08-14 | 2025-08-14 |  | 2028-10-05 | 2028-10-05 |  | 1148 | 1148 | 220 | 220 |  | 220 | 0% | 0% | 3% | 0% | Amber | [Assigned] with 39 days past due start date;
DSFFLOW-6736 | Assigned | Maiden Installation, Migration, Continuous Testing | BOS, ISD | Common Services-Data Migration, Core Commerce, BSS Application Testing | 37 | 37 | 0 | 2025-08-14 | 2025-08-14 |  | 2026-10-30 | 2026-10-30 |  | 442 | 442 | 30409 | 30409 |  | 30409 | 0% | 0% | 9% | 0% | Amber | [Assigned] with 39 days past due start date;
DSFFLOW-6461 | Assigned | Upgrade | Core Network | MSS | 39 | 39 | 0 | 2025-09-01 | 2025-09-01 |  | 2025-12-31 | 2025-12-31 |  | 121 | 121 | 877 | 877 |  | 877 | 0% | 0% | 18% | 0% | Amber | [Assigned] with 21 days past due start date;
DSFFLOW-6331 | Assigned | Upgrade | Core Network | MSS | 57 | 57 | 0 | 2025-07-09 | 2025-07-09 |  | 2025-12-31 | 2025-12-31 |  | 175 | 175 | 2185 | 2185 |  | 2185 | 0% | 0% | 43% | 0% | Amber | [Assigned] with 75 days past due start date;
DSFFLOW-4013 | Assigned | Maiden Installation | Core Network | MSS | 38 | 38 | 0 | 2025-07-25 | 2025-07-25 |  | 2026-04-15 | 2026-04-15 |  | 264 | 264 | 2613 | 2613 |  | 2613 | 0% | 0% | 23% | 0% | Amber | [Assigned] with 59 days past due start date;
DSFFLOW-1809 | Assigned | Upgrade, Maiden Installation | Core Network | MSS, Signaling | 46 | 46 | 0 | 2025-03-03 | 2025-09-15 |  | 2025-12-15 | 2025-12-31 |  | 287 | 107 | 1202 | 1202 |  | 1202 | 0% | 0% | 8% | 0% | Amber | [Assigned] with 7 days past due start date;
DSFFLOW-6779 | Assigned | Expansion | Core Network | Cloud-3PP/MPBN | 49 | 49 | 0 | 2025-08-31 | 2025-08-31 |  | 2025-12-15 | 2025-12-15 |  | 106 | 106 | 973.87 | 973.87 |  | 973.87 | 0% | 0% | 21% | 0% | Amber | [Assigned] with 22 days past due start date;
DSFFLOW-5350 | Assigned | Upgrade | BOS | D&A Mediation | 67 | 67 | 0 | 2025-07-21 | 2025-07-21 |  | 2026-05-31 | 2026-05-31 |  | 314 | 314 | 2487.1 | 2487.1 |  | 2487.1 | 0% | 0% | 20% | 0% | Amber | [Assigned] with 63 days past due start date;
DSFFLOW-4729 | Assigned | Upgrade | Core Network | Cloud-3PP/MPBN | 16 | 16 | 0 | 2025-08-01 | 2025-08-01 |  | 2025-10-31 | 2025-10-31 |  | 91 | 91 | 320 | 320 |  | 320 | 0% | 0% | 58% | 0% | Amber | [Assigned] with 52 days past due start date;
DSFFLOW-6645 | Assigned | Expansion | Core Network | Cloud-3PP/MPBN | 29 | 29 | 0 | 2025-08-31 | 2025-08-31 |  | 2025-12-12 | 2025-12-12 |  | 103 | 103 | 728 | 728 |  | 728 | 0% | 0% | 22% | 0% | Amber | [Assigned] with 22 days past due start date;
DSFFLOW-3998 | Assigned | Upgrade | Core Network | MSS | 13 | 13 | 0 | 2025-07-25 | 2025-10-30 |  | 2026-04-15 | 2025-12-31 |  | 264 | 62 | 220 | 220 |  | 220 | 0% | 0% | -59% | 0% | Green | [Assigned] with 38 days left to start;
DSFFLOW-6573 | Assigned | Upgrade | Core Network | IMS | 45 | 45 | 0 | 2025-08-25 | 2025-08-25 |  | 2025-10-30 | 2025-10-30 |  | 66 | 66 | 309 | 309 |  | 309 | 0% | 0% | 43% | 0% | Amber | [Assigned] with 28 days past due start date;
DSFFLOW-3294 | Assigned | Upgrade | Core Network | IMS | 65 | 65 | 0 | 2025-07-08 | 2025-06-26 |  | 2025-09-22 | 2025-08-15 |  | 76 | 50 | 312 | 312 |  | 312 | 0% | 0% | 175% | 0% | Amber | [Assigned] with 88 days past due start date;
DSFFLOW-325 | Assigned | Upgrade | Core Network | MSS | 34 | 34 | 0 | 2025-04-22 | 2025-09-15 |  | 2026-12-31 | 2025-12-31 |  | 618 | 107 | 512 | 512 |  | 512 | 0% | 0% | 8% | 0% | Amber | [Assigned] with 7 days past due start date;
DSFFLOW-6794 | Assigned | Upgrade | Core Network | Cloud, EPC, UDM | 94 | 94 | 0 | 2025-09-14 | 2025-09-14 |  | 2027-02-25 | 2027-02-25 |  | 529 | 529 | 4728.4 | 4728.4 |  | 4728.4 | 0% | 0% | 2% | 0% | Amber | [Assigned] with 8 days past due start date;
DSFFLOW-626 | Backlog | Maiden Installation | Core Network | EPC | 34 | 34 | 0 | 2025-04-29 | 2025-04-29 | 2025-04-29 | 2025-08-31 | 2025-08-31 |  | 124 | 124 | 2496 | 2496 | 904 | 2392 | 4% | 0% | 118% | 36% | Red | [Backlog] with wrong project state with efforts burning; 146 days past due start date;
DSFFLOW-356 | Backlog | Expansion | Core Network | UDM | 13 | 13 | 0 | 2024-12-18 | 2024-12-18 |  | 2026-07-31 | 2026-07-31 |  | 590 | 590 | 222 | 222 |  | 222 | 0% | 0% | 47% | 0% | Amber | [Backlog] with 278 days past due start date;
DSFFLOW-371 | Backlog | Upgrade | Core Network | MSS | 28 | 28 | 0 | 2025-03-24 | 2025-09-15 |  | 2025-07-25 | 2025-12-31 |  | 123 | 107 | 700 | 700 |  | 700 | 0% | 0% | 8% | 0% | Amber | [Backlog] with 7 days past due start date;
DSFFLOW-1223 | Backlog | Expansion | Core Network | EPC, Signaling, UDM | 166 | 166 | 1 | 2025-05-09 | 2025-05-09 |  | 2025-12-31 | 2025-12-31 |  | 236 | 236 | 33976 | 33976 | 1129 | 33976 | 0% | 1% | 58% | 3% | Red | [Backlog] with wrong project state with work happening; efforts burning; 136 days past due start date;
DSFFLOW-879 | Rejected | Upgrade | Network Management | Element Management & Reporting | 12 | 12 | 0 | 2025-05-09 | 2025-05-09 |  | 2025-06-29 | 2025-06-29 |  | 51 | 51 | 0 | 0 |  | 0 | 0% | 0% | 263% | 0%

## Sheet1
DSF Project | Status | Domain | Sub-Domain | Flow | Plan Work | Replan Work | Closed Work | Planned FNI Nodes | FNIs Completed | Planned SNI Nodes | SNIs Completed | Plan Start | Replan Start | Actual Start | Plan End | Replan End | Actual End | Plan Days | Sum of Replan Days | Plan Hrs | Replan Hrs | Logged Hrs | EAC Hrs | Efficiency At EAC | Work Progress | Time Progress | Effort Progress | RAG | RAG Reason
DSFFLOW-1840 | In Progress | Network Management | Element Management | Upgrade | 1221 | 1221 | 888 | 2 | 100% | 75 | 61% | Jun 08 2025 | Jun 08 2025 | Jun 23 2025 | Nov 06 2025 | Nov 29 2025 |  | 151 | 174 | 17146.71 | 17146.71 | 12375.8642 | 16834.0108 | 2% | 73% | 61% | 72% | Green | [In Prog] late start;
DSFFLOW-245 | In Progress | Network Management | Element Management | Upgrade, Maiden Installation | 853 | 545 | 107 | 1 | 0% | 28 | 4% | May 15 2025 | Apr 07 2025 |  | Oct 01 2025 | Dec 31 2025 |  | 139 | 268 | 24189 | 16930 | 12088.5 | 15530.5 | 8% | 20% | 63% | 71% | Red | [In Prog] efforts burnt outweighing work output;
DSFFLOW-760 | In Progress | BOS | D&A Mediation, Monetization Charging | Upgrade | 2546 | 2546 | 796 | 9 | 56% | 597 | 20% | May 05 2025 | May 05 2025 | May 12 2025 | Apr 20 2026 | Apr 20 2026 |  | 350 | 350 | 33240.9 | 33240.9 | 11333.7017 | 32190.8117 | 3% | 31% | 40% | 34% | Green | [In Prog] late start;
DSFFLOW-447 | In Progress | BOS | Monetization Billing | Upgrade | 37 | 37 | 19 | 1 | 0% |  |  | Apr 01 2025 | Apr 01 2025 | May 20 2025 | Dec 05 2025 | Dec 05 2025 |  | 248 | 248 | 10676.2 | 10676.2 | 7670.6097 | 9687.71 | 9% | 51% | 70% | 72% | Green | [In Prog] late start;
DSFFLOW-5109 | In Progress | Core Network, Network Management | Cloud, Core Network Automation, EPC, IMS, MSS, Resource Orchestration, UDM | Maiden Installation, Migration | 248 | 248 | 203 | 20 | 20% | 3 | 0% | Jun 01 2025 | Jun 01 2025 | Aug 22 2025 | Sep 29 2025 | Sep 29 2025 |  | 120 | 120 | 8622.5 | 8622.5 | 7252.16 | 8162.5 | 5% | 82% | 94% | 84% | Green | [In Prog] late start;
DSFFLOW-507 | In Progress | Network Management | Element Management & Reporting | Upgrade | 527 | 1464 | 468 | 1 | 0% | 71 | 44% | Feb 28 2025 | Mar 01 2025 | Jun 26 2025 | Jul 30 2025 | Sep 29 2025 |  | 152 | 212 | 6628 | 18453 | 5450.6833 | 16611.6833 | 10% | 32% | 97% | 30% | Amber | [In Prog] efforts burnt misaligned with time progress; late start;
DSFFLOW-576 | In Progress | BOS | Monetization Billing | Upgrade | 34 | 34 | 22 | 1 | 0% |  |  | Mar 03 2025 | Mar 03 2025 | May 13 2025 | Aug 14 2025 | Oct 10 2025 |  | 164 | 221 | 7946.6 | 7946.6 | 5055.2 | 7691.4 | 3% | 65% | 92% | 64% | Green | [In Prog] late start;
DSFFLOW-741 | In Progress | Network Management | Element Management | Upgrade | 159 | 159 | 146 | 5 | 60% |  |  | Apr 22 2025 | Apr 22 2025 | May 19 2025 | Sep 19 2025 | Oct 10 2025 |  | 150 | 171 | 5800 | 5800 | 4740.8333 | 6025.8333 | -4% | 92% | 90% | 82% | Amber | [In Prog] projecting 1%+ EAC effort overrun ; late start;
DSFFLOW-1278 | In Progress | Core Network | IMS | Migration | 353 | 340 | 289 | 9 | 0% | 17 | 0% | May 08 2025 | May 08 2025 | May 22 2025 | Sep 15 2025 | Sep 19 2025 |  | 130 | 134 | 4478.5 | 4478.5 | 4006.0758 | 4337.0758 | 3% | 85% | 102% | 89% | Green | [In Prog] late start;
DSFFLOW-2529 | Closed | Core Network | Cloud, EPC, IMS, MSS, UDM | Maiden Installation | 15 | 15 | 15 | 5 | 100% |  |  | Jun 24 2025 | Jun 24 2025 | Jun 26 2025 | Aug 29 2025 | Aug 29 2025 | Sep 04 2025 | 66 | 66 | 3284 | 3284 | 3284 | 3284 | 0% | 100% | 109% | 100% | Red | [Closed] schedule overrun > 10%;
DSFFLOW-5184 | In Progress | Core Network, Network Management | Activation, Core Network Automation, EPC, Exposure, Signaling, UDM | Upgrade | 127 | 127 | 66 | 10 | 10% | 10 | 20% | Jun 15 2025 | Aug 25 2025 | Aug 25 2025 | Oct 31 2025 | Oct 31 2025 |  | 138 | 67 | 5333 | 5333 | 3233 | 5116 | 4% | 52% | 43% | 61% | Green | [In Prog]
DSFFLOW-1416 | In Progress | Core Network, Network Management | Activation, EPC, IMS, MSS, UDM | Migration | 139 | 155 | 23 | 11 | 0% |  |  | Apr 23 2025 | Apr 23 2025 | May 27 2025 | Dec 31 2025 | Dec 31 2025 |  | 252 | 252 | 8449.25 | 8449.25 | 3050.255 | 8234.75 | 3% | 15% | 60% | 36% | Green | [In Prog] late start;
DSFFLOW-2078 | In Progress | Core Network | EPC, IMS | Upgrade, Maiden Installation | 46 | 55 | 50 | 3 | 67% | 3 | 33% | Jun 17 2025 | Jun 17 2025 | Jun 17 2025 | Sep 26 2025 | Sep 26 2025 |  | 101 | 101 | 1930 | 3252 | 2924 | 3228 | 1% | 91% | 96% | 90% | Amber | [In Prog] efforts burnt misaligned with work progress;
DSFFLOW-3475 | In Progress | Core Network | EPC, IMS, Signaling, UDM | Upgrade | 190 | 190 | 118 | 9 | 0% | 9 | 0% | Apr 30 2025 | May 05 2025 | May 05 2025 | Sep 29 2025 | Sep 29 2025 |  | 152 | 147 | 3427.5 | 3427.5 | 2866.25 | 3314.5 | 3% | 62% | 95% | 84% | Amber | [In Prog] efforts burnt misaligned with work progress;
DSFFLOW-2123 | In Progress | Core Network, Network Management | Activation, Core Network Automation, EPC, Exposure, UDM | Maiden Installation | 82 | 82 | 21 | 7 | 0% |  |  | May 07 2025 | May 07 2025 | Jun 20 2025 | Oct 30 2026 | Oct 30 2026 |  | 541 | 541 | 6272 | 6272 | 2819 | 6027 | 4% | 26% | 26% | 45% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-2009 | In Progress | Core Network | Cloud, EPC, IMS, UDM | Upgrade | 172 | 172 | 150 | 10 | 60% | 6 | 50% | Apr 29 2025 | Apr 29 2025 | Apr 29 2025 | Mar 31 2026 | Mar 31 2026 |  | 336 | 336 | 3164 | 3164 | 2696 | 2975 | 6% | 87% | 44% | 85% | Green | [In Prog]
DSFFLOW-2402 | In Progress | BOS | Monetization Charging | Upgrade | 169 | 169 | 24 |  |  |  |  | May 05 2025 | May 05 2025 | Jul 08 2025 | Jun 29 2026 | Jun 30 2026 |  | 420 | 421 | 18647.44 | 18647.44 | 2646.5 | 17668 | 5% | 14% | 33% | 14% | Green | [In Prog] late start;
DSFFLOW-206 | In Progress | Core Network | IMS | Upgrade | 214 | 188 | 93 | 7 | 0% | 14 | 0% | Feb 16 2025 | Apr 15 2025 | Apr 15 2025 | Dec 18 2025 | Oct 30 2025 |  | 305 | 198 | 3892 | 3892 | 2456.5 | 3362.75 | 14% | 49% | 81% | 63% | Green | [In Prog] late start;
DSFFLOW-1307 | In Progress | BOS | Monetization Charging | Expansion | 161 | 161 | 160 | 2 | 100% | 2 | 100% | May 11 2025 | May 11 2025 | May 11 2025 | Aug 21 2025 | Sep 30 2025 |  | 102 | 142 | 4315.75 | 4315.75 | 2405.2667 | 2746.0167 | 36% | 99% | 94% | 56% | Amber | [In Prog] efforts burnt misaligned with work progress;
DSFFLOW-2047 | In Progress | Network Management | Element Management | Upgrade | 368 | 402 | 50 | 10 | 0% | 8 | 0% | May 08 2025 | May 08 2025 | Jun 18 2025 | Aug 31 2026 | Aug 31 2026 |  | 480 | 480 | 9297 | 11569 | 2279 | 11475 | 1% | 12% | 29% | 20% | Green | [In Prog] late start;
DSFFLOW-477 | Closed | Core Network | EPC | Upgrade, Maiden Installation | 49 | 49 | 34 | 3 | 100% |  |  | Nov 08 2024 | Nov 08 2024 | Apr 29 2025 | Feb 28 2026 | Feb 28 2026 | Sep 18 2025 | 477 | 477 | 2564 | 2564 | 2254 | 2494 | 3% | 69% | 66% | 88% | Green | [In Prog] late start;
DSFFLOW-1629 | Closed | Core Network | EPC, Signaling, UDM | Upgrade | 175 | 175 | 175 | 21 | 100% |  |  | Apr 01 2025 | Apr 02 2025 | Apr 02 2025 | Jun 29 2025 | Jun 30 2025 | Jun 30 2025 | 89 | 89 | 2725.1292 | 2725.1292 | 2238.05 | 2238.05 | 18% | 100% | 100% | 82% | Red | [Closed] schedule overrun > 10%; efforts saved; feedback: opportunity for optimized effort baseline; late start;
DSFFLOW-1584 | In Progress | Core Network, Network Management | Activation, Core Network Automation, EPC, IMS, Resource Orchestration, UDM | Maiden Installation | 43 | 53 | 45 | 7 | 0% | 12 | 0% | May 12 2025 | May 12 2025 | May 12 2025 | Sep 15 2025 | Sep 15 2025 |  | 126 | 126 | 2549.99 | 2549.99 | 2148.99 | 2532.99 | 1% | 85% | 106% | 84% | Amber | [In Prog] efforts burnt misaligned with work progress;
DSFFLOW-115 | In Progress | Network Management | Element Management | Upgrade | 192 | 181 | 81 | 7 | 29% | 3 | 100% | Mar 16 2025 | Mar 17 2025 | Mar 27 2025 | Jun 29 2025 | Sep 30 2025 |  | 105 | 197 | 3902 | 3750 | 2100 | 2740 | 27% | 45% | 96% | 56% | Green | [In Prog] late start;
DSFFLOW-1911 | In Progress | Core Network | EPC | Migration | 41 | 53 | 27 | 4 | 0% | 4 | 0% | Apr 03 2025 | Apr 03 2025 | Jun 13 2025 | Nov 30 2025 | Nov 29 2025 |  | 241 | 240 | 3433 | 4421 | 2097 | 4388 | 1% | 51% | 72% | 47% | Green | [In Prog] late start;
DSFFLOW-401 | Closed | Core Network | EPC | Upgrade, Expansion, Migration | 152 | 150 | 150 | 10 | 100% | 5 | 100% | Jul 10 2024 | Jul 10 2024 | Apr 30 2025 | Dec 12 2025 | Dec 12 2025 | Jun 23 2025 | 520 | 520 | 2112 | 1932 | 1908.1 | 1908.1 | 1% | 100% | 67% | 99% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; late start;
DSFFLOW-1166 | Closed | Core Network | Cloud | Upgrade | 70 | 70 | 70 | 2 | 100% | 6 | 100% | May 19 2025 | May 19 2025 | Jun 06 2025 | Dec 30 2025 | Dec 30 2025 | Sep 02 2025 | 225 | 225 | 1875 | 1875 | 1874.5 | 1874.5 | 0% | 100% | 47% | 100% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; late start;
DSFFLOW-2384 | In Progress | Network Management | Resource Orchestration | Upgrade | 12 | 12 | 5 | 1 | 100% |  |  | Jun 16 2025 | Jun 01 2025 | Jun 24 2025 | Jun 30 2026 | Dec 31 2026 |  | 379 | 578 | 4016.35 | 4016.35 | 1772.25 | 2892.85 | 28% | 42% | 20% | 44% | Green | [In Prog] late start;
DSFFLOW-80 | Closed | Core Network | EPC, IMS, UDM | Upgrade | 176 | 150 | 150 | 10 | 100% |  |  | Feb 06 2025 | Feb 06 2025 | Mar 10 2025 | Jun 06 2025 | Jun 06 2025 | Jun 05 2025 | 120 | 120 | 1786 | 1786 | 1758 | 1758 | 2% | 100% | 99% | 98% | Green | [Closed] ahead of schedule; efforts saved; late start;
DSFFLOW-5732 | In Progress | Core Network | Cloud, UDM | Upgrade | 149 | 143 | 119 | 5 | 40% | 7 | 29% | Jul 27 2025 | Jul 28 2025 | Jul 28 2025 | Oct 30 2025 | Oct 30 2025 |  | 95 | 94 | 2596 | 2540 | 1754 | 2456 | 3% | 83% | 60% | 69% | Green | [In Prog] late start;
DSFFLOW-3109 | In Progress | Core Network | IMS | Upgrade | 153 | 169 | 102 | 8 | 0% | 8 | 0% | Jul 14 2025 | Jul 14 2025 | Jul 14 2025 | Aug 29 2025 | Sep 29 2025 |  | 46 | 77 | 2101 | 2411 | 1709.26 | 2192.01 | 9% | 60% | 91% | 71% | Green | [In Prog]
DSFFLOW-3760 | In Progress | Core Network | Signaling, UDM | Maiden Installation | 29 | 29 | 0 | 3 | 0% | 3 | 0% | Mar 31 2025 | Mar 31 2025 | Jul 29 2025 | Mar 31 2026 | Mar 31 2026 |  | 365 | 365 | 6752 | 6752 | 1680 | 6752 | 0% | 0% | 48% | 25% | Amber | [In Prog] time ticking without any work progress; efforts burnt misaligned with work progress; late start;
DSFFLOW-2513 | In Progress | Core Network | EPC, Signaling | Maiden Installation | 46 | 46 | 0 | 2 | 0% | 2 | 0% | Jul 25 2024 | Jul 25 2024 | Jul 24 2025 | Dec 31 2025 | Dec 31 2025 |  | 524 | 524 | 1896 | 1896 | 1584 | 1736 | 8% | 0% | 81% | 84% | Red | [In Prog] efforts burning without any work progress; time ticking without any work progress; late start;
DSFFLOW-133 | On Hold | BOS | Core Commerce | Upgrade | 423 | 423 | 165 | 4 | 50% | 17 | 12% | Mar 17 2025 | Mar 17 2025 | Apr 09 2025 | Jun 30 2025 | Sep 29 2025 |  | 105 | 196 | 3067 | 3067 | 1563.0008 | 3136.9992 | -2% | 39% | 96% | 51% | Amber | [On Hold] projecting 1%+ EAC effort overrun ; work progress misaligned with time progress; late start;
DSFFLOW-1119 | In Progress | Network Management | Element Management | Upgrade | 161 | 160 | 53 | 2 | 0% | 4 | 0% | May 15 2025 | May 21 2025 | Jun 02 2025 | Dec 31 2025 | Dec 31 2025 |  | 230 | 224 | 3306 | 3298 | 1469 | 2716.5 | 18% | 33% | 56% | 45% | Green | [In Prog] late start;
DSFFLOW-862 | In Progress | Core Network | MSS | Upgrade | 63 | 63 | 22 | 4 | 0% | 2 | 0% | May 05 2025 | May 19 2025 | May 19 2025 | Dec 31 2025 | Dec 31 2025 |  | 240 | 226 | 2474.75 | 2474.75 | 1468.1 | 2474.75 | 0% | 35% | 56% | 59% | Amber | [In Prog] efforts burnt misaligned with work progress;
DSFFLOW-1745 | Closed | Core Network, Network Management | EPC, Exposure, Resource Orchestration, UDM | Upgrade, Expansion | 101 | 101 | 101 | 8 | 100% |  |  | Jun 04 2025 | Jun 04 2025 | Jun 06 2025 | Aug 30 2025 | Aug 30 2025 | Jul 28 2025 | 87 | 87 | 1432 | 1432 | 1432 | 1432 | 0% | 100% | 63% | 100% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan;
DSFFLOW-1894 | Closed | Core Network | EPC | Upgrade | 25 | 23 | 23 | 5 | 100% |  |  | Dec 31 2024 | Dec 31 2024 | Jun 26 2025 | Dec 30 2025 | Dec 30 2025 | Aug 30 2025 | 364 | 364 | 1584 | 1424 | 1424 | 1424 | 0% | 100% | 67% | 100% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; late start;
DSFFLOW-4070 | In Progress | BOS | Core Commerce, D&A Mediation, Monetization Billing | Maiden Installation | 60 | 60 | 0 | 4 | 0% | 16 | 0% | Jun 06 2025 | Jun 06 2025 | Jul 31 2025 | Dec 31 2027 | Dec 31 2027 |  | 938 | 938 | 48905.4997 | 48905.4997 | 1410.25 | 48677.4997 | 0% | 0% | 12% | 3% | Green | [In Prog] late start; Delivery Manager not assigned
DSFFLOW-677 | In Progress | Core Network | IMS | Upgrade | 102 | 102 | 88 | 6 | 33% | 10 | 10% | Apr 24 2025 | Apr 14 2025 | Apr 14 2025 | Dec 31 2025 | Sep 30 2025 |  | 251 | 169 | 1792 | 1800 | 1402 | 1720 | 4% | 86% | 95% | 78% | Green | [In Prog] early start;
DSFFLOW-2750 | In Progress | Core Network | IMS | Maiden Installation, Migration | 189 | 189 | 12 | 12 | 0% | 30 | 0% | Jun 24 2025 | Jun 24 2025 | Jul 09 2025 | Dec 26 2025 | Dec 26 2025 |  | 185 | 185 | 5869 | 5869 | 1400.7 | 5469 | 7% | 6% | 49% | 24% | Green | [In Prog] late start;
DSFFLOW-3044 | In Progress | Core Network, Network Management | Activation, Signaling, UDM | Maiden Installation | 263 | 289 | 134 | 11 | 36% | 8 | 25% | Jul 09 2025 | Jul 09 2025 | Jul 15 2025 | Dec 31 2025 | Dec 31 2025 |  | 175 | 175 | 3496 | 4277 | 1380.1 | 3464.1 | 19% | 46% | 43% | 32% | Green | [In Prog]
DSFFLOW-151 | In Progress | Network Management | Element Management | Upgrade | 87 | 75 | 60 | 3 | 0% |  |  | Apr 13 2025 | Apr 13 2025 | Apr 13 2025 | Sep 26 2025 | Sep 26 2025 |  | 166 | 166 | 1719 | 1545 | 1379.5 | 1418.0167 | 8% | 80% | 98% | 89% | Green | [In Prog]
DSFFLOW-2882 | In Progress | BOS | D&A Mediation, Monetization Billing | Upgrade | 37 | 37 | 10 | 2 | 0% | 2 | 50% | May 10 2025 | May 10 2025 | Jul 10 2025 | Nov 18 2025 | Nov 18 2025 |  | 192 | 192 | 2844.2497 | 2844.2497 | 1360.1 | 2748.7997 | 3% | 27% | 70% | 48% | Green | [In Prog] late start;
DSFFLOW-4124 | In Progress | Network Management | Element Management | Maiden Installation | 113 | 113 | 40 | 2 | 0% | 2 | 0% | Jul 31 2025 | Jul 31 2025 | Aug 04 2025 | Jan 30 2026 | Jan 30 2026 |  | 183 | 183 | 4680 | 4680 | 1356 | 4676 | 0% | 35% | 29% | 29% | Green | [In Prog]
DSFFLOW-2656 | In Progress | Network Management | Element Management | Upgrade | 96 | 98 | 63 | 4 | 50% | 2 | 50% | Jul 01 2025 | Jul 01 2025 | Jul 01 2025 | Dec 19 2025 | Dec 19 2025 |  | 171 | 171 | 2840 | 2544 | 1350.7333 | 2492.8333 | 2% | 64% | 49% | 53% | Green | [In Prog]
DSFFLOW-1713 | In Progress | Core Network | UDM | Upgrade | 18 | 18 | 8 | 2 | 0% | 2 | 0% | Mar 15 2025 | Mar 15 2025 | Mar 15 2025 | Oct 30 2025 | Oct 30 2025 |  | 229 | 229 | 2328 | 2328 | 1341 | 2336 | 0% | 44% | 83% | 58% | Green | [In Prog] late start;
DSFFLOW-4085 | In Progress | Core Network | Cloud | Upgrade | 206 | 206 | 27 | 1 | 0% | 30 | 0% | Jul 07 2025 | Jul 07 2025 | Jul 07 2025 | Nov 14 2025 | Nov 14 2025 |  | 130 | 130 | 7116.98 | 7116.98 | 1283.96 | 7008.54 | 2% | 13% | 60% | 18% | Green | [In Prog] late start;
DSFFLOW-64 | Closed | Network Management | Element Management | Upgrade | 58 | 56 | 56 | 1 | 100% | 1 | 100% | Mar 02 2025 | Mar 02 2025 | Mar 13 2025 | Aug 30 2025 | Sep 12 2025 | Sep 19 2025 | 181 | 194 | 1350.91 | 1350.91 | 1231.6597 | 1231.6597 | 9% | 100% | 104% | 91% | Green | [In Prog] late start;
DSFFLOW-4778 | Closed | Core Network | EPC, IMS, Signaling | Upgrade | 70 | 70 | 66 | 6 | 100% |  |  | Jun 22 2025 | Jun 23 2025 | Jun 23 2025 | Aug 30 2025 | Aug 29 2025 | Aug 29 2025 | 69 | 67 | 1231 | 1231 | 1173 | 1070 | 13% | 94% | 100% | 95% | Red | [In Prog] effort budget breached; late start;
DSFFLOW-1568 | In Progress | BOS | D&A Mediation | Upgrade | 33 | 33 | 17 | 2 | 0% | 1 | 0% | May 25 2025 | May 25 2025 | Jun 30 2025 | Sep 19 2025 | Sep 19 2025 |  | 117 | 117 | 1614.5 | 1614.5 | 1169.0133 | 1503.14 | 7% | 52% | 103% | 72% | Green | [In Prog] late start;
DSFFLOW-2544 | In Progress | Core Network | Cloud-3PP/MPBN | Maiden Installation | 78 | 78 | 2 | 2 | 0% | 2 | 0% | Apr 19 2025 | Apr 19 2025 | Jun 26 2025 | Oct 31 2025 | Oct 31 2025 |  | 195 | 195 | 8854.5 | 8854.5 | 1160.5 | 8738 | 1% | 3% | 80% | 13% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-2249 | In Progress | BOS | Monetization Charging | Upgrade, Expansion, Maiden Installation | 396 | 396 | 42 | 10 | 10% | 10 | 10% | Jun 22 2025 | Jun 22 2025 | Jun 27 2025 | Sep 19 2025 | Nov 28 2025 |  | 89 | 159 | 3683.11 | 3683.11 | 1154.2 | 3173.29 | 14% | 11% | 58% | 31% | Amber | [In Prog] efforts burnt misaligned with work progress; efforts burnt misaligned with time progress; work progress misaligned with time progress;
DSFFLOW-3649 | In Progress | Core Network | IMS | Upgrade | 31 | 31 | 16 | 3 | 33% | 9 | 0% | Jul 03 2025 | Jul 03 2025 | Jul 03 2025 | Dec 30 2025 | Dec 30 2025 |  | 180 | 180 | 2715 | 2715 | 1150 | 2595 | 4% | 52% | 45% | 42% | Green | [In Prog]
DSFFLOW-1223 | Backlog | Core Network | EPC, Signaling, UDM | Expansion | 166 | 166 | 1 | 39 | 0% | 12 | 0% | May 09 2025 | May 09 2025 |  | Dec 31 2025 | Dec 31 2025 |  | 236 | 236 | 33976 | 33976 | 1129 | 33976 | 0% | 1% | 58% | 3% | Red | [Backlog] with wrong project state with work happening; efforts burning; 129 days past due start date;
DSFFLOW-4677 | In Progress | Core Network | EPC | Maiden Installation | 127 | 127 | 2 | 4 | 0% | 13 | 0% | Aug 11 2025 | Aug 11 2025 | Aug 11 2025 | Dec 31 2026 | Dec 31 2026 |  | 507 | 507 | 10485.6 | 10485.6 | 1120.75 | 10435.6 | 0% | 2% | 8% | 11% | Green | [In Prog]
DSFFLOW-993 | In Progress | Core Network | UDM | Maiden Installation | 40 | 40 | 10 | 1 | 0% | 1 | 0% | Feb 10 2025 | Feb 10 2025 | Feb 10 2025 | Dec 31 2025 | Dec 31 2025 |  | 324 | 324 | 1955 | 1955 | 1045 | 1676 | 14% | 25% | 69% | 53% | Amber | [In Prog] efforts burnt misaligned with work progress;
DSFFLOW-4498 | In Progress | Core Network | EPC, IMS, MSS, UDM | Upgrade | 210 | 206 | 21 | 9 | 0% | 8 | 0% | Jul 15 2025 | Jul 15 2025 | Jul 15 2025 | Jan 15 2026 | Jan 15 2026 |  | 184 | 184 | 3907 | 3907 | 1021.1667 | 3895.8333 | 0% | 10% | 38% | 26% | Green | [In Prog] late start;
DSFFLOW-3669 | In Progress | Core Network | EPC, IMS, Signaling, UDM | Upgrade | 226 | 226 | 19 | 9 | 0% | 9 | 0% | Jun 09 2025 | Jun 19 2025 | Jun 19 2025 | Oct 30 2025 | Nov 30 2025 |  | 143 | 164 | 4764 | 4764 | 1013.25 | 4630 | 3% | 8% | 58% | 21% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-1662 | In Progress | Network Management | Element Management | Upgrade | 67 | 67 | 45 | 2 | 0% |  |  | May 07 2025 | May 07 2025 | Jun 06 2025 | Jul 31 2025 | Sep 30 2025 |  | 85 | 146 | 1440 | 1440 | 1010 | 1355 | 6% | 67% | 95% | 70% | Green | [In Prog] late start;
DSFFLOW-2169 | In Progress | Core Network | EPC, Signaling, UDM | Maiden Installation | 327 | 327 | 1 | 10 | 0% | 10 | 0% | Jun 15 2025 | Jun 15 2025 | Jun 24 2025 | Aug 20 2027 | Aug 20 2027 |  | 796 | 796 | 29308.1 | 29308.1 | 998.7 | 29302.09 | 0% | 0% | 13% | 3% | Green | [In Prog] late start;
DSFFLOW-4140 | In Progress | Core Network | Cloud, EPC, IMS, UDM | Upgrade | 97 | 97 | 21 | 6 | 0% | 6 | 0% | Apr 16 2025 | Apr 16 2025 | Apr 16 2025 | Dec 30 2025 | Dec 30 2025 |  | 258 | 258 | 2201 | 2201 | 996 | 2121 | 4% | 22% | 62% | 45% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-386 | Closed | Core Network | EPC | Maiden Installation | 30 | 30 | 30 | 1 | 100% | 1 | 100% | Nov 10 2024 | Nov 10 2024 | Jan 01 2025 | Jan 26 2025 | Jan 26 2025 | Jun 30 2025 | 77 | 77 | 1773 | 1773 | 993 | 993 | 44% | 100% | 299% | 56% | Red | [Closed] schedule overrun > 10%; efforts saved; feedback: opportunity for optimized effort baseline; late start;
DSFFLOW-1383 | Closed | Core Network | EPC | Upgrade | 63 | 63 | 63 | 3 | 100% | 2 | 100% | Dec 31 2024 | Dec 31 2024 | Jan 01 2025 | Jun 30 2025 | Jun 30 2025 | May 27 2025 | 181 | 181 | 952 | 952 | 952 | 952 | 0% | 100% | 81% | 100% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan;
DSFFLOW-3311 | In Progress | BOS | Monetization Charging | Expansion | 415 | 415 | 171 | 2 | 50% | 4 | 0% | Jul 27 2025 | Jul 27 2025 | Jul 22 2025 | Sep 30 2025 | Sep 30 2025 |  | 65 | 65 | 3533.6 | 3533.6 | 946.55 | 3015.1 | 15% | 41% | 88% | 27% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress;
DSFFLOW-3498 | In Progress | Core Network | EPC, Signaling, UDM | Migration | 77 | 77 | 37 | 5 | 0% | 8 | 0% | Jun 18 2025 | Jun 18 2025 | Jul 23 2025 | Dec 31 2025 | Dec 31 2025 |  | 196 | 196 | 1514.6 | 1514.6 | 936.5 | 1474.6 | 3% | 48% | 49% | 62% | Green | [In Prog] late start;
DSFFLOW-3745 | In Progress | Core Network | UDM | Migration | 15 | 14 | 0 |  |  | 1 | 0% | Jul 28 2025 | Jul 28 2025 | Aug 12 2025 | Dec 26 2025 | Dec 26 2025 |  | 151 | 151 | 2080 | 2080 | 911.5 | 2080 | 0% | 0% | 38% | 44% | Amber | [In Prog] time ticking without any work progress; efforts burnt misaligned with work progress; late start;
DSFFLOW-1103 | Closed | Core Network, Network Management | EPC, Resource Orchestration | Maiden Installation | 44 | 44 | 44 | 3 | 100% |  |  | May 16 2025 | May 16 2025 | May 19 2025 | Aug 30 2025 | Sep 08 2025 | Sep 04 2025 | 106 | 115 | 938 | 938 | 907 | 907 | 3% | 100% | 97% | 97% | Green | [Closed] ahead of schedule; efforts saved;
DSFFLOW-626 | Backlog | Core Network | EPC | Maiden Installation | 34 | 34 | 0 | 2 | 0% | 2 | 0% | Apr 29 2025 | Apr 29 2025 | Apr 29 2025 | Aug 31 2025 | Aug 31 2025 |  | 124 | 124 | 2496 | 2496 | 904 | 2392 | 4% | 0% | 118% | 36% | Red | [Backlog] with wrong project state with efforts burning; 139 days past due start date;
DSFFLOW-4694 | In Progress | Core Network | Cloud | Upgrade | 48 | 48 | 11 | 4 | 0% | 1 | 0% | Jul 13 2025 | Jul 14 2025 | Jul 14 2025 | Dec 30 2025 | Dec 30 2025 |  | 170 | 169 | 2298 | 2298 | 875 | 2263 | 2% | 23% | 42% | 38% | Green | [In Prog] late start;
DSFFLOW-1322 | Closed | Core Network | EPC, Exposure, UDM | Upgrade | 88 | 33 | 33 | 4 | 100% | 6 | 100% | Apr 22 2025 | Apr 22 2025 | Aug 21 2025 | Aug 30 2025 | Aug 30 2025 | Aug 21 2025 | 130 | 130 | 940.5 | 884.5 | 869.5 | 869.5 | 2% | 100% | 93% | 98% | Green | [Closed] ahead of schedule; efforts saved; late start;
DSFFLOW-6590 | In Progress | Core Network | IMS | Maiden Installation | 23 | 23 | 0 |  |  |  |  | Aug 25 2025 | Aug 25 2025 | Sep 16 2025 | Dec 31 2028 | Dec 31 2028 |  | 1224 | 1224 | 1559.99 | 1559.99 | 836 | 1559.99 | 0% | 0% | 2% | 54%
DSFFLOW-3528 | In Progress | Core Network | EPC | Upgrade | 130 | 130 | 14 | 1 | 0% | 7 | 0% | Jul 04 2025 | Jul 07 2025 | Jul 07 2025 | Dec 31 2025 | Dec 31 2025 |  | 180 | 177 | 1992 | 1992 | 820 | 1912 | 4% | 11% | 44% | 41% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-1926 | In Progress | Core Network | Cloud | Maiden Installation | 97 | 97 | 15 | 3 | 33% | 6 | 17% | May 26 2025 | May 26 2025 | Jul 10 2025 | Dec 31 2026 | Dec 31 2026 |  | 584 | 584 | 2188.6 | 2188.6 | 817.6 | 2098.6 | 4% | 15% | 21% | 37% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-2689 | In Progress | Network Management | Element Management | Upgrade | 130 | 128 | 58 | 2 | 0% | 3 | 0% | Jun 23 2025 | Jul 14 2025 | Jul 14 2025 | Mar 31 2026 | Nov 30 2025 |  | 281 | 139 | 1759.9 | 1805.4 | 813.3997 | 1722.3997 | 5% | 45% | 51% | 45% | Green | [In Prog]
DSFFLOW-1087 | In Progress | Network Management | Element Management | Upgrade | 60 | 58 | 34 | 2 | 0% | 1 | 0% | May 14 2025 | May 14 2025 | May 17 2025 | Nov 29 2025 | Nov 29 2025 |  | 199 | 199 | 1160 | 1175 | 811.5 | 1050.5 | 11% | 59% | 66% | 69% | Green | [In Prog]
DSFFLOW-2482 | Closed | Core Network | EPC | Expansion | 24 | 24 | 16 | 1 | 0% | 1 | 100% | Jun 09 2025 | Jun 09 2025 | Jun 24 2025 | Dec 12 2025 | Dec 12 2025 | Sep 12 2025 | 186 | 186 | 816 | 816 | 804 | 716 | 12% | 67% | 51% | 99% | Red | [Closed] incomplete work; ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; late start;
DSFFLOW-1057 | In Progress | Core Network | EPC | Upgrade, Maiden Installation | 86 | 86 | 9 | 3 | 0% | 6 | 0% | May 07 2025 | May 16 2025 | May 16 2025 | Jan 30 2026 | Jan 30 2026 |  | 268 | 259 | 3893.75 | 3893.75 | 802.5 | 3876.75 | 0% | 10% | 50% | 21% | Green | [In Prog] late start;
DSFFLOW-4636 | In Progress | Core Network | Core Network Automation, EPC | Maiden Installation | 51 | 51 | 0 |  |  |  |  | Jun 30 2025 | Jun 30 2025 | Aug 22 2025 | Jun 29 2026 | Jun 29 2026 |  | 364 | 364 | 1716 | 1716 | 795 | 1660 | 3% | 0% | 23% | 46% | Amber | [In Prog] time ticking without any work progress; efforts burnt misaligned with work progress; late start;
DSFFLOW-2497 | In Progress | Core Network, Network Management | Activation, EPC, Resource Orchestration | Migration | 96 | 98 | 18 | 4 | 0% | 2 | 0% | May 29 2025 | Jun 30 2025 | Jun 27 2025 | Feb 27 2026 | Aug 30 2025 |  | 274 | 61 | 2110 | 2488 | 788 | 2486 | 0% | 18% | 137% | 32% | Green | [In Prog] late start;
DSFFLOW-1337 | In Progress | BOS | Monetization Charging | Upgrade, Expansion | 338 | 338 | 18 | 14 | 0% | 24 | 0% | Apr 14 2025 | Apr 14 2025 | May 30 2025 | Oct 30 2026 | Oct 30 2026 |  | 564 | 564 | 5063 | 5063 | 786.25 | 4796.75 | 5% | 5% | 29% | 16% | Green | [In Prog] late start;
DSFFLOW-1151 | In Progress | BOS | Monetization Charging | Upgrade | 498 | 498 | 78 | 5 | 40% | 38 | 8% | Jun 01 2025 | Jun 01 2025 | Jun 01 2025 | Feb 28 2026 | Feb 28 2026 |  | 272 | 272 | 3023 | 3023 | 783.05 | 2908 | 4% | 16% | 42% | 26% | Green | [In Prog]
DSFFLOW-4260 | In Progress | Core Network | Cloud | Upgrade | 86 | 86 | 20 | 2 | 100% | 10 | 10% | Jul 06 2025 | Jul 06 2025 | Jul 06 2025 | Nov 29 2025 | Nov 29 2025 |  | 146 | 146 | 2248 | 2248 | 732 | 1920 | 15% | 23% | 54% | 33% | Green | [In Prog] late start;
DSFFLOW-1041 | In Progress | Core Network | IMS | Maiden Installation | 17 | 13 | 13 | 4 | 100% | 5 | 100% | May 14 2025 | May 14 2025 | May 16 2025 | Apr 30 2027 | Apr 30 2027 | Jun 27 2025 | 716 | 716 | 728 | 728 | 728 | 604 | 17% | 100% | 6% | 100% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress;
DSFFLOW-5303 | In Progress | Core Network | Cloud | Maiden Installation | 68 | 68 | 7 | 3 | 0% | 3 | 0% | Aug 12 2025 | Aug 12 2025 | Aug 26 2025 | Dec 31 2028 | Dec 31 2028 |  | 1237 | 1237 | 2709.5 | 2709.5 | 728 | 2619.5 | 3% | 10% | 3% | 27% | Green | [In Prog] late start;
DSFFLOW-611 | In Progress | Core Network | EPC | Maiden Installation | 58 | 58 | 0 | 2 | 0% | 2 | 0% | Feb 10 2025 | Feb 10 2025 | Jul 21 2025 | Dec 31 2025 | Dec 31 2025 |  | 324 | 324 | 2055 | 2055 | 727 | 1899 | 8% | 0% | 69% | 35% | Amber | [In Prog] time ticking without any work progress; efforts burnt misaligned with work progress; late start;
DSFFLOW-1790 | Closed | Core Network | Cloud | Upgrade | 85 | 85 | 85 | 5 | 100% | 15 | 100% | Jun 02 2025 | Jun 02 2025 | Jul 10 2025 | Mar 31 2026 | Mar 31 2026 | Aug 26 2025 | 302 | 302 | 726 | 726 | 726 | 726 | 0% | 100% | 28% | 100% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; late start;
DSFFLOW-5480 | In Progress | Core Network | Cloud | Upgrade | 140 | 140 | 1 | 2 | 0% | 18 | 0% | Aug 25 2025 | Aug 25 2025 | Aug 25 2025 | Aug 31 2026 | Aug 31 2026 |  | 371 | 371 | 8499.5 | 8760.5 | 722.5 | 8760.5 | 0% | 1% | 8% | 8% | Green | [In Prog]
DSFFLOW-2641 | In Progress | Network Management | Element Management | Upgrade | 24 | 24 | 18 | 1 | 0% |  |  | Jul 01 2025 | Jul 01 2025 | Jul 01 2025 | Sep 29 2025 | Sep 29 2025 |  | 90 | 90 | 850 | 850 | 705.95 | 830.45 | 2% | 75% | 92% | 83% | Green | [In Prog]
DSFFLOW-4213 | In Progress | Core Network | IMS | Upgrade | 80 | 80 | 40 | 3 | 0% | 3 | 0% | Jul 25 2025 | Jul 30 2025 | Jul 30 2025 | Oct 31 2025 | Oct 31 2025 |  | 98 | 93 | 1036 | 1036 | 702.6475 | 1022.7708 | 1% | 50% | 59% | 68% | Green | [In Prog]
DSFFLOW-1599 | In Progress | Network Management | Element Management | Upgrade | 63 | 62 | 51 | 2 | 0% |  |  | May 15 2025 | May 15 2025 | Jun 24 2025 | Aug 29 2025 | Sep 30 2025 |  | 106 | 138 | 1102 | 1094 | 697.5 | 771.5 | 29% | 82% | 94% | 64% | Green | [In Prog] late start;
DSFFLOW-1263 | In Progress | Core Network | EPC | Maiden Installation | 36 | 36 | 11 | 2 | 0% | 2 | 0% | May 11 2025 | May 11 2025 | Jul 11 2025 | Aug 01 2025 | Aug 01 2025 |  | 82 | 82 | 871 | 871 | 687.75 | 809 | 7% | 31% | 163% | 79% | Amber | [In Prog] efforts burnt misaligned with work progress; efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-3396 | Closed | BOS | Monetization Billing | Maiden Installation | 19 | 11 | 11 | 1 | 100% |  |  | Jun 11 2025 | Jun 11 2025 | Jun 16 2025 | Jul 23 2025 | Jul 23 2025 | Aug 07 2025 | 42 | 42 | 760 | 760 | 680 | 680 | 11% | 100% | 135% | 89% | Red | [Closed] schedule overrun > 10%; efforts saved; feedback: opportunity for optimized effort baseline;
DSFFLOW-1368 | In Progress | Core Network | EPC | Migration | 21 | 21 | 1 | 1 | 0% |  |  | May 23 2025 | May 23 2025 | Jun 25 2025 | Dec 31 2025 | Dec 31 2025 |  | 222 | 222 | 1214.8 | 1214.8 | 672.03 | 1214.8 | 0% | 5% | 55% | 55% | Red | [In Prog] efforts burnt outweighing work output; late start;
DSFFLOW-3142 | In Progress | Core Network | Cloud | Maiden Installation | 100 | 100 | 7 | 3 | 0% | 6 | 0% | Jul 06 2025 | Jul 06 2025 | Jul 15 2025 | Sep 14 2025 | Sep 14 2025 |  | 70 | 70 | 1766.6 | 1766.6 | 670 | 1688.6 | 4% | 7% | 111% | 38% | Amber | [In Prog] efforts burnt misaligned with work progress; efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-2467 | In Progress | BOS | D&A Mediation | Upgrade | 25 | 25 | 6 | 1 | 0% |  |  | Jun 11 2025 | Jun 11 2025 | Jun 26 2025 | Nov 30 2025 | Nov 30 2025 |  | 172 | 172 | 1232.5 | 1232.5 | 669.31 | 1082.84 | 12% | 24% | 60% | 54% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-168 | Closed | BOS | Monetization Charging | Upgrade | 59 | 59 | 59 | 1 | 0% | 5 | 40% | Mar 21 2025 | Mar 18 2025 | Mar 18 2025 | Sep 03 2025 | Sep 03 2025 | Jun 13 2025 | 166 | 169 | 790.8 | 790.8 | 652.5 | 652.5 | 17% | 100% | 52% | 83% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; feedback: opportunity for optimized effort baseline;
DSFFLOW-1729 | In Progress | Network Management | Element Management | Upgrade | 67 | 64 | 26 | 2 | 0% |  |  | May 07 2025 | May 07 2025 | Jun 09 2025 | Oct 31 2025 | Oct 31 2025 |  | 177 | 177 | 1240 | 1200 | 651 | 1187 | 1% | 41% | 78% | 54% | Green | [In Prog] late start;
DSFFLOW-894 | In Progress | Core Network | UDM | Upgrade | 23 | 23 | 6 | 1 | 0% | 1 | 0% | May 06 2025 | May 06 2025 | May 06 2025 | Dec 31 2025 | Dec 31 2025 |  | 239 | 239 | 940 | 940 | 643 | 940 | 0% | 26% | 58% | 68% | Amber | [In Prog] efforts burnt misaligned with work progress;
DSFFLOW-3730 | In Progress | Core Network | UDM | Migration | 16 | 15 | 0 |  |  | 1 | 0% | Jul 28 2025 | Jul 28 2025 | Aug 12 2025 | Oct 31 2025 | Oct 31 2025 |  | 95 | 95 | 1283 | 1283 | 634.5 | 1283 | 0% | 0% | 59% | 49% | Amber | [In Prog] time ticking without any work progress; efforts burnt misaligned with work progress; late start;
DSFFLOW-550 | Closed | Network Management | Element Management & Reporting | Upgrade | 42 | 43 | 43 |  |  | 1 | 100% | Apr 30 2025 | Apr 07 2025 | Jul 02 2025 | Feb 27 2026 | Jul 23 2025 | Jul 18 2025 | 303 | 107 | 624 | 624 | 618 | 618 | 1% | 100% | 95% | 99% | Green | [Closed] ahead of schedule; efforts saved; late start;
DSFFLOW-3852 | In Progress | Core Network | Cloud | Migration | 118 | 118 | 22 | 2 | 0% | 10 | 0% | Jul 22 2025 | Jul 22 2025 | Jul 31 2025 | Dec 31 2025 | Dec 31 2025 |  | 162 | 162 | 2002.5 | 2002.5 | 618 | 1936.5 | 3% | 19% | 39% | 31% | Green | [In Prog] late start;
DSFFLOW-2321 | Closed | Core Network | Exposure | Upgrade | 51 | 31 | 31 | 1 | 100% | 1 | 100% | Jun 02 2025 | Jun 19 2025 | Jun 19 2025 | Aug 29 2025 | Sep 05 2025 | Sep 05 2025 | 88 | 78 | 881.75 | 693 | 607.7667 | 607.7667 | 12% | 100% | 100% | 88% | Amber | [Closed] schedule overrun < 10%; efforts saved; feedback: opportunity for optimized effort baseline; late start;
DSFFLOW-2107 | In Progress | Core Network | IMS, UDM | Maiden Installation | 90 | 90 | 0 | 5 | 0% | 5 | 0% | May 29 2025 | May 29 2025 | Jun 30 2025 | Feb 27 2026 | Feb 27 2026 |  | 274 | 274 | 4087.7 | 4087.7 | 606.5997 | 4044.2 | 1% | 0% | 43% | 15% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-1200 | Closed | Network Management | Element Management & Reporting | Upgrade | 192 | 35 | 35 | 2 | 100% | 2 | 100% | May 08 2025 | Feb 10 2025 | Apr 22 2025 | Aug 31 2026 | Oct 31 2025 | Jun 19 2025 | 480 | 263 | 3156 | 1055.5 | 605.5 | 605.5 | 43% | 100% | 49% | 57% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; feedback: opportunity for optimized effort baseline; late start;
DSFFLOW-4850 | In Progress | Core Network | Core Network Automation, EPC, IMS, MSS, Signaling, UDM | Migration | 301 | 301 | 10 | 16 | 0% | 6 | 0% | Aug 11 2025 | Aug 11 2025 | Sep 01 2025 | Oct 25 2025 | Oct 25 2025 |  | 75 | 75 | 8332.6 | 8332.6 | 604 | 8332.6 | 0% | 3% | 57% | 7% | Green | [In Prog] late start;
DSFFLOW-5367 | In Progress | Core Network | Cloud | Maiden Installation | 79 | 79 | 8 | 2 | 0% | 4 | 0% | Aug 08 2025 | Aug 08 2025 | Aug 26 2025 | Dec 31 2028 | Dec 31 2028 |  | 1241 | 1241 | 2541 | 2541 | 601 | 2493 | 2% | 10% | 4% | 24% | Green | [In Prog] late start;
DSFFLOW-1445 | Closed | Core Network | IMS | Upgrade | 78 | 59 | 59 | 3 | 0% | 3 | 0% | May 27 2025 | May 27 2025 | May 28 2025 | Jul 18 2025 | Jul 04 2025 | Jul 04 2025 | 52 | 38 | 801 | 639.5 | 600.2697 | 600.2697 | 6% | 100% | 100% | 94% | Green | [Closed] efforts saved;
DSFFLOW-1247 | On Hold | Core Network | EPC, IMS, UDM | Upgrade | 168 | 168 | 0 | 6 | 0% | 6 | 0% | May 06 2025 | May 23 2025 | May 23 2025 | Dec 31 2025 | Dec 31 2025 |  | 239 | 222 | 2729 | 2729 | 581.5 | 2643.25 | 3% | 0% | 55% | 21% | Amber | [On Hold] time ticking without any work progress; efforts burnt misaligned with work progress; late start;
DSFFLOW-97 | Closed | Network Management | Element Management & Reporting | Upgrade | 50 | 47 | 47 | 4 | 100% |  |  | Mar 12 2025 | Mar 12 2025 | Mar 13 2025 | May 31 2025 | Jul 31 2025 | Jul 15 2025 | 80 | 141 | 844 | 801.5 | 575 | 575 | 28% | 100% | 89% | 72% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; feedback: opportunity for optimized effort baseline;
DSFFLOW-4361 | In Progress | Core Network | Cloud, EPC | Upgrade | 141 | 141 | 15 | 3 | 33% | 12 | 0% | Jun 19 2025 | Jun 19 2025 | Jun 19 2025 | Dec 19 2025 | Dec 19 2025 |  | 183 | 183 | 3597 | 3597 | 571 | 3597 | 0% | 11% | 52% | 16% | Green | [In Prog] late start;
DSFFLOW-4540 | In Progress | Core Network | Cloud | Upgrade | 34 | 34 | 0 | 2 | 0% | 2 | 0% | Jul 28 2025 | Jul 14 2025 | Jul 14 2025 | Dec 31 2025 | Feb 21 2026 |  | 156 | 222 | 1364 | 1364 | 570 | 1108 | 19% | 0% | 32% | 42% | Amber | [In Prog] time ticking without any work progress; efforts burnt misaligned with work progress; late start;
DSFFLOW-845 | In Progress | Core Network | MSS | Upgrade | 22 | 22 | 7 | 1 | 0% |  |  | Feb 24 2025 | Sep 15 2025 | Sep 09 2025 | Jun 30 2025 | Dec 31 2025 |  | 126 | 107 | 674 | 674 | 558 | 673 | 0% | 32% | 7% | 83% | Amber | [In Prog] efforts burnt misaligned with work progress; efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-5636 | In Progress | BOS | Common Services-Data Migration, Core Commerce, Monetization Charging | Maiden Installation, Migration, Business Configuration | 107 | 107 | 0 | 3 | 0% | 15 | 0% | Jul 24 2025 | Jul 24 2025 | Sep 08 2025 | Apr 16 2026 | Apr 16 2026 |  | 266 | 266 | 15668.1 | 15668.1 | 555.29 | 15651.06 | 0% | 0% | 23% | 4% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-1135 | Closed | BOS | D&A Mediation | Upgrade | 34 | 34 | 34 | 2 | 100% |  |  | May 19 2025 | May 19 2025 | May 19 2025 | Jun 20 2025 | Jun 20 2025 | Jun 20 2025 | 32 | 32 | 569.1 | 569.1 | 548 | 548 | 4% | 100% | 100% | 96% | Green | [Closed] efforts saved;
DSFFLOW-5597 | In Progress | Core Network | Cloud | Upgrade | 34 | 34 | 5 | 2 | 0% | 2 | 0% | Aug 10 2025 | Aug 11 2025 | Aug 11 2025 | Oct 30 2025 | Oct 30 2025 |  | 81 | 80 | 1828 | 1906 | 540 | 1810 | 5% | 15% | 53% | 28% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-3233 | In Progress | Core Network | UDM | Migration | 16 | 15 | 1 |  |  | 1 | 0% | Jul 14 2025 | Jul 14 2025 | Aug 12 2025 | Aug 15 2025 | Aug 15 2025 |  | 32 | 32 | 614 | 614 | 529 | 614 | 0% | 7% | 215% | 86% | Red | [In Prog] efforts burnt outweighing work output; efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-4564 | In Progress | Core Network | Cloud | Upgrade | 32 | 32 | 10 | 2 | 0% | 2 | 0% | Jul 22 2025 | Jul 22 2025 | Jul 22 2025 | Jan 15 2026 | Jan 15 2026 |  | 177 | 177 | 1211 | 1211 | 527 | 1183 | 2% | 31% | 35% | 44% | Green | [In Prog]
DSFFLOW-1646 | In Progress | Network Management | Element Management | Upgrade | 67 | 67 | 26 | 2 | 0% |  |  | May 27 2025 | Jul 21 2025 | Jun 09 2025 | Aug 29 2025 | Oct 17 2025 |  | 94 | 88 | 1440 | 1440 | 520.01 | 1424.01 | 1% | 39% | 72% | 36% | Green | [On Hold] early start;
DSFFLOW-4588 | In Progress | Core Network | Core Network Automation, EPC, UDM | Maiden Installation | 83 | 83 | 0 | 1 | 0% | 6 | 0% | Jul 30 2025 | Jul 30 2025 | Aug 08 2025 | Jun 30 2026 | Jun 30 2026 |  | 335 | 335 | 2284 | 2284 | 519.3997 | 2279 | 0% | 0% | 16% | 23% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-5858 | In Progress | Core Network | EPC | Upgrade, Maiden Installation | 62 | 62 | 2 |  |  |  |  | Aug 28 2025 | Sep 01 2025 | Sep 01 2025 | Jun 30 2026 | Oct 31 2025 |  | 306 | 60 | 1370 | 1370 | 510 | 1328 | 3% | 3% | 36% | 37% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-2234 | In Progress | Network Management | Element Management & Reporting | Upgrade | 38 | 38 | 38 |  |  | 1 | 100% | Jun 17 2025 | Jun 17 2025 | Jun 30 2025 | Oct 31 2025 | Oct 31 2025 |  | 136 | 136 | 652 | 652 | 501 | 501 | 23% | 100% | 72% | 77% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-2219 | Closed | Core Network | Cloud | Expansion | 37 | 35 | 28 | 1 | 100% | 1 | 100% | Jun 09 2025 | Jun 09 2025 | Jun 18 2025 | Dec 12 2025 | Dec 12 2025 | Sep 12 2025 | 186 | 186 | 517.35 | 502.35 | 494.85 | 494.85 | 1% | 80% | 51% | 99% | Red | [Closed] incomplete work; ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; late start;
DSFFLOW-952 | Closed | Core Network | UDM | Migration | 18 | 16 | 6 |  |  | 1 | 100% | May 12 2025 | May 12 2025 | May 12 2025 | Jun 29 2025 | Jun 29 2025 | Aug 29 2025 | 48 | 48 | 491.25 | 491.25 | 491.25 | 491.25 | 0% | 38% | 224% | 100% | Red | [Closed] incomplete work; effort budget spent; schedule overrun > 10%;
DSFFLOW-798 | In Progress | Core Network | Cloud | Maiden Installation | 77 | 77 | 0 | 11 | 0% |  |  | May 05 2025 | Apr 01 2025 | Jun 03 2025 | Dec 30 2025 | Mar 20 2026 |  | 239 | 353 | 6839 | 6839 | 487.75 | 7613.5 | -11% | 0% | 49% | 7% | Red | [In Prog] projecting 5%+ EAC effort overrun; time ticking without any work progress; late start;
DSFFLOW-2858 | Closed | BOS | Monetization Charging | Upgrade | 34 | 34 | 34 | 2 | 100% | 4 | 100% | May 09 2025 | Jun 09 2025 | Jul 16 2025 | Jul 25 2025 | Jul 25 2025 | Aug 06 2025 | 77 | 46 | 486 | 486 | 486 | 486 | 0% | 100% | 126% | 100% | Red | [Closed] schedule overrun > 10%; late start;
DSFFLOW-3093 | In Progress | Core Network | Cloud | Expansion | 89 | 89 | 17 | 4 | 0% | 4 | 0% | Jun 04 2025 | Jun 04 2025 | Jul 15 2025 | Mar 31 2026 | Mar 31 2026 |  | 300 | 300 | 2335.5 | 2335.5 | 481 | 2293.5 | 2% | 19% | 37% | 21% | Green | [In Prog] late start;
DSFFLOW-2610 | In Progress | Core Network | Signaling | Upgrade | 11 | 11 | 8 | 1 | 0% |  |  | Jun 27 2025 | Jun 27 2025 | Jun 27 2025 | Dec 31 2025 | Dec 31 2025 |  | 187 | 187 | 605 | 605 | 480 | 605 | 0% | 73% | 47% | 79% | Red | [In Prog] efforts burning without any work progress; time ticking without any work progress;
DSFFLOW-4396 | In Progress | Core Network | MSS | Upgrade | 43 | 41 | 23 | 1 | 0% | 7 | 0% | Aug 04 2025 | Aug 04 2025 | Aug 05 2025 | Oct 06 2025 | Oct 06 2025 |  | 63 | 63 | 734 | 734 | 476.9167 | 691.0833 | 6% | 56% | 78% | 65% | Green | [In Prog]
DSFFLOW-3870 | In Progress | Core Network | Cloud | Expansion | 62 | 62 | 29 | 4 | 100% | 4 | 50% | Jul 14 2025 | Jul 14 2025 | Jul 29 2025 | Dec 24 2025 | Dec 24 2025 |  | 163 | 163 | 727.94 | 727.94 | 473.2697 | 712.9397 | 2% | 47% | 43% | 65% | Green | [In Prog] late start;
DSFFLOW-2575 | In Progress | Core Network | Cloud | Maiden Installation | 32 | 32 | 7 | 2 | 0% |  |  | Jun 23 2025 | Jun 23 2025 | Jul 14 2025 | Dec 01 2025 | Dec 01 2025 |  | 161 | 161 | 1262 | 1262 | 472 | 1221 | 3% | 22% | 57% | 37% | Green | [In Prog] late start;
DSFFLOW-462 | Closed | Core Network | MSS | Upgrade | 28 | 28 | 28 | 1 | 100% | 4 | 100% | Mar 17 2025 | Apr 30 2025 | Apr 30 2025 | Jun 30 2025 | Sep 03 2025 | Sep 03 2025 | 105 | 126 | 469 | 469 | 468.7 | 468.7 | 0% | 100% | 100% | 100% | Green | [Closed]
DSFFLOW-2264 | In Progress | BOS | Monetization Charging | Upgrade, Maiden Installation | 571 | 571 | 11 | 7 | 0% | 29 | 0% | Jun 16 2025 | Jun 16 2025 | Jun 16 2025 | Feb 16 2026 | Feb 16 2026 |  | 245 | 245 | 5197.5 | 5197.5 | 462 | 4958.5 | 5% | 2% | 40% | 9% | Green | [In Prog]
DSFFLOW-3562 | In Progress | Core Network | Cloud | Upgrade | 23 | 23 | 12 | 2 | 50% |  |  | Jul 23 2025 | Jul 23 2025 | Jul 23 2025 | Sep 30 2025 | Sep 30 2025 |  | 69 | 69 | 844 | 844 | 460 | 804 | 5% | 52% | 89% | 55% | Amber | [In Prog] projecting 1%+ EAC effort overrun ; efforts burnt misaligned with work progress; work progress misaligned with time progress;
DSFFLOW-32 | Closed | Network Management | Element Management & Reporting | Upgrade | 57 | 31 | 31 | 2 | 100% |  |  | Dec 08 2024 | Dec 08 2024 | Dec 09 2024 | Feb 17 2025 | Feb 18 2025 | Feb 17 2025 | 71 | 72 | 910 | 459 | 457 | 457 | 0% | 100% | 99% | 100% | Green | [Closed] ahead of schedule;
DSFFLOW-4744 | In Progress | Core Network | EPC, UDM | Maiden Installation | 25 | 17 | 7 |  |  |  |  | Feb 11 2025 | Feb 11 2025 | Aug 14 2025 | Dec 31 2025 | Dec 31 2025 |  | 323 | 323 | 1001 | 1001 | 456 | 1001 | 0% | 41% | 69% | 46% | Green | [In Prog] late start;
DSFFLOW-2352 | Closed | Core Network | Signaling | Upgrade | 26 | 26 | 26 | 2 | 100% |  |  | Jun 02 2025 | Jun 02 2025 | Jun 02 2025 | Jul 04 2025 | Jul 30 2025 | Jul 30 2025 | 32 | 58 | 511 | 511 | 452 | 452 | 12% | 100% | 100% | 88% | Red | [Closed] schedule overrun > 10%; efforts saved; feedback: opportunity for optimized effort baseline; late start;
DSFFLOW-1008 | In Progress | Network Management | Resource Orchestration | Upgrade | 26 | 25 | 22 | 1 | 0% |  |  | Jun 16 2025 | Jun 03 2025 | Jun 18 2025 | Sep 30 2025 | Sep 30 2025 |  | 106 | 119 | 507.1 | 507.1 | 451 | 484.1 | 5% | 88% | 93% | 89% | Green | [In Prog] late start;
DSFFLOW-3513 | In Progress | Network Management | Activation | Maiden Installation | 69 | 69 | 3 | 1 | 0% | 3 | 0% | Jul 11 2025 | Jul 11 2025 | Jul 24 2025 | Dec 26 2025 | Dec 26 2025 |  | 168 | 168 | 3075.0867 | 3075.0867 | 445 | 3032.5867 | 1% | 4% | 44% | 14% | Green | [In Prog] late start;
DSFFLOW-3786 | In Progress | Core Network | EPC, UDM | Maiden Installation | 29 | 29 | 0 | 3 | 0% | 3 | 0% | Mar 31 2025 | Mar 31 2025 | Jul 29 2025 | Mar 31 2026 | Mar 31 2026 |  | 365 | 365 | 10283 | 10283 | 440 | 10283 | 0% | 0% | 48% | 4% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-2593 | In Progress | Core Network | EPC | Maiden Installation | 16 | 16 | 2 | 2 | 0% | 1 | 0% | May 25 2025 | May 25 2025 | Jul 02 2025 | Dec 31 2025 | Dec 31 2025 |  | 220 | 220 | 2581 | 2581 | 439 | 2551 | 1% | 13% | 55% | 17% | Green | [In Prog] late start;
DSFFLOW-2368 | On Hold | Network Management | Activation, Resource Orchestration | Upgrade | 34 | 34 | 15 | 2 | 0% | 1 | 0% | Jun 01 2025 | Jun 01 2025 | Jun 20 2025 | Aug 31 2033 | Aug 31 2033 |  | 3013 | 3013 | 766.71 | 766.71 | 437.7 | 738.71 | 4% | 44% | 4% | 57% | Amber | [On Hold] efforts burnt misaligned with time progress; late start;
DSFFLOW-2813 | In Progress | Network Management | Resource Orchestration | Maiden Installation | 11 | 11 | 5 | 1 | 0% |  |  | May 04 2025 | May 04 2025 | Jul 10 2025 | Mar 31 2026 | Mar 31 2026 |  | 331 | 331 | 1125 | 1125 | 434.75 | 1125 | 0% | 45% | 43% | 39% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-5335 | In Progress | Core Network | UDM | Migration | 14 | 14 | 2 |  |  | 1 | 0% | Aug 19 2025 | Aug 19 2025 | Aug 26 2025 | Dec 30 2025 | Dec 30 2025 |  | 133 | 133 | 811 | 811 | 432.5 | 811 | 0% | 14% | 26% | 53% | Amber | [In Prog] efforts burnt misaligned with work progress;
DSFFLOW-49 | Closed | Network Management | Element Management & Reporting | Upgrade | 30 | 30 | 30 | 1 | 100% |  |  | Feb 19 2025 | Feb 20 2025 | Feb 28 2025 | Aug 29 2025 | Apr 17 2025 | Mar 27 2025 | 191 | 56 | 488 | 488 | 430 | 430 | 12% | 100% | 63% | 88% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; feedback: opportunity for optimized effort baseline; late start;
DSFFLOW-3060 | In Progress | Core Network | UDM | Upgrade | 71 | 44 | 20 | 3 | 67% | 5 | 20% | Jun 25 2025 | Jul 16 2025 | Jul 16 2025 | Nov 28 2025 | Nov 28 2025 |  | 156 | 135 | 1032 | 832 | 428 | 756 | 9% | 45% | 51% | 51% | Green | [In Prog]
DSFFLOW-2435 | In Progress | Core Network | EPC | Upgrade | 16 | 16 | 10 | 1 | 100% | 2 | 0% | Jun 16 2025 | Jun 16 2025 | Jun 16 2025 | Oct 30 2025 | Oct 30 2025 |  | 136 | 136 | 558 | 558 | 428 | 542 | 3% | 63% | 72% | 77% | Green | [In Prog] late start;
DSFFLOW-5417 | In Progress | BOS | Core Commerce | Maiden Installation, Business Configuration | 39 | 39 | 1 | 2 | 0% |  |  | May 20 2025 | May 20 2025 | Aug 28 2025 | Jul 30 2026 | Jul 30 2026 |  | 436 | 436 | 20355 | 20355 | 428 | 19931 | 2% | 3% | 29% | 2% | Green | [In Prog] late start;
DSFFLOW-2138 | Closed | Network Management | Resource Orchestration | Upgrade, Maiden Installation | 52 | 37 | 37 | 2 | 100% | 2 | 100% | Jun 12 2025 | Jun 12 2025 | Jun 18 2025 | Aug 15 2025 | Aug 31 2025 | Aug 14 2025 | 64 | 80 | 646.6497 | 559.9 | 425.65 | 425.65 | 24% | 100% | 79% | 76% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; feedback: opportunity for optimized effort baseline;
DSFFLOW-5716 | Closed | Core Network | EPC | Upgrade | 24 | 24 | 24 | 1 | 100% | 1 | 100% | May 05 2025 | Jul 07 2025 | Jul 07 2025 | Sep 05 2025 | Aug 29 2025 | Aug 28 2025 | 123 | 53 | 422.5 | 422.5 | 423 | 423 | 0% | 100% | 98% | 100% | Red | [Closed] incomplete work; effort budget spent; schedule overrun < 10%; late start;
DSFFLOW-6605 | In Progress | Core Network | UDM | Maiden Installation | 18 | 18 | 1 |  |  |  |  | Aug 20 2025 | Aug 20 2025 | Sep 16 2025 | Dec 31 2028 | Dec 31 2028 |  | 1229 | 1229 | 1060.5 | 1060.5 | 421 | 996 | 6% | 6% | 3% | 40%
DSFFLOW-4457 | Closed | Network Management | Element Management & Reporting | Upgrade | 38 | 14 | 14 | 2 | 100% |  |  | Aug 04 2025 | Jul 08 2025 | Aug 05 2025 | Dec 26 2025 | Sep 15 2025 | Aug 13 2025 | 144 | 69 | 946.5 | 505.5 | 405.5 | 405.5 | 20% | 100% | 53% | 80% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; feedback: opportunity for optimized effort baseline; late start;
DSFFLOW-1864 | In Progress | Network Management | Element Management & Reporting | Upgrade | 35 | 35 | 35 |  |  | 1 | 100% | Jun 09 2025 | Jun 09 2025 | Jun 18 2025 | Dec 31 2025 | Dec 31 2025 |  | 205 | 205 | 506 | 506 | 397 | 397 | 22% | 100% | 51% | 78% | Amber | [In Prog] efforts burnt misaligned with work progress; work progress misaligned with time progress; late start;
DSFFLOW-5229 | In Progress | Network Management | Element Management | Upgrade | 106 | 106 | 3 | 1 | 0% | 5 | 0% | Aug 17 2025 | Aug 17 2025 | Aug 25 2025 | Mar 30 2026 | Mar 30 2026 |  | 225 | 225 | 4286.9667 | 4286.9667 | 395.25 | 4138.2167 | 3% | 3% | 16% | 9% | Green | [In Prog] late start;
DSFFLOW-591 | In Progress | Core Network | Cloud-3PP/MPBN | Upgrade | 30 | 30 | 10 | 1 | 0% |  |  | Apr 22 2025 | Apr 22 2025 | Jun 05 2025 | Jun 30 2025 | Jun 30 2025 |  | 69 | 69 | 850 | 850 | 387 | 789.5 | 7% | 33% | 220% | 46% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-3685 | Closed | Core Network | MSS | Upgrade | 24 | 24 | 24 | 2 | 100% | 2 | 100% | Jun 30 2025 | Jun 27 2025 | Jun 27 2025 | Sep 14 2025 | Sep 01 2025 | Sep 01 2025 | 76 | 66 | 434.5 | 434.5 | 386 | 386 | 11% | 100% | 100% | 89% | Green | [Closed] efforts saved; feedback: opportunity for optimized effort baseline;
DSFFLOW-4605 | In Progress | Core Network | Cloud | Upgrade | 127 | 127 | 26 | 3 | 100% | 12 | 0% | Jul 24 2025 | Jul 24 2025 | Jul 24 2025 | Dec 31 2025 | Dec 31 2025 |  | 160 | 160 | 2196 | 2196 | 386 | 2196 | 0% | 20% | 38% | 18% | Green | [In Prog] late start;
DSFFLOW-3127 | In Progress | Core Network | EPC | Upgrade | 57 | 57 | 8 | 2 | 0% | 2 | 0% | Jun 21 2025 | Jun 23 2025 | Jun 23 2025 | Aug 30 2025 | Dec 31 2025 |  | 70 | 191 | 638 | 638 | 384 | 600 | 6% | 14% | 48% | 60% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-2828 | On Hold | Core Network | UDM | Migration | 15 | 15 | 1 |  |  | 1 | 0% | Jul 14 2025 | Jul 14 2025 |  | Nov 28 2025 | Nov 28 2025 |  | 137 | 137 | 593 | 593 | 383.5 | 542 | 9% | 7% | 51% | 65% | Red | [On Hold] efforts burnt outweighing work output;
DSFFLOW-4379 | In Progress | Network Management | Element Management | Upgrade | 69 | 69 | 28 | 1 | 0% | 2 | 0% | Aug 03 2025 | Aug 04 2025 | Aug 04 2025 | Dec 31 2025 | Dec 31 2025 |  | 150 | 149 | 1002.5 | 1002.5 | 383 | 925.5 | 8% | 41% | 33% | 38% | Green | [In Prog]
DSFFLOW-2947 | Closed | Core Network | MSS | Upgrade | 21 | 21 | 21 | 1 | 100% |  |  | Mar 18 2025 | May 08 2025 | May 08 2025 | Aug 15 2025 | Jul 15 2025 | Jul 15 2025 | 150 | 68 | 411.5 | 411.5 | 382.5 | 382.5 | 7% | 100% | 100% | 93% | Green | [Closed] efforts saved;
DSFFLOW-1400 | In Progress | Core Network | EPC | Maiden Installation | 37 | 37 | 5 | 2 | 0% | 2 | 0% | May 22 2023 | May 22 2023 | May 27 2025 | Jul 30 2025 | Jul 30 2025 |  | 800 | 800 | 1432 | 1432 | 376 | 1432 | 0% | 14% | 107% | 26% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-4245 | In Progress | Network Management | Activation, Element Management, Resource Orchestration | Upgrade | 41 | 41 | 22 | 3 | 67% |  |  | Jul 21 2025 | Jul 21 2025 | Aug 06 2025 | Sep 30 2025 | Sep 30 2025 |  | 71 | 71 | 461.9 | 461.9 | 374.79 | 462.65 | 0% | 54% | 89% | 81% | Amber | [In Prog] efforts burnt misaligned with work progress; work progress misaligned with time progress; late start;
DSFFLOW-4299 | In Progress | Core Network | Cloud, EPC, UDM | Upgrade | 88 | 88 | 11 | 8 | 0% |  |  | Jul 21 2025 | Jul 28 2025 | Jul 28 2025 | Oct 31 2025 | Oct 31 2025 |  | 102 | 95 | 1686 | 1686 | 374.5 | 1617 | 4% | 13% | 59% | 22% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-2336 | Closed | Core Network | Signaling | Upgrade | 26 | 26 | 26 | 2 | 100% |  |  | Jun 02 2025 | Jun 02 2025 | Jun 02 2025 | Jul 04 2025 | Aug 15 2025 | Aug 14 2025 | 32 | 74 | 446 | 446 | 356 | 356 | 20% | 100% | 99% | 80% | Red | [Closed] incomplete work; schedule overrun > 10%; efforts saved; feedback: opportunity for optimized effort baseline; late start;
DSFFLOW-3836 | In Progress | Network Management | Activation | Upgrade | 48 | 48 | 18 | 2 | 50% | 1 | 0% | May 31 2025 | May 31 2025 | Jul 30 2025 | Sep 29 2025 | Sep 29 2025 |  | 121 | 121 | 612 | 612 | 354 | 540 | 12% | 38% | 94% | 58% | Green | [In Prog] work progress misaligned with time progress; late start;
DSFFLOW-5079 | In Progress | BOS | Monetization Charging | Expansion | 67 | 67 | 39 | 1 | 0% |  |  | Jul 28 2025 | Jul 28 2025 | Aug 20 2025 | Sep 30 2025 | Sep 30 2025 |  | 64 | 64 | 674.8 | 674.8 | 343.45 | 644.55 | 4% | 58% | 88% | 51% | Green | [In Prog] late start;
DSFFLOW-5827 | In Progress | Core Network | UDM | Upgrade | 24 | 16 | 11 | 1 | 100% | 1 | 100% | Jul 27 2025 | Jul 27 2025 | Jul 26 2025 | Oct 30 2025 | Oct 30 2025 |  | 95 | 95 | 376 | 376 | 340 | 340 | 10% | 69% | 60% | 90% | Green | [In Prog] late start;
DSFFLOW-5245 | In Progress | Core Network | Cloud | Expansion, Maiden Installation | 72 | 72 | 0 | 6 | 0% |  |  | Aug 18 2025 | Aug 18 2025 | Aug 29 2025 | Jun 30 2026 | Jun 30 2026 |  | 316 | 316 | 1478 | 1478 | 339.5 | 1448 | 2% | 0% | 11% | 23% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-3029 | In Progress | Core Network | IMS | Migration | 20 | 20 | 3 | 2 | 0% | 2 | 0% | May 07 2025 | May 07 2025 | Jul 14 2025 | Dec 31 2025 | Dec 31 2025 |  | 238 | 238 | 902 | 902 | 336 | 902 | 0% | 15% | 58% | 37% | Green | [In Prog] late start;
DSFFLOW-5773 | In Progress | Core Network | MSS | Maiden Installation | 41 | 41 | 7 | 1 | 0% | 5 | 0% | Jul 07 2025 | Jul 07 2025 | Sep 02 2025 | Oct 31 2025 | Sep 30 2025 |  | 116 | 85 | 518 | 518 | 332.5 | 438 | 15% | 17% | 91% | 64% | Amber | [In Prog] efforts burnt misaligned with work progress; work progress misaligned with time progress; late start;
DSFFLOW-1697 | Closed | Core Network | EPC | Upgrade | 30 | 21 | 21 | 2 | 100% | 2 | 100% | May 26 2025 | Jun 12 2025 | Jun 12 2025 | Aug 31 2025 | Sep 04 2025 | Sep 04 2025 | 97 | 84 | 346 | 346 | 310 | 310 | 10% | 100% | 100% | 90% | Amber | [Closed] schedule overrun < 10%; efforts saved; late start;
DSFFLOW-3078 | In Progress | Core Network | UDM | Upgrade | 27 | 27 | 4 | 1 | 0% | 4 | 0% | Jul 02 2025 | Jul 03 2025 | Jul 03 2025 | Sep 01 2025 | Oct 17 2025 |  | 61 | 106 | 656 | 656 | 306 | 651 | 1% | 15% | 77% | 47% | Amber | [In Prog] efforts burnt misaligned with work progress; work progress misaligned with time progress;
DSFFLOW-3812 | On Hold | Core Network | Cloud | Upgrade | 36 | 36 | 4 | 2 | 0% | 2 | 0% | May 05 2025 | Jul 28 2025 | Jul 28 2025 | Dec 30 2025 | Dec 30 2025 |  | 239 | 155 | 785 | 879 | 305 | 854 | 3% | 11% | 37% | 35% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-5461 | Closed | Core Network | Cloud | Upgrade | 18 | 18 | 18 | 1 | 100% |  |  | Jun 08 2025 | Jun 08 2025 | Jun 08 2025 | Aug 14 2026 | Aug 14 2026 | Aug 14 2025 | 432 | 432 | 305 | 305 | 305 | 305 | 0% | 100% | 16% | 100% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-1614 | Closed | Network Management | Resource Orchestration | Upgrade | 54 | 52 | 52 | 1 | 100% | 1 | 100% | May 28 2025 | May 28 2025 | Jun 04 2025 | Jan 30 2026 | Jan 30 2026 | Sep 15 2025 | 247 | 247 | 299.7533 | 299.7533 | 300.12 | 300.12 | 0% | 100% | 45% | 100% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress;
DSFFLOW-4525 | In Progress | Core Network | UDM | Migration | 15 | 15 | 0 |  |  | 1 | 0% | Aug 11 2025 | Aug 11 2025 | Aug 29 2025 | Jan 30 2026 | Jan 30 2026 |  | 172 | 172 | 1277 | 1277 | 297.5 | 1277 | 0% | 0% | 25% | 23% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-3342 | In Progress | Network Management | Activation, Resource Orchestration | Upgrade | 145 | 140 | 26 | 6 | 0% | 2 | 0% | Jul 10 2025 | Jul 10 2025 | Jul 10 2025 | Nov 21 2025 | Jun 12 2026 |  | 134 | 337 | 3933 | 3933 | 295.5 | 3876 | 1% | 19% | 22% | 8% | Green | [In Prog]
DSFFLOW-4411 | Closed | Network Management | Element Management | Upgrade | 34 | 31 | 31 | 1 | 100% | 2 | 100% | Aug 06 2025 | Aug 06 2025 | Aug 11 2025 | Sep 30 2025 | Sep 30 2025 | Sep 10 2025 | 55 | 55 | 515.95 | 456.45 | 284.45 | 284.45 | 38% | 100% | 64% | 62% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; feedback: opportunity for optimized effort baseline;
DSFFLOW-4992 | In Progress | Core Network | UDM | Maiden Installation | 16 | 16 | 4 |  |  |  |  | Jul 13 2025 | Jul 13 2025 | Aug 22 2025 | Dec 31 2025 | Dec 31 2025 |  | 171 | 171 | 308 | 308 | 280 | 308 | 0% | 25% | 42% | 91% | Red | [In Prog] efforts burnt outweighing work output; efforts burnt misaligned with time progress; late start;
DSFFLOW-4955 | In Progress | Network Management | Element Management | Maiden Installation | 77 | 77 | 8 | 2 | 0% | 2 | 0% | Aug 18 2025 | Aug 18 2025 | Aug 25 2025 | Nov 28 2025 | Nov 28 2025 |  | 102 | 102 | 2003.5 | 2003.5 | 278 | 2003.5 | 0% | 10% | 35% | 14% | Green | [In Prog]
DSFFLOW-1879 | Closed | Network Management | Element Management & Reporting | Maiden Installation | 25 | 14 | 14 | 1 | 100% |  |  | May 26 2025 | May 26 2025 | May 26 2025 | Jun 30 2025 | Jun 30 2025 | Jun 30 2025 | 35 | 35 | 304.5 | 298 | 268.5 | 268.5 | 10% | 100% | 100% | 90% | Green | [Closed] efforts saved;
DSFFLOW-2931 | On Hold | Network Management | Activation | Maiden Installation | 46 | 46 | 4 | 1 | 0% | 1 | 0% | Jun 08 2025 | Jun 08 2025 | Jun 09 2025 | Dec 30 2025 | Dec 30 2025 |  | 205 | 205 | 1061.25 | 1061.25 | 267.72 | 1027.07 | 3% | 9% | 52% | 25% | Green | [On Hold]
DSFFLOW-2625 | Closed | Core Network | IMS | Upgrade | 30 | 28 | 28 | 1 | 0% | 1 | 0% | Jun 29 2025 | Jun 30 2025 | Jun 30 2025 | Jul 31 2025 | Aug 01 2025 | Aug 01 2025 | 32 | 32 | 267 | 267 | 267.01 | 267.01 | 0% | 100% | 100% | 100% | Green | [Closed]
DSFFLOW-310 | Closed | Core Network | UDM | Upgrade | 19 | 19 | 19 | 1 | 100% | 1 | 100% | Apr 20 2025 | Apr 22 2025 | Apr 22 2025 | May 31 2025 | Jun 05 2025 | Jun 05 2025 | 41 | 44 | 267 | 267 | 267 | 267 | 0% | 100% | 100% | 100% | Green | [Closed]
DSFFLOW-340 | Closed | Core Network | UDM | Upgrade | 17 | 17 | 17 | 1 | 100% | 1 | 100% | Mar 04 2025 | Mar 04 2025 | Mar 04 2025 | Jun 30 2025 | Aug 11 2025 | Aug 11 2025 | 118 | 160 | 264 | 264 | 264 | 264 | 0% | 100% | 100% | 100% | Green | [Closed]
DSFFLOW-4628 | In Progress | Core Network | Core Network Automation, UDM | Maiden Installation | 29 | 29 | 0 |  |  |  |  | Aug 09 2025 | Aug 09 2025 | Aug 22 2025 | Jun 29 2026 | Jun 29 2026 |  | 324 | 324 | 730 | 730 | 263 | 710 | 3% | 0% | 14% | 36% | Amber | [In Prog] efforts burnt misaligned with work progress; late start;
DSFFLOW-1026 | Closed | Network Management | Resource Orchestration | Upgrade | 22 | 19 | 19 | 1 | 100% | 1 | 100% | Apr 20 2025 | Apr 20 2025 | Jun 13 2025 | Jun 29 2025 | Jun 29 2025 | Jul 09 2025 | 70 | 70 | 277.75 | 260.77 | 260.77 | 260.77 | 0% | 100% | 114% | 100% | Red | [Closed] schedule overrun > 10%; late start;
DSFFLOW-5544 | In Progress | Core Network | Cloud-3PP/MPBN | Maiden Installation | 57 | 57 | 0 | 2 | 0% |  |  | May 26 2025 | May 26 2025 | Aug 28 2025 | Dec 13 2025 | Dec 13 2025 |  | 201 | 201 | 3635.2 | 3635.2 | 260.75 | 3498.2 | 4% | 0% | 59% | 7% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-4865 | Closed | Core Network | MSS, Signaling | Upgrade | 23 | 23 | 23 | 2 | 100% | 2 | 100% | Jun 06 2024 | Jun 06 2024 | Aug 19 2025 | Aug 21 2025 | Aug 21 2025 | Aug 21 2025 | 441 | 441 | 280.5 | 280.5 | 255 | 255 | 9% | 100% | 100% | 91% | Green | [Closed] efforts saved; late start;
DSFFLOW-5938 | In Progress | Core Network | MSS | Maiden Installation | 40 | 40 | 1 | 1 | 0% | 3 | 0% | Jul 24 2025 | Jul 24 2025 | Sep 15 2025 | Mar 31 2026 | Mar 31 2026 |  | 250 | 250 | 2280 | 2280 | 249.75 | 2228 | 2% | 3% | 24% | 11% | Amber | [Assigned] with 53 days past due start date;
DSFFLOW-2901 | On Hold | Network Management | Resource Orchestration | Maiden Installation | 34 | 33 | 13 | 1 | 0% |  |  | Jun 01 2025 | Jun 01 2025 | Jul 08 2025 | Aug 30 2025 | Aug 30 2025 |  | 90 | 90 | 777.75 | 777.75 | 248.75 | 742.75 | 5% | 39% | 125% | 32% | Amber | [On Hold] efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-4794 | Closed | Network Management | Element Management & Reporting | Upgrade | 23 | 17 | 17 | 1 | 100% |  |  | Aug 11 2025 | Aug 11 2025 | Aug 15 2025 | Aug 28 2025 | Aug 29 2025 | Sep 01 2025 | 17 | 18 | 282 | 282 | 248 | 248 | 12% | 100% | 116% | 88% | Red | [Closed] schedule overrun > 10%; efforts saved; feedback: opportunity for optimized effort baseline;
DSFFLOW-4760 | In Progress | Network Management | Resource Orchestration | Upgrade | 52 | 52 | 37 | 2 | 50% | 2 | 50% | Aug 12 2025 | Aug 12 2025 | Aug 14 2025 | Sep 29 2025 | Sep 29 2025 |  | 48 | 48 | 217.08 | 276.58 | 245.32 | 241.58 | 13% | 71% | 86% | 89% | Green | [In Prog]
DSFFLOW-4230 | Closed | Core Network | Cloud | Upgrade | 17 | 17 | 17 | 1 | 100% |  |  | Aug 03 2025 | Aug 04 2025 | Aug 04 2025 | Aug 21 2025 | Aug 21 2025 | Aug 21 2025 | 18 | 17 | 272 | 272 | 243 | 243 | 11% | 100% | 100% | 89% | Red | [Closed] effort overrun > 1%; schedule overrun > 10%;
DSFFLOW-4442 | In Progress | Network Management | Element Management | Upgrade | 25 | 24 | 10 | 1 | 0% |  |  | Jul 27 2025 | Jul 27 2025 | Aug 06 2025 | Sep 18 2025 | Sep 18 2025 |  | 53 | 53 | 418.2 | 418.2 | 242.5 | 415.7 | 1% | 42% | 107% | 58% | Green | [In Prog] work progress misaligned with time progress; late start;
DSFFLOW-3458 | Closed | Core Network | Cloud | Upgrade | 18 | 18 | 18 | 1 | 100% | 1 | 100% | Jul 22 2025 | Jul 22 2025 | Jul 29 2025 | Aug 29 2025 | Aug 29 2025 | Aug 11 2025 | 38 | 38 | 242 | 242 | 242 | 242 | 0% | 100% | 54% | 100% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan;
DSFFLOW-4713 | In Progress | Core Network | MSS | Upgrade | 38 | 38 | 15 | 2 | 50% | 4 | 75% | Jul 25 2025 | Aug 25 2025 | Aug 25 2025 | Aug 30 2025 | Dec 31 2025 |  | 36 | 128 | 652 | 652 | 241 | 652 | 0% | 39% | 22% | 37% | Green | [In Prog]
DSFFLOW-5797 | In Progress | Core Network | IMS | Upgrade | 30 | 30 | 10 | 2 | 0% | 2 | 0% | Aug 03 2025 | Aug 03 2025 | Aug 03 2025 | Nov 29 2025 | Nov 29 2025 |  | 118 | 118 | 746 | 746 | 240 | 746 | 0% | 33% | 43% | 32% | Green | [In Prog] late start;
DSFFLOW-4343 | In Progress | Core Network | Cloud, EPC | Upgrade | 141 | 141 | 4 | 3 | 0% | 12 | 0% | Jun 19 2025 | Jun 19 2025 | Aug 18 2025 | Dec 19 2025 | Dec 19 2025 |  | 183 | 183 | 3597 | 3597 | 239 | 3597 | 0% | 3% | 52% | 7% | Green | [In Prog] late start;
DSFFLOW-4916 | In Progress | Network Management | Element Management | Upgrade | 78 | 78 | 12 | 2 | 0% |  |  | Aug 18 2025 | Aug 18 2025 | Aug 25 2025 | Dec 15 2025 | Dec 15 2025 |  | 119 | 119 | 1231.8 | 1231.8 | 238.01 | 1231.81 | 0% | 15% | 30% | 19% | Amber | [In Prog] time ticking without any work progress;
DSFFLOW-4198 | In Progress | Core Network | UDM | Upgrade | 16 | 16 | 5 | 1 | 0% |  |  | Jul 30 2025 | Aug 04 2025 | Aug 04 2025 | Sep 30 2025 | Oct 31 2025 |  | 62 | 88 | 460 | 460 | 237.5 | 377.5 | 18% | 31% | 56% | 52% | Amber | [In Prog] efforts burnt misaligned with work progress;
DSFFLOW-2560 | Closed | Network Management | Resource Orchestration | Upgrade | 24 | 18 | 18 | 1 | 100% |  |  | Jun 26 2025 | Jun 26 2025 | Jun 27 2025 | Jul 08 2025 | Jul 08 2025 | Jul 07 2025 | 12 | 12 | 222 | 222 | 222 | 222 | 0% | 100% | 92% | 100% | Green | [Closed] ahead of schedule;
DSFFLOW-5060 | In Progress | Core Network | IMS | Maiden Installation | 50 | 50 | 3 | 5 | 0% |  |  | Aug 07 2025 | Aug 07 2025 | Aug 19 2025 | Dec 19 2025 | Dec 19 2025 |  | 134 | 134 | 2379 | 2379 | 214 | 2369 | 0% | 6% | 35% | 9% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-3547 | Closed | Core Network | MSS | Upgrade | 13 | 13 | 13 | 1 | 100% |  |  | Jul 06 2025 | Jul 08 2025 | Jul 08 2025 | Aug 14 2025 | Aug 08 2025 | Aug 08 2025 | 39 | 31 | 220 | 220 | 210 | 210 | 5% | 100% | 100% | 95% | Green | [Closed] efforts saved;
DSFFLOW-535 | In Progress | Core Network | EPC | Maiden Installation | 14 | 14 | 13 | 1 | 0% |  |  | Jan 01 2025 | Dec 31 2024 | Jan 01 2025 | Jul 31 2025 | May 29 2025 | Apr 30 2025 | 211 | 149 | 149 | 149 | 206 | 198 | -33% | 93% | 81% | 138% | Red | [In Prog] effort budget breached; projecting 5%+ EAC effort overrun; efforts burnt misaligned with work progress; efforts burnt misaligned with time progress;
DSFFLOW-3581 | Closed | Core Network | MSS | Upgrade | 13 | 13 | 13 | 1 | 100% |  |  | Jul 22 2025 | Jul 03 2025 | Jul 03 2025 | Aug 15 2025 | Aug 08 2025 | Aug 08 2025 | 24 | 36 | 220 | 220 | 204.5 | 204.5 | 7% | 100% | 100% | 93% | Green | [Closed] efforts saved;
DSFFLOW-921 | Closed | Core Network | UDM | Upgrade | 23 | 23 | 23 | 1 | 100% | 2 | 100% | May 14 2025 | May 14 2025 | May 14 2025 | Jul 04 2025 | Jul 04 2025 | Jul 04 2025 | 51 | 51 | 202.5 | 202.5 | 202.4 | 202.4 | 0% | 100% | 100% | 100% | Green | [Closed]
DSFFLOW-2419 | Closed | Core Network | IMS | Upgrade | 52 | 52 | 52 | 2 | 100% | 2 | 100% | Jun 05 2025 | Jun 09 2025 | Jun 09 2025 | Jun 26 2025 | Jul 16 2025 | Jul 16 2025 | 21 | 37 | 322 | 322 | 200 | 200 | 38% | 100% | 100% | 62% | Red | [Closed] schedule overrun > 10%; efforts saved; feedback: opportunity for optimized effort baseline; late start;
DSFFLOW-2962 | In Progress | Core Network | Cloud | Maiden Installation | 101 | 101 | 0 | 2 | 0% | 8 | 0% | Jul 07 2025 | Jul 07 2025 | Aug 05 2025 | Dec 30 2025 | Dec 30 2025 |  | 176 | 176 | 1816 | 1816 | 192.0008 | 1816 | 0% | 0% | 44% | 11% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-5401 | In Progress | Core Network | Exposure, IMS | Upgrade | 102 | 102 | 8 | 2 | 0% | 2 | 0% | Aug 22 2025 | Jul 22 2025 | Jul 22 2025 | Dec 31 2025 | Jan 23 2026 |  | 131 | 185 | 1405.4 | 1405.4 | 184.13 | 1397.3867 | 1% | 8% | 34% | 13% | Green | [In Prog]
DSFFLOW-3381 | Closed | Core Network | Signaling | Upgrade | 19 | 19 | 19 | 1 | 100% | 1 | 100% | Jun 10 2025 | Jun 04 2025 | Jun 04 2025 | Jul 30 2025 | Jul 22 2025 | Jul 22 2025 | 50 | 48 | 179 | 179 | 178.5 | 178.5 | 0% | 100% | 100% | 100% | Green | [Closed]
DSFFLOW-937 | Closed | Core Network | IMS | Upgrade | 16 | 16 | 16 | 1 | 0% | 1 | 0% | May 06 2025 | May 06 2025 | May 06 2025 | Jun 29 2025 | Sep 29 2025 | Sep 12 2025 | 54 | 146 | 176 | 176 | 172 | 172 | 2% | 100% | 88% | 98% | Red | [Closed] effort overrun > 1%; schedule overrun > 10%; late start;
DSFFLOW-3327 | Block | Network Management | Resource Orchestration | Upgrade | 26 | 26 | 14 | 1 | 0% |  |  | Jul 15 2025 | Jul 15 2025 | Jul 21 2025 | Oct 31 2025 | Oct 31 2025 |  | 108 | 108 | 334 | 334 | 166.05 | 319.5 | 4% | 54% | 64% | 50% | Green | [Block]
DSFFLOW-3265 | In Progress | Core Network | Cloud, Core Network Automation, EPC, IMS, UDM | Migration | 88 | 88 | 1 | 14 | 0% | 5 | 0% | May 15 2025 | May 15 2025 | Sep 12 2025 | Nov 20 2025 | Nov 20 2025 |  | 189 | 189 | 8395 | 8395 | 162 | 8395 | 0% | 1% | 69% | 2% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-5029 | In Progress | Core Network | UDM | Upgrade | 28 | 28 | 3 | 1 | 0% | 2 | 0% | Jul 29 2025 | Jul 14 2025 | Jul 14 2025 | Nov 03 2025 | Oct 31 2025 |  | 97 | 109 | 608 | 608 | 160 | 608 | 0% | 11% | 65% | 26% | Green | [In Prog] work progress misaligned with time progress; late start;
DSFFLOW-5888 | In Progress | Core Network | IMS | Maiden Installation | 19 | 19 | 0 |  |  |  |  | Sep 01 2025 | Sep 01 2025 | Sep 08 2025 | Sep 29 2025 | Sep 29 2025 |  | 28 | 28 | 595.2 | 595.2 | 157.6 | 545.6 | 8% | 0% | 76% | 26% | Amber | [In Prog] time ticking without any work progress;
DSFFLOW-5200 | In Progress | Core Network | Cloud | Upgrade | 52 | 52 | 6 | 1 | 0% | 5 | 0% | Aug 31 2025 | Aug 11 2025 | Aug 11 2025 | Oct 23 2025 | Oct 23 2025 |  | 53 | 73 | 691 | 691 | 152 | 651 | 6% | 12% | 58% | 22% | Amber | [In Prog] time ticking without any work progress; efforts burnt misaligned with work progress; early start;
DSFFLOW-3443 | On Hold | Network Management | Element Management & Reporting | Upgrade | 21 | 15 | 9 | 1 | 0% |  |  | Jul 14 2025 | Jul 14 2025 | Jul 14 2025 | Sep 19 2025 | Sep 19 2025 | Aug 01 2025 | 67 | 67 | 158.5 | 158.5 | 149 | 229 | -44% | 60% | 28% | 94% | Red | [On Hold] projecting 5%+ EAC effort overrun; efforts burnt misaligned with work progress; efforts burnt misaligned with time progress;
DSFFLOW-5446 | In Progress | Core Network | UDM | Maiden Installation | 20 | 20 | 0 | 1 | 0% |  |  | Aug 25 2025 | Aug 25 2025 | Aug 28 2025 | Oct 31 2025 | Oct 31 2025 |  | 67 | 67 | 521 | 521 | 144 | 521 | 0% | 0% | 43% | 28% | Amber | [In Prog] time ticking without any work progress; efforts burnt misaligned with work progress;
DSFFLOW-4427 | Closed | Network Management | Element Management & Reporting | Upgrade | 24 | 18 | 18 |  |  | 1 | 100% | Jul 28 2025 | Jul 28 2025 | Aug 06 2025 | Aug 08 2025 | Aug 08 2025 | Aug 11 2025 | 11 | 11 | 148 | 148 | 140 | 140 | 5% | 100% | 125% | 95% | Red | [Closed] schedule overrun > 10%; efforts saved; late start;
DSFFLOW-3700 | Closed | Core Network | Signaling | Upgrade | 20 | 19 | 19 | 1 | 100% |  |  | Jun 04 2025 | Jun 04 2025 | Jul 24 2025 | Jul 31 2026 | Jul 31 2026 | Jul 25 2025 | 422 | 422 | 138 | 138 | 138 | 138 | 0% | 100% | 12% | 100% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; late start;
DSFFLOW-5843 | In Progress | Core Network | MSS | Upgrade | 27 | 23 | 3 | 1 | 0% | 3 | 0% | Sep 02 2025 | Sep 08 2025 | Sep 16 2025 | Dec 31 2025 | Dec 31 2025 |  | 120 | 114 | 588.5 | 588.5 | 137.5 | 563 | 4% | 13% | 13% | 23% | Amber | [Assigned] with 13 days past due start date;
DSFFLOW-4055 | On Hold | Network Management | Element Management & Reporting | Upgrade | 26 | 19 | 12 | 2 | 0% |  |  | Aug 04 2025 | Aug 04 2025 | Aug 04 2025 | Sep 30 2025 | Sep 30 2025 |  | 57 | 57 | 328 | 328 | 134.02 | 286.02 | 13% | 63% | 86% | 41% | Amber | [On Hold] efforts burnt misaligned with work progress;
DSFFLOW-6166 | In Progress | Core Network | Cloud | Upgrade | 17 | 17 | 5 | 1 | 0% |  |  | Aug 25 2025 | Aug 25 2025 | Sep 09 2025 | Sep 10 2025 | Sep 10 2025 |  | 16 | 16 | 158 | 158 | 134 | 158 | 0% | 29% | 171% | 85% | Red | [In Prog] efforts burning without any work progress; time ticking without any work progress; late start;
DSFFLOW-6252 | In Progress | Network Management | Element Management | Upgrade | 111 | 111 | 2 | 2 | 0% | 8 | 0% | Sep 13 2025 | Sep 13 2025 | Sep 10 2025 | Jun 29 2026 | Jun 29 2026 |  | 289 | 289 | 2239 | 2239 | 133.5 | 2194 | 2% | 2% | 3% | 6% | Green | [In Prog]
DSFFLOW-1679 | In Progress | Core Network | Cloud-3PP/MPBN | Maiden Installation | 30 | 30 | 1 | 1 | 0% | 1 | 0% | May 16 2025 | May 16 2025 | Jul 22 2025 | Dec 31 2026 | Dec 31 2026 |  | 594 | 594 | 1088.5 | 1088.5 | 128.5 | 1073 | 1% | 3% | 22% | 12% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-3715 | On Hold | Core Network | MSS | Upgrade | 15 | 15 | 3 | 1 | 0% |  |  | Jun 10 2025 | Jul 25 2025 | Jul 25 2025 | Aug 30 2025 | Oct 31 2025 |  | 81 | 98 | 187 | 187 | 127.5 | 187 | 0% | 20% | 61% | 68% | Amber | [In Prog] efforts burnt misaligned with work progress;
DSFFLOW-2708 | On Hold | Core Network | Cloud, Signaling | Upgrade | 14 | 14 | 3 | 2 | 0% | 2 | 0% | Jun 01 2025 | Jun 01 2025 | Jun 01 2025 | Oct 31 2025 | Oct 31 2025 |  | 152 | 152 | 315 | 315 | 121 | 308 | 2% | 21% | 75% | 38% | Green | [In Prog] late start;
DSFFLOW-6379 | In Progress | Core Network | EPC | Upgrade | 22 | 22 | 2 | 1 | 0% | 1 | 0% | Sep 09 2025 | Sep 09 2025 | Sep 19 2025 | Sep 23 2025 | Sep 23 2025 |  | 14 | 14 | 216 | 216 | 112 | 216 | 0% | 9% | 93% | 52% | Amber | [Assigned] with 6 days past due start date;
DSFFLOW-2452 | On Hold | Network Management | Resource Orchestration | Maiden Installation | 44 | 44 | 2 | 1 | 0% | 1 | 0% | May 29 2025 | May 29 2025 | Jul 11 2025 | Feb 27 2026 | Feb 27 2026 |  | 274 | 274 | 1157 | 1157 | 111.58 | 1157 | 0% | 5% | 43% | 10% | Green | [On Hold] late start;
DSFFLOW-4624 | In Progress | Core Network | Signaling | Maiden Installation | 18 | 18 | 0 |  |  |  |  | Aug 09 2025 | Aug 09 2025 | Aug 22 2025 | Jun 29 2026 | Jun 29 2026 |  | 324 | 324 | 570 | 570 | 111 | 559 | 2% | 0% | 14% | 19% | Green | [In Prog] late start;
DSFFLOW-6271 | In Progress | Network Management | Resource Orchestration | Upgrade | 28 | 25 | 11 | 1 | 0% |  |  | Mar 03 2025 | Mar 03 2025 | Sep 09 2025 | Oct 09 2025 | Oct 10 2025 |  | 220 | 221 | 310 | 310 | 110.4167 | 294.1667 | 5% | 44% | 92% | 36% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-5683 | In Progress | Core Network | Cloud, EPC, UDM | Maiden Installation | 131 | 131 | 1 | 3 | 0% | 5 | 0% | Aug 25 2025 | Aug 25 2025 | Sep 04 2025 | Dec 22 2025 | Dec 22 2025 |  | 119 | 119 | 2340 | 2372 | 102 | 2372 | 0% | 1% | 24% | 4% | Green | [In Prog] late start;
DSFFLOW-5578 | In Progress | Core Network | Cloud | Upgrade | 20 | 20 | 1 | 2 | 0% |  |  | Aug 27 2025 | Sep 04 2025 | Sep 04 2025 | Oct 30 2025 | Oct 30 2025 |  | 64 | 56 | 286 | 286 | 96 | 286 | 0% | 5% | 33% | 34% | Amber | [In Prog] time ticking without any work progress; efforts burnt misaligned with work progress; late start;
DSFFLOW-5319 | On Hold | Core Network | Cloud | Upgrade | 16 | 16 | 15 | 1 | 100% | 1 | 0% | Aug 25 2025 | Aug 25 2025 | Aug 26 2025 | Sep 11 2025 | Sep 11 2025 |  | 17 | 17 | 102.5 | 102.5 | 94.0167 | 102.5167 | 0% | 94% | 161% | 92% | Red | [On Hold] projecting 5%+ EAC effort overrun; work progress misaligned with time progress;
DSFFLOW-662 | In Progress | Network Management | Resource Orchestration | Maiden Installation | 63 | 50 | 8 | 1 | 0% | 3 | 0% | Mar 04 2025 | Mar 04 2025 | Jun 05 2025 | Dec 31 2026 | Dec 31 2026 |  | 667 | 667 | 576.2 | 206.3 | 92.9667 | 538.7833 | -161% | 16% | 30% | 45% | Red | [In Prog] projecting 5%+ EAC effort overrun; efforts burnt misaligned with work progress; late start;
DSFFLOW-5960 | On Hold | BOS | D&A Mediation | Maiden Installation | 27 | 27 | 3 |  |  |  |  | Aug 13 2025 | Aug 13 2025 | Sep 09 2025 | Mar 31 2026 | Mar 31 2026 |  | 230 | 230 | 473.3 | 473.3 | 91.2 | 441.5 | 7% | 11% | 18% | 19% | Green | [In Prog] late start;
DSFFLOW-4880 | In Progress | Core Network | Cloud-3PP/MPBN, IMS, MSS, Signaling, UDM | Migration | 135 | 135 | 0 | 16 | 0% | 16 | 0% | Aug 13 2025 | Aug 13 2025 | Sep 05 2025 | Dec 05 2025 | Dec 05 2025 |  | 114 | 114 | 2814.2 | 2814.2 | 88.1 | 2814.1 | 0% | 0% | 36% | 3% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-3611 | Closed | Core Network | Cloud | Upgrade | 17 | 17 | 17 | 1 | 100% |  |  | Jul 23 2025 | Jul 23 2025 | Jul 24 2025 | Aug 28 2025 | Aug 28 2025 | Aug 07 2025 | 36 | 36 | 106 | 106 | 88 | 88 | 17% | 100% | 43% | 83% | Green | [Closed] ahead of schedule; feedback: opportunity for optimized time plan; efforts saved; feedback: opportunity for optimized effort baseline;
DSFFLOW-6398 | In Progress | Core Network | MSS, Signaling | Expansion | 67 | 67 | 0 | 3 | 0% | 4 | 0% | Aug 12 2025 | Aug 12 2025 | Sep 12 2025 | Aug 29 2025 | Oct 31 2025 |  | 17 | 80 | 1525 | 1525 | 85 | 1440 | 6% | 0% | 52% | 6% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-970 | In Progress | Core Network | Cloud-3PP/MPBN | Upgrade | 27 | 27 | 2 | 1 | 0% |  |  | May 08 2025 | May 08 2025 | Aug 07 2025 | Jul 29 2025 | Jul 29 2025 |  | 82 | 82 | 660.75 | 660.75 | 81.5 | 658.25 | 0% | 7% | 166% | 12% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-6286 | In Progress | Core Network | EPC | Upgrade | 18 | 18 | 2 | 1 | 0% |  |  | Aug 25 2025 | Aug 25 2025 | Sep 10 2025 | Sep 18 2025 | Oct 20 2025 |  | 24 | 56 | 141 | 141 | 80 | 141 | 0% | 11% | 51% | 57% | Amber | [In Prog] time ticking without any work progress; efforts burnt misaligned with work progress; late start;
DSFFLOW-6349 | In Progress | Core Network | MSS | Upgrade | 24 | 24 | 1 | 1 | 0% | 1 | 0% | Sep 11 2025 | Sep 11 2025 | Sep 11 2025 | Dec 31 2025 | Dec 31 2025 |  | 111 | 111 | 474 | 474 | 80 | 474 | 0% | 4% | 11% | 17% | Green | [In Prog]
DSFFLOW-1474 | In Progress | Core Network | IMS | Upgrade | 54 | 54 | 5 | 3 | 0% | 2 | 0% | Mar 24 2025 | Mar 20 2025 | Mar 20 2025 | Aug 30 2025 | Jul 15 2025 |  | 159 | 117 | 461.5 | 461.5 | 72 | 393.5 | 15% | 9% | 158% | 16% | Green | [In Prog] late start;
DSFFLOW-3596 | In Progress | Core Network | UDM | Upgrade | 36 | 36 | 2 | 1 | 0% | 2 | 0% | Jul 24 2025 | Jul 24 2025 | Jul 24 2025 | Oct 31 2025 | Oct 31 2025 |  | 99 | 99 | 481.5 | 481.5 | 66 | 481.5 | 0% | 6% | 61% | 14% | Green | [In Prog]
DSFFLOW-5085 | In Progress | BOS | Monetization Charging | Expansion | 80 | 80 | 3 | 1 | 0% | 1 | 0% | Aug 04 2025 | Aug 04 2025 | Aug 20 2025 | Nov 30 2025 | Nov 30 2025 |  | 118 | 118 | 794.9 | 794.9 | 65.5 | 797.2 | 0% | 4% | 42% | 8% | Green | [In Prog] late start;
DSFFLOW-6305 | In Progress | Core Network | EPC | Upgrade | 42 | 42 | 2 | 1 | 0% | 4 | 0% | Sep 08 2025 | Sep 08 2025 | Sep 19 2025 | Sep 29 2025 | Oct 19 2025 |  | 21 | 41 | 378 | 378 | 64 | 378 | 0% | 5% | 36% | 17% | Amber | [Assigned] with 7 days past due start date;
DSFFLOW-5699 | In Progress | Network Management | Element Management | Upgrade | 55 | 51 | 5 | 2 | 0% | 1 | 0% | Aug 31 2025 | Aug 31 2025 | Sep 01 2025 | Nov 18 2025 | Nov 18 2025 |  | 79 | 79 | 637.5 | 637.5 | 59.5 | 637.5 | 0% | 10% | 29% | 9% | Green | [In Prog]
DSFFLOW-4971 | In Progress | Core Network | Cloud-3PP/MPBN | Expansion | 44 | 44 | 3 | 1 | 0% | 1 | 0% | Jul 29 2025 | Jul 29 2025 | Aug 19 2025 | Nov 30 2025 | Nov 30 2025 |  | 124 | 124 | 636 | 636 | 53.5 | 636 | 0% | 7% | 45% | 8% | Green | [In Prog] late start;
DSFFLOW-6689 | In Progress | Core Network | Cloud | Expansion | 61 | 61 | 1 | 2 | 0% | 4 | 0% | Sep 03 2025 | Sep 03 2025 | Sep 19 2025 | Dec 31 2025 | Dec 31 2025 |  | 119 | 119 | 690 | 690 | 48 | 690 | 0% | 2% | 17% | 7%
DSFFLOW-4028 | In Progress | Core Network | Cloud | Maiden Installation | 33 | 33 | 0 | 1 | 0% |  |  | Jul 14 2025 | Jul 14 2025 | Jul 30 2025 | Sep 05 2025 | Sep 05 2025 |  | 53 | 53 | 1736 | 1736 | 42 | 1694 | 2% | 0% | 131% | 2% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-3411 | In Progress | Core Network | IMS | Upgrade | 46 | 46 | 0 | 1 | 0% | 2 | 0% | Jul 14 2025 | Jul 14 2025 | Jul 14 2025 | Aug 15 2025 | Oct 17 2025 |  | 32 | 95 | 560 | 560 | 42 | 536 | 4% | 0% | 74% | 8% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-6356 | In Progress | Core Network | MSS | Upgrade | 28 | 28 | 0 | 1 | 0% | 2 | 0% | Sep 11 2025 | Sep 11 2025 | Sep 11 2025 | Dec 19 2025 | Dec 19 2025 |  | 99 | 99 | 720 | 720 | 40 | 720 | 0% | 0% | 12% | 6% | Green | [In Prog]
DSFFLOW-6660 | In Progress | Network Management | Element Management | Upgrade, Expansion | 41 | 41 | 0 | 2 | 0% |  |  | Sep 16 2025 | Sep 16 2025 | Sep 18 2025 | Oct 30 2025 | Oct 30 2025 |  | 44 | 44 | 830.5 | 830.5 | 35 | 812.5 | 2% | 0% | 16% | 4%
DSFFLOW-5918 | In Progress | Core Network | EPC | Maiden Installation | 94 | 94 | 0 |  |  | 6 | 0% | Aug 31 2025 | Aug 31 2025 | Sep 09 2025 | Dec 31 2026 | Dec 31 2026 |  | 487 | 487 | 6447 | 6447 | 31 | 6442 | 0% | 0% | 5% | 0% | Green | [In Prog] late start;
DSFFLOW-5045 | In Progress | Core Network | Cloud, Core Network Automation, IMS | Maiden Installation | 40 | 40 | 0 | 4 | 0% |  |  | Aug 07 2025 | Aug 07 2025 | Aug 19 2025 | Dec 19 2025 | Dec 19 2025 |  | 134 | 134 | 1139 | 1139 | 21.3 | 1139 | 0% | 0% | 35% | 2% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-3418 | In Progress | Core Network | IMS | Upgrade | 38 | 38 | 0 | 1 | 0% | 2 | 0% | Jul 14 2025 | Jul 14 2025 | Jul 14 2025 | Sep 12 2025 | Sep 22 2025 |  | 60 | 70 | 515 | 515 | 20 | 495 | 4% | 0% | 100% | 4% | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-5755 | In Progress | Core Network | IMS | Upgrade | 50 | 50 | 0 | 1 | 0% | 3 | 0% | Aug 17 2025 | Sep 02 2025 | Sep 02 2025 | Oct 30 2025 | Oct 30 2025 |  | 74 | 58 | 476 | 476 | 8.8333 | 467.1667 | 2% | 0% | 36% | 2% | Amber | [In Prog] time ticking without any work progress;
DSFFLOW-2765 | In Progress | Core Network | Cloud, EPC | Upgrade | 49 | 49 | 2 | 3 | 0% | 3 | 0% | Nov 11 2024 | Nov 11 2024 | Jul 07 2025 | Dec 20 2024 | Dec 20 2024 |  | 39 | 39 | 1560 | 1560 | 1 | 1534 | 2% | 4% | 790% | 0% | Amber | [In Prog] efforts burnt misaligned with time progress; work progress misaligned with time progress; late start;
DSFFLOW-4483 | In Progress | Core Network | EPC | Expansion | 12 | 12 | 8 |  |  |  |  | Aug 18 2025 | Aug 18 2025 | Aug 06 2025 | Sep 12 2025 | Sep 12 2025 |  | 25 | 25 | 161 | 161 | 1 | 161 | 0% | 67% | 138% | 1% | Amber | [In Prog] efforts burnt misaligned with time progress; early start;
DSFFLOW-6032 | In Progress | Core Network | Cloud, EPC | Maiden Installation, Migration | 795 | 795 | 0 | 22 | 0% | 46 | 0% | Mar 25 2025 | Mar 25 2025 | Sep 10 2025 | Dec 30 2026 | Dec 30 2026 |  | 645 | 645 | 14876.5 | 14876.5 |  | 14876.5 | 0% | 0% | 28% |  | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-2674 | In Progress | Core Network | EPC | Maiden Installation | 41 | 41 | 0 |  |  | 4 | 0% | May 01 2024 | May 01 2024 | Jul 10 2025 | Sep 30 2025 | Sep 30 2025 |  | 517 | 517 | 1454 | 1454 |  | 1454 | 0% | 0% | 98% |  | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-3294 | Assigned | Core Network | IMS | Upgrade | 65 | 65 | 0 | 1 | 0% | 4 | 0% | Jul 08 2025 | Jun 26 2025 |  | Sep 22 2025 | Aug 15 2025 |  | 76 | 50 | 312 | 312 |  | 312 | 0% | 0% | 175% |  | Amber | [Assigned] with 69 days past due start date;
DSFFLOW-6573 | Assigned | Core Network | IMS | Upgrade | 45 | 45 | 0 | 1 | 0% | 4 | 0% | Aug 25 2025 | Aug 25 2025 |  | Oct 30 2025 | Oct 30 2025 |  | 66 | 66 | 309 | 309 |  | 309 | 0% | 0% | 43%
DSFFLOW-3998 | Assigned | Core Network | MSS | Upgrade | 13 | 13 | 0 | 1 | 0% |  |  | Jul 25 2025 | Oct 30 2025 |  | Apr 15 2026 | Dec 31 2025 |  | 264 | 62 | 220 | 220 |  | 220 | 0% | 0% | -59% |  | Amber | [Assigned] with 52 days past due start date;
DSFFLOW-4013 | Assigned | Core Network | MSS | Maiden Installation | 38 | 38 | 0 | 1 | 0% | 1 | 0% | Jul 25 2025 | Jul 25 2025 |  | Apr 15 2026 | Apr 15 2026 |  | 264 | 264 | 2613 | 2613 |  | 2613 | 0% | 0% | 23% |  | Amber | [Assigned] with 52 days past due start date;
DSFFLOW-371 | Backlog | Core Network | MSS | Upgrade | 28 | 28 | 0 | 1 | 0% | 2 | 0% | Mar 24 2025 | Sep 15 2025 |  | Jul 25 2025 | Dec 31 2025 |  | 123 | 107 | 700 | 700 |  | 700 | 0% | 0% | 7% |  | Amber | [Backlog] with 175 days past due start date;
DSFFLOW-5903 | In Progress | Core Network | MSS | Upgrade | 22 | 22 | 0 | 1 | 0% | 3 | 0% | Jul 31 2025 | Jul 31 2025 | Jul 31 2025 | Sep 29 2026 | Sep 29 2026 |  | 425 | 425 | 195 | 195 |  | 195 | 0% | 0% | 13% |  | Green | [In Prog] late start;
DSFFLOW-879 | Rejected | Network Management | Element Management & Reporting | Upgrade | 12 | 12 | 0 | 1 | 0% |  |  | May 09 2025 | May 09 2025 |  | Jun 29 2025 | Jun 29 2025 |  | 51 | 51 | 0 | 0 |  | 0 | 0% | 0% | 263%
DSFFLOW-6645 | Assigned | Core Network | Cloud-3PP/MPBN | Expansion | 29 | 29 | 0 | 1 | 0% |  |  | Aug 31 2025 | Aug 31 2025 |  | Dec 12 2025 | Dec 12 2025 |  | 103 | 103 | 728 | 728 |  | 728 | 0% | 0% | 22%
DSFFLOW-356 | Backlog | Core Network | UDM | Expansion | 13 | 13 | 0 | 1 | 0% | 1 | 0% | Dec 18 2024 | Dec 18 2024 |  | Jul 31 2026 | Jul 31 2026 |  | 590 | 590 | 222 | 222 |  | 222 | 0% | 0% | 47% |  | Amber | [Backlog] with 271 days past due start date;
DSFFLOW-4729 | Assigned | Core Network | Cloud-3PP/MPBN | Upgrade | 16 | 16 | 0 | 1 | 0% |  |  | Aug 01 2025 | Aug 01 2025 |  | Oct 31 2025 | Oct 31 2025 |  | 91 | 91 | 320 | 320 |  | 320 | 0% | 0% | 58% |  | Amber | [Assigned] with 45 days past due start date;
DSFFLOW-5135 | In Progress | Network Management | Element Management & Reporting | Upgrade | 300 | 300 | 0 | 9 | 0% | 9 | 0% | Aug 18 2025 | Aug 18 2025 | Aug 25 2025 | Dec 31 2025 | Dec 31 2025 |  | 135 | 135 | 3521 | 3521 |  | 3521 | 0% | 0% | 26% |  | Amber | [In Prog] time ticking without any work progress;
DSFFLOW-5350 | Assigned | BOS | D&A Mediation | Upgrade | 67 | 67 | 0 | 1 | 0% | 2 | 0% | Jul 21 2025 | Jul 21 2025 |  | May 31 2026 | May 31 2026 |  | 314 | 314 | 2487.1 | 2487.1 |  | 2487.1 | 0% | 0% | 20% |  | Amber | [Assigned] with 56 days past due start date;
DSFFLOW-6779 | Assigned | Core Network | Cloud-3PP/MPBN | Expansion | 49 | 49 | 0 | 1 | 0% | 2 | 0% | Aug 31 2025 | Aug 31 2025 |  | Dec 15 2025 | Dec 15 2025 |  | 106 | 106 | 973.87 | 973.87 |  | 973.87 | 0% | 0% | 21%
DSFFLOW-6491 | In Progress | Core Network | EPC, IMS | Expansion | 70 | 70 | 0 | 4 | 0% | 6 | 0% | Aug 12 2025 | Aug 12 2025 | Sep 12 2025 | Oct 31 2025 | Oct 31 2025 |  | 80 | 80 | 1120 | 1120 |  | 1120 | 0% | 0% | 52% |  | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-6543 | In Progress | Core Network | UDM | Expansion | 46 | 46 | 0 | 3 | 0% | 3 | 0% | Aug 12 2025 | Aug 12 2025 | Sep 12 2025 | Dec 19 2025 | Dec 19 2025 |  | 129 | 129 | 559 | 559 |  | 559 | 0% | 0% | 32% |  | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-1809 | Assigned | Core Network | MSS, Signaling | Upgrade, Maiden Installation | 46 | 46 | 0 | 5 | 0% | 6 | 0% | Mar 03 2025 | Sep 15 2025 |  | Dec 15 2025 | Dec 31 2025 |  | 287 | 107 | 1202 | 1202 |  | 1202 | 0% | 0% | 7% |  | Amber | [Assigned] with 196 days past due start date;
DSFFLOW-325 | Assigned | Core Network | MSS | Upgrade | 34 | 34 | 0 | 1 | 0% | 4 | 0% | Apr 22 2025 | Sep 15 2025 |  | Dec 31 2026 | Dec 31 2025 |  | 618 | 107 | 512 | 512 |  | 512 | 0% | 0% | 7% |  | Amber | [Assigned] with 146 days past due start date;
DSFFLOW-2843 | In Progress | BOS | Common Services-Data Migration | Migration | 10 | 10 | 0 |  |  |  |  | Jun 16 2025 | Jun 16 2025 | Jun 17 2025 | Dec 31 2026 | Dec 31 2026 |  | 563 | 563 | 1 | 1 |  | 1 | 0% | 0% | 18% |  | Green | [In Prog]
DSFFLOW-6736 | Assigned | BOS, ISD | Common Services-Data Migration, Core Commerce, BSS Application Testing | Maiden Installation, Migration, Continuous Testing | 37 | 37 | 0 | 2 | 0% |  |  | Aug 14 2025 | Aug 14 2025 |  | Oct 30 2026 | Oct 30 2026 |  | 442 | 442 | 30409 | 30409 |  | 30409 | 0% | 0% | 9%
DSFFLOW-3630 | In Progress | Core Network | Cloud | Migration | 60 | 60 | 0 | 1 | 0% | 7 | 0% | Jul 04 2025 | Jul 04 2025 | Sep 16 2025 | Dec 31 2025 | Dec 31 2025 |  | 180 | 180 | 2549 | 2549 |  | 2549 | 0% | 0% | 45% |  | Amber | [Assigned] with 73 days past due start date;
DSFFLOW-2916 | Assigned | Core Network | MSS | Maiden Installation | 12 | 12 | 0 | 1 | 0% |  |  | May 15 2025 | May 15 2025 |  | Dec 21 2026 | Dec 21 2026 |  | 585 | 585 | 204 | 204 |  | 204 | 0% | 0% | 22% |  | Amber | [Assigned] with 123 days past due start date;
DSFFLOW-6627 | Assigned | Network Management | Element Management | Upgrade | 76 | 76 | 0 | 2 | 0% | 2 | 0% | Sep 04 2025 | Sep 04 2025 |  | Dec 31 2025 | Dec 31 2025 |  | 118 | 118 | 897.5 | 897.5 |  | 897.5 | 0% | 0% | 16%
DSFFLOW-6446 | In Progress | Core Network | UDM | Upgrade | 22 | 22 | 0 | 1 | 0% |  |  | Aug 07 2025 | Aug 07 2025 | Sep 12 2025 | Dec 12 2025 | Dec 12 2025 |  | 127 | 127 | 587.5 | 587.5 |  | 587.5 | 0% | 0% | 37% |  | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-6331 | Assigned | Core Network | MSS | Upgrade | 57 | 57 | 0 | 3 | 0% | 2 | 0% | Jul 09 2025 | Jul 09 2025 |  | Dec 31 2025 | Dec 31 2025 |  | 175 | 175 | 2185 | 2185 |  | 2185 | 0% | 0% | 43% |  | Amber | [Assigned] with 68 days past due start date;
DSFFLOW-6461 | Assigned | Core Network | MSS | Upgrade | 39 | 39 | 0 | 1 | 0% | 4 | 0% | Sep 01 2025 | Sep 01 2025 |  | Dec 31 2025 | Dec 31 2025 |  | 121 | 121 | 877 | 877 |  | 877 | 0% | 0% | 18% |  | Amber | [Assigned] with 14 days past due start date;
DSFFLOW-5009 | Assigned | Core Network | UDM | Maiden Installation | 14 | 14 | 0 | 1 | 0% | 3 | 0% | Aug 18 2025 | Aug 18 2025 |  | Dec 31 2028 | Dec 31 2028 |  | 1231 | 1231 | 220 | 220 |  | 220 | 0% | 0% | 3% |  | Amber | [Assigned] with 28 days past due start date;
DSFFLOW-5559 | Assigned | Core Network | UDM | Upgrade | 13 | 13 | 0 | 1 | 0% | 2 | 0% | Aug 14 2025 | Aug 14 2025 |  | Oct 05 2028 | Oct 05 2028 |  | 1148 | 1148 | 220 | 220 |  | 220 | 0% | 0% | 3% |  | Amber | [Assigned] with 32 days past due start date;
DSFFLOW-5812 | In Progress | Core Network | MSS | Upgrade | 216 | 216 | 0 | 1 | 0% | 50 | 0% | Sep 11 2025 | Sep 11 2025 | Sep 11 2025 | Nov 20 2025 | Nov 20 2025 |  | 70 | 70 | 1368 | 1368 |  | 1368 | 0% | 0% | 17% |  | Green | [In Prog]
DSFFLOW-5981 | In Progress | BOS | Monetization Charging | Business Configuration | 32 | 32 | 0 | 2 | 0% |  |  | Aug 03 2025 | Aug 03 2025 | Sep 12 2025 | Dec 30 2025 | Dec 30 2025 |  | 149 | 149 | 798.4 | 798.4 |  | 798.4 | 0% | 0% | 34% |  | Amber | [In Prog] time ticking without any work progress; late start;
DSFFLOW-6003 | Assigned | BOS | Monetization Billing | Upgrade, Continuous Adaptation | 60 | 60 | 0 | 1 | 0% | 5 | 0% | Jul 31 2025 | Jul 31 2025 |  | Mar 29 2026 | Mar 29 2026 |  | 241 | 241 | 15277.75 | 15277.75 |  | 15277.75 | 0% | 0% | 22% |  | Amber | [Assigned] with 46 days past due start date;
DSFFLOW-5621 | In Progress | Core Network | MSS | Upgrade | 36 | 36 | 0 | 1 | 0% | 5 | 0% | Aug 29 2025 | Aug 29 2025 | Aug 29 2025 | Dec 30 2026 | Dec 30 2026 |  | 488 | 488 | 319 | 319 |  | 319 | 0% | 0% | 5% |  | Green | [In Prog]
DSFFLOW-6476 | In Progress | Core Network | MSS | Upgrade | 12 | 12 | 0 |  |  |  |  | Aug 01 2025 | Aug 01 2025 | Sep 18 2025 | Oct 15 2025 | Oct 15 2025 |  | 75 | 75 | 220 | 220 |  | 220 | 0% | 0% | 70% |  | Amber | [Assigned] with 45 days past due start date;
DSFFLOW-6794 | Assigned | Core Network | Cloud, EPC, UDM | Upgrade | 94 | 94 | 0 | 3 | 0% | 9 | 0% | Sep 14 2025 | Sep 14 2025 |  | Feb 25 2027 | Feb 25 2027 |  | 529 | 529 | 4728.4 | 4728.4 |  | 4728.4 | 0% | 0% | 2%