## RAGStatus
DSF | Status | Domain | Sub-Domain | Plan Work | Replan Work | Closed Work | Plan Start | Replan Start | Actual Start | Plan End | Replan End | Actual End | Plan Days | Replan Days | Plan Hr | Replan Hr | Logged Hr | Work Prog | Time Prog | Effort Prog | RAG | Reason
DSFFLOW-32 | Closed | Network Management | Element Management & Reporting | 57 | 31 | 31 | 2024-12-08 | 2024-12-08 | 2024-12-09 | 2025-02-17 | 2025-02-18 | 2025-02-17 | 71 | 72 | 910 | 459 | 457 | 100% | 98% | 100% | Green | [Closed] On/ahead of schedule; Within efforts budget;
DSFFLOW-1629 | Closed | Core Network | EPC,UDM,Signaling | 175 | 175 | 105 | 2025-04-01 | 2025-04-01 | 2025-06-03 | 2025-06-29 | 2025-06-29 | 2025-07-07 | 89 | 89 | 2726 | 2726 | 2828.06 | 60% | 108% | 104% | Red | [Closed] Late start; Incomplete work; Consumed all or more effort budget;
DSFFLOW-1383 | Closed | Core Network | EPC | 63 | 63 |  | 2024-12-31 | 2024-12-31 | 2025-01-01 | 2025-06-30 | 2025-06-30 | 2025-05-27 | 181 | 181 | 952 | 952 | 952 | 0% | 81% | 100% | Red | [Closed] Incomplete work; Consumed all or more effort budget;
DSFFLOW-1200 | Closed | Network Management | Element Management & Reporting | 192 | 35 | 35 | 2025-05-08 | 2025-02-10 | 2025-04-22 | 2026-08-31 | 2025-10-31 | 2025-06-19 | 480 | 263 | 3156 | 986 | 605.5 | 100% | 49% | 62% | Amber | [Closed] Late start; Overtly buffered time plan; Inflated effort budget;
DSFFLOW-1879 | Closed | Network Management | Element Management & Reporting | 25 | 17 | 17 | 2025-05-26 | 2025-05-26 | 2025-05-26 | 2025-06-30 | 2025-06-30 | 2025-06-30 | 35 | 35 | 305 | 272 | 268.5 | 100% | 100% | 99% | Green | [Closed] On/ahead of schedule; Within efforts budget;
DSFFLOW-1135 | Closed | BOS | D&A Mediation | 34 | 34 | 34 | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-06-20 | 2025-06-20 | 2025-06-20 | 32 | 32 | 570 | 570 | 548 | 100% | 100% | 97% | Green | [Closed] On/ahead of schedule; Within efforts budget;
DSFFLOW-1026 | Closed | Network Management | Resource Orchestration | 20 | 18 | 18 | 2025-04-20 | 2025-04-20 | 2025-06-13 | 2025-06-29 | 2025-06-29 | 2025-07-09 | 70 | 70 | 278 | 261 | 260.77 | 100% | 114% | 101% | Amber | [Closed] Late start; Schedule slip > 5% tolerance;
DSFFLOW-921 | Closed | Core Network | UDM | 23 | 23 | 23 | 2025-05-09 | 2025-05-09 | 2025-05-14 | 2025-07-31 | 2025-07-31 | 2025-07-04 | 83 | 83 | 240 | 240 | 232.1 | 100% | 67% | 97% | Amber | [Closed] Overtly buffered time plan; Within efforts budget;
DSFFLOW-2560 | Closed | Network Management | Resource Orchestration | 24 | 18 | 18 | 2025-06-06 | 2025-06-06 | 2025-06-27 | 2026-01-31 | 2026-01-31 | 2025-07-07 | 239 | 239 | 222 | 222 | 222 | 100% | 13% | 100% | Amber | [Closed] Late start; Overtly buffered time plan; Within efforts budget;
DSFFLOW-401 | Closed | Core Network | EPC | 152 | 152 | 62 | 2024-07-10 | 2024-07-10 | 2025-04-30 | 2025-12-12 | 2025-12-12 | 2025-06-23 | 520 | 520 | 2112 | 2112 | 1746.1 | 40% | 66% | 83% | Red | [Closed] Late start; Incomplete work;
DSFFLOW-386 | Closed | Core Network | EPC | 30 | 30 | 30 | 2024-11-10 | 2024-11-10 | 2025-01-01 | 2025-01-26 | 2025-01-26 | 2025-06-30 | 77 | 77 | 2766 | 2766 | 994 | 100% | 298% | 36% | Amber | [Closed] Late start; Inflated effort budget; Schedule slip > 5% tolerance;
DSFFLOW-1445 | Closed | Core Network | IMS | 78 | 59 | 59 | 2025-05-27 | 2025-05-27 | 2025-05-28 | 2025-07-18 | 2025-07-04 | 2025-07-04 | 52 | 38 | 801 | 640 | 600.27 | 100% | 100% | 94% | Green | [Closed] On/ahead of schedule; Within efforts budget;
DSFFLOW-310 | Closed | Core Network | UDM | 19 | 19 | 19 | 2025-04-20 | 2025-04-20 | 2025-06-05 | 2025-05-31 | 2025-05-31 | 2025-06-05 | 41 | 41 | 267 | 267 | 315 | 100% | 112% | 118% | Red | [Closed] Late start; Schedule slip > 5% tolerance; Effort burn > 5% tolerance;
DSFFLOW-49 | Closed | Network Management | Element Management & Reporting | 30 | 30 | 30 | 2025-02-19 | 2025-02-20 | 2025-02-28 | 2025-08-29 | 2025-04-17 | 2025-03-27 | 191 | 56 | 488 | 488 | 430 | 100% | 63% | 89% | Amber | [Closed] Late start; Overtly buffered time plan; Inflated effort budget;
DSFFLOW-80 | Closed | Core Network | EPC,UDM,IMS | 176 | 150 | 150 | 2025-02-06 | 2025-02-06 | 2025-03-10 | 2025-06-06 | 2025-06-06 | 2025-06-05 | 120 | 120 | 1786 | 1786 | 1758 | 100% | 99% | 99% | Green | [Closed] Late start; On/ahead of schedule; Within efforts budget;
DSFFLOW-2123 | In Progress | Core Network,Network Management | Activation,EPC,UDM,Exposure,Core Network Automation | 76 | 76 | 7 | 2025-05-07 | 2025-05-07 | 2025-06-20 | 2026-10-30 | 2026-10-30 |  | 541 | 541 | 5608 | 5608 | 1190 | 9% | 12% | 22% | Green | [In Prog] Late start; Progress variance within control limts;
DSFFLOW-2107 | In Progress | Core Network | UDM,IMS | 90 | 90 |  | 2025-05-29 | 2025-05-29 | 2025-06-30 | 2026-02-27 | 2026-02-27 |  | 274 | 274 | 4426 | 4426 | 606.6 | 0% | 16% | 14% | Amber | [In Prog] Late start; Time ticking without any work progress;
DSFFLOW-2078 | In Progress | Core Network | EPC,IMS | 46 | 46 | 24 | 2025-04-03 | 2025-04-03 | 2025-06-17 | 2025-12-05 | 2025-12-05 |  | 246 | 246 | 2855 | 2855 | 2800 | 52% | 41% | 99% | Red | [In Prog] Late start; Efforts burnt outweigh work output;
DSFFLOW-2047 | In Progress | Network Management | Element Management & Reporting | 326 | 326 | 25 | 2025-05-08 | 2025-05-08 | 2025-06-18 | 2026-08-31 | 2026-08-31 |  | 480 | 480 | 9025 | 9025 | 191 | 8% | 13% | 3% | Green | [In Prog] Late start; Progress variance within control limts;
DSFFLOW-2765 | In Progress | Core Network | EPC,Cloud | 49 | 49 |  | 2024-11-11 | 2024-11-11 | 2025-07-07 | 2024-12-20 | 2024-12-20 |  | 39 | 39 | 1560 | 1560 |  | 0% | 612% |  | Amber | [In Prog] Late start; Time ticking without any work progress;
DSFFLOW-2009 | In Progress | Core Network | EPC,UDM,IMS,Cloud | 172 | 172 | 81 | 2025-04-29 | 2025-04-29 | 2025-06-23 | 2026-03-31 | 2026-03-31 |  | 336 | 336 | 3074 | 3074 | 1771 | 47% | 22% | 58% | Green | [In Prog] Late start; Progress variance within control limts;
DSFFLOW-1994 | In Progress | Network Management | Resource Orchestration | 39 | 38 | 4 | 2025-06-22 | 2025-06-22 | 2025-06-24 | 2025-07-10 | 2025-07-10 |  | 18 | 18 | 314 | 306 | 28 | 10% | 115% | 10% | Amber | [In Prog] Slow work progress relative to schedule;
DSFFLOW-1926 | In Progress | Core Network | Cloud | 97 | 97 | 2 | 2025-05-26 | 2025-05-26 | 2025-07-10 | 2026-12-31 | 2026-12-31 |  | 584 | 584 | 2189 | 2189 | 327.6 | 2% | 8% | 15% | Green | [In Prog] Late start; Progress variance within control limts;
DSFFLOW-1911 | In Progress | Core Network | EPC | 41 | 41 |  | 2025-04-03 | 2025-04-03 | 2025-06-13 | 2025-09-29 | 2025-09-29 |  | 179 | 179 | 3433 | 3433 | 1279 | 0% | 57% | 38% | Red | [In Prog] Late start; Efforts burning without any work progress; Time ticking without any work progress;
DSFFLOW-1894 | In Progress | Core Network | EPC | 25 | 25 | 1 | 2024-12-31 | 2024-12-31 | 2025-06-26 | 2025-12-30 | 2025-12-30 |  | 364 | 364 | 1584 | 1584 | 688 | 4% | 53% | 44% | Red | [In Prog] Late start; Efforts burnt outweigh work output; Slow work progress relative to schedule;
DSFFLOW-2656 | In Progress | Network Management | Element Management & Reporting | 98 | 98 | 12 | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-12-19 | 2025-12-19 |  | 171 | 171 | 2840 | 2840 | 234.7 | 12% | 8% | 9% | Green | [In Prog] Progress variance within control limts;
DSFFLOW-2169 | In Progress | Core Network | EPC,UDM,Signaling | 327 | 327 |  | 2025-06-15 | 2025-06-15 | 2025-06-24 | 2027-08-20 | 2027-08-20 |  | 796 | 796 | 29309 | 29309 | 0.11 | 0% | 3% | 1% | Green | [In Prog] Late start; Progress variance within control limts;
DSFFLOW-1864 | In Progress | Network Management | Element Management & Reporting | 35 | 35 | 32 | 2025-06-09 | 2025-06-09 | 2025-06-18 | 2025-12-31 | 2025-12-31 |  | 205 | 205 | 506 | 506 | 343 | 91% | 16% | 68% | Green | [In Prog] Late start; Progress variance within control limts;
DSFFLOW-1840 | In Progress | Network Management | Element Management & Reporting | 1221 | 1221 | 282 | 2025-06-08 | 2025-06-08 | 2025-06-23 | 2025-11-29 | 2025-11-29 |  | 174 | 174 | 17156 | 17156 | 2501.34 | 23% | 20% | 15% | Green | [In Prog] Late start; Progress variance within control limts;
DSFFLOW-1790 | In Progress | Core Network | Cloud | 85 | 85 | 19 | 2025-06-02 | 2025-06-02 | 2025-07-10 | 2026-03-31 | 2026-03-31 |  | 302 | 302 | 726 | 726 | 140 | 22% | 13% | 20% | Green | [In Prog] Late start; Progress variance within control limts;
DSFFLOW-1745 | In Progress | Core Network,Network Management | Resource Orchestration,EPC,UDM,Exposure | 101 | 101 | 13 | 2025-06-04 | 2025-06-04 | 2025-06-06 | 2025-08-30 | 2025-08-30 |  | 87 | 87 | 1424 | 1424 | 574 | 12% | 45% | 41% | Red | [In Prog] Efforts burnt outweigh work output; Slow work progress relative to schedule;
DSFFLOW-1729 | In Progress | Network Management | Element Management & Reporting | 67 | 67 | 4 | 2025-05-07 | 2025-05-07 | 2025-06-09 | 2025-10-31 | 2025-10-31 |  | 177 | 177 | 1208 | 1208 | 148 | 5% | 38% | 13% | Amber | [In Prog] Late start; Slow work progress relative to schedule;
DSFFLOW-1697 | In Progress | Core Network | EPC | 30 | 21 | 9 | 2025-05-26 | 2025-05-26 | 2025-06-12 | 2025-08-31 | 2025-08-31 |  | 97 | 97 | 346 | 346 | 310 | 42% | 50% | 90% | Red | [In Prog] Late start; Efforts burnt outweigh work output;
DSFFLOW-2901 | In Progress | Network Management | Resource Orchestration | 34 | 33 | 7 | 2025-06-01 | 2025-06-01 | 2025-07-08 | 2025-08-30 | 2025-08-30 |  | 90 | 90 | 778 | 778 | 45.5 | 21% | 47% | 6% | Amber | [In Prog] Late start; Slow work progress relative to schedule;
DSFFLOW-1614 | In Progress | Network Management | Resource Orchestration | 54 | 54 | 53 | 2025-05-28 | 2025-05-28 | 2025-06-04 | 2026-01-30 | 2026-01-30 |  | 247 | 247 | 300 | 300 | 315.14 | 98% | 18% | 106% | Red | [In Prog] Effort budget already exceeded;
DSFFLOW-1584 | In Progress | Core Network,Network Management | Activation,Resource Orchestration,EPC,UDM,IMS,Core Network Automation | 41 | 41 | 5 | 2025-05-12 | 2025-05-12 | 2025-05-12 | 2025-08-15 | 2025-08-15 |  | 95 | 95 | 2458 | 2458 | 1292 | 12% | 65% | 53% | Red | [In Prog] Efforts burnt outweigh work output; Slow work progress relative to schedule;
DSFFLOW-2813 | In Progress | Network Management | Resource Orchestration | 11 | 11 |  | 2025-05-04 | 2025-05-04 | 2025-07-10 | 2026-03-31 | 2026-03-31 |  | 331 | 331 | 1125 | 1125 | 241 | 0% | 21% | 22% | Red | [In Prog] Late start; Efforts burning without any work progress; Time ticking without any work progress;
DSFFLOW-2882 | In Progress | BOS | D&A Mediation,Monetization Billing | 37 | 37 |  | 2025-05-10 | 2025-05-10 | 2025-07-10 | 2025-11-18 | 2025-11-18 |  | 192 | 192 | 2845 | 2845 | 51 | 0% | 33% | 2% | Amber | [In Prog] Late start; Time ticking without any work progress;
DSFFLOW-2750 | In Progress | Core Network | IMS | 189 | 189 | 4 | 2025-06-24 | 2025-06-24 | 2025-07-09 | 2025-12-26 | 2025-12-26 |  | 185 | 185 | 6009 | 6009 | 284 | 2% | 10% | 5% | Green | [In Prog] Late start; Progress variance within control limts;
DSFFLOW-2234 | In Progress | Network Management | Element Management & Reporting | 38 | 38 | 11 | 2025-06-17 | 2025-06-17 | 2025-06-30 | 2025-10-31 | 2025-10-31 |  | 136 | 136 | 652 | 652 | 172 | 29% | 19% | 27% | Green | [In Prog] Late start; Progress variance within control limts;
DSFFLOW-2641 | In Progress | Network Management | Element Management & Reporting | 24 | 24 | 3 | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-09-29 | 2025-09-29 |  | 90 | 90 | 850 | 850 | 113.7 | 12% | 15% | 14% | Green | [In Prog] Progress variance within control limts;
DSFFLOW-2625 | In Progress | Core Network | IMS | 30 | 30 | 4 | 2025-06-29 | 2025-06-29 | 2025-06-30 | 2025-07-31 | 2025-07-22 | 2025-07-22 | 32 | 23 | 267 | 267 | 58.25 | 13% | 100% | 22% | Amber | [In Prog] Slow work progress relative to schedule;
DSFFLOW-2610 | In Progress | Core Network | Signaling | 11 | 11 |  | 2025-06-27 | 2025-06-27 | 2025-07-02 | 2025-12-31 | 2025-12-31 |  | 187 | 187 | 605 | 605 | 120 | 0% | 9% | 20% | Red | [In Prog] Efforts burning without any work progress;
DSFFLOW-2674 | In Progress | Core Network | EPC | 41 | 41 |  | 2024-05-01 | 2024-05-01 | 2025-07-10 | 2025-09-30 | 2025-09-30 |  | 517 | 517 | 1454 | 1454 |  | 0% | 84% |  | Amber | [In Prog] Late start; Time ticking without any work progress;
DSFFLOW-2708 | In Progress | Core Network | Signaling,Cloud | 14 | 14 |  | 2025-06-01 | 2025-06-01 | 2025-07-04 | 2025-10-31 | 2025-10-31 |  | 152 | 152 | 315 | 315 | 13 | 0% | 29% | 5% | Amber | [In Prog] Late start; Time ticking without any work progress;
DSFFLOW-2593 | In Progress | Core Network | EPC | 16 | 16 |  | 2025-05-25 | 2025-05-25 | 2025-07-02 | 2025-12-31 | 2025-12-31 |  | 220 | 220 | 2581 | 2581 | 419 | 0% | 22% | 17% | Red | [In Prog] Late start; Efforts burning without any work progress; Time ticking without any work progress;
DSFFLOW-2724 | In Progress | Core Network,Network Management | Resource Orchestration,EPC,UDM,IMS,MSS,Core Network Automation | 38 | 38 |  | 2025-06-01 | 2025-06-01 | 2025-07-07 | 2025-09-29 | 2025-09-29 |  | 120 | 120 | 8513 | 8513 | 72 | 0% | 35% | 1% | Amber | [In Prog] Late start; Time ticking without any work progress;
DSFFLOW-2544 | In Progress | Core Network | Cloud-3PP/MPBN | 78 | 78 |  | 2025-04-19 | 2025-04-19 | 2025-06-26 | 2025-10-31 | 2025-10-31 |  | 195 | 195 | 8303 | 8303 |  | 0% | 43% |  | Amber | [In Prog] Late start; Time ticking without any work progress;
DSFFLOW-2529 | In Progress | Core Network | EPC,UDM,IMS,MSS,Cloud | 15 | 15 |  | 2025-06-24 | 2025-06-24 | 2025-06-26 | 2025-08-29 | 2025-08-29 |  | 66 | 66 | 2325 | 2325 | 1797 | 0% | 29% | 78% | Red | [In Prog] Efforts burning without any work progress; Time ticking without any work progress;
DSFFLOW-2497 | In Progress | Core Network,Network Management | Activation,Resource Orchestration,EPC | 96 | 96 | 14 | 2025-05-29 | 2025-05-29 | 2025-06-27 | 2026-02-27 | 2026-02-27 |  | 274 | 274 | 2112 | 2112 | 466 | 15% | 16% | 23% | Green | [In Prog] Late start; Progress variance within control limts;
DSFFLOW-2219 | In Progress | Core Network | Cloud | 24 | 24 |  | 2025-06-09 | 2025-06-09 | 2025-06-18 | 2025-12-12 | 2025-12-12 |  | 186 | 186 | 518 | 518 | 172.75 | 0% | 18% | 34% | Red | [In Prog] Late start; Efforts burning without any work progress; Time ticking without any work progress;
DSFFLOW-2482 | In Progress | Core Network | EPC | 24 | 24 |  | 2025-06-09 | 2025-06-09 | 2025-06-24 | 2025-12-12 | 2025-12-12 |  | 186 | 186 | 816 | 816 | 141 | 0% | 18% | 18% | Red | [In Prog] Late start; Efforts burning without any work progress; Time ticking without any work progress;
DSFFLOW-2452 | In Progress | Network Management | Resource Orchestration | 44 | 44 | 1 | 2025-05-29 | 2025-05-29 | 2025-07-11 | 2026-02-27 | 2026-02-27 |  | 274 | 274 | 1157 | 1157 | 74 | 2% | 16% | 7% | Green | [In Prog] Late start; Progress variance within control limts;
DSFFLOW-2435 | In Progress | Core Network | EPC | 16 | 16 |  | 2025-06-16 | 2025-06-16 | 2025-07-07 | 2025-06-30 | 2025-06-30 |  | 14 | 14 | 558 | 558 | 272 | 0% | 186% | 49% | Red | [In Prog] Late start; Efforts burning without any work progress; Time ticking without any work progress;
DSFFLOW-2402 | In Progress | BOS | Monetization Charging | 169 | 169 | 24 | 2025-05-05 | 2025-05-05 | 2025-07-08 | 2026-06-29 | 2026-06-29 |  | 420 | 420 | 18648 | 18648 | 24 | 15% | 16% | 1% | Green | [In Prog] Late start; Progress variance within control limts;
DSFFLOW-2384 | In Progress | Network Management | Resource Orchestration | 12 | 12 |  | 2025-06-16 | 2025-06-16 | 2025-06-24 | 2026-06-30 | 2026-06-30 |  | 379 | 379 | 1531 | 1531 | 452.5 | 0% | 8% | 30% | Red | [In Prog] Late start; Efforts burning without any work progress;
DSFFLOW-2368 | In Progress | Network Management | Activation,Resource Orchestration | 34 | 34 | 15 | 2025-06-01 | 2025-06-01 | 2025-06-20 | 2033-08-31 | 2033-08-31 |  | 3013 | 3013 | 767 | 767 | 431.7 | 44% | 1% | 57% | Green | [In Prog] Late start; Progress variance within control limts;
DSFFLOW-2352 | In Progress | Core Network | Signaling | 26 | 26 |  | 2025-06-02 | 2025-06-02 | 2025-06-27 | 2025-07-04 | 2025-07-04 |  | 32 | 32 | 360 | 360 | 30 | 0% | 127% | 9% | Amber | [In Prog] Late start; Time ticking without any work progress;
DSFFLOW-1568 | In Progress | BOS | D&A Mediation | 33 | 33 | 2 | 2025-05-25 | 2025-05-25 | 2025-06-30 | 2025-08-28 | 2025-08-28 |  | 95 | 95 | 3229 | 3229 | 280.45 | 6% | 52% | 9% | Amber | [In Prog] Late start; Slow work progress relative to schedule;
DSFFLOW-2321 | In Progress | Core Network | Exposure | 51 | 51 | 1 | 2025-06-02 | 2025-06-02 | 2025-06-19 | 2025-08-29 | 2025-08-29 |  | 88 | 88 | 882 | 882 | 140.25 | 1% | 47% | 16% | Amber | [In Prog] Late start; Slow work progress relative to schedule;
DSFFLOW-2264 | In Progress | BOS | Monetization Charging | 571 | 571 |  | 2025-05-14 | 2025-05-14 | 2025-06-20 | 2026-04-03 | 2026-04-03 |  | 324 | 324 | 5198 | 5198 |  | 0% | 18% |  | Amber | [In Prog] Late start; Time ticking without any work progress;
DSFFLOW-2249 | In Progress | BOS | Monetization Charging | 396 | 396 | 1 | 2025-06-22 | 2025-06-22 | 2025-06-27 | 2025-09-19 | 2025-09-19 |  | 89 | 89 | 3684 | 3684 | 255 | 0% | 24% | 7% | Amber | [In Prog] Time ticking without any work progress;
DSFFLOW-2467 | In Progress | BOS | D&A Mediation | 25 | 25 |  | 2025-06-11 | 2025-06-11 | 2025-06-26 | 2025-11-30 | 2025-11-30 |  | 172 | 172 | 1233 | 1233 | 263 | 0% | 19% | 22% | Red | [In Prog] Late start; Efforts burning without any work progress; Time ticking without any work progress;
DSFFLOW-2336 | In Progress | Core Network | Signaling | 26 | 26 |  | 2025-06-02 | 2025-06-02 | 2025-06-27 | 2025-07-04 | 2025-07-04 |  | 32 | 32 | 365 | 365 | 35 | 0% | 127% | 10% | Amber | [In Prog] Late start; Time ticking without any work progress;
DSFFLOW-1599 | In Progress | Network Management | Element Management & Reporting | 63 | 63 | 5 | 2025-05-15 | 2025-05-15 | 2025-06-24 | 2025-08-29 | 2025-08-29 |  | 106 | 106 | 1072 | 1072 | 120 | 8% | 57% | 12% | Amber | [In Prog] Late start; Slow work progress relative to schedule;
DSFFLOW-741 | In Progress | Network Management | Element Management & Reporting | 159 | 159 | 108 | 2025-04-22 | 2025-04-22 | 2025-05-19 | 2025-08-31 | 2025-08-31 |  | 131 | 131 | 4986 | 4986 | 3574.83 | 67% | 62% | 72% | Green | [In Prog] Late start; Progress variance within control limts;
DSFFLOW-115 | In Progress | Network Management | Element Management & Reporting | 192 | 192 | 72 | 2025-03-16 | 2025-03-17 | 2025-03-27 | 2025-06-29 | 2025-08-29 |  | 105 | 165 | 3382 | 3382 | 1922.04 | 37% | 71% | 57% | Amber | [In Prog] Late start; Slow work progress relative to schedule;
DSFFLOW-952 | In Progress | Core Network | UDM | 14 | 13 | 2 | 2025-05-12 | 2025-05-12 | 2025-05-12 | 2025-06-29 | 2025-06-29 |  | 48 | 48 | 531 | 531 | 350.75 | 15% | 128% | 67% | Red | [In Prog] Efforts burnt outweigh work output; Slow work progress relative to schedule;
DSFFLOW-133 | In Progress | BOS | Core Commerce | 423 | 423 | 71 | 2025-03-17 | 2025-03-17 | 2025-04-09 | 2025-06-30 | 2025-08-15 |  | 105 | 151 | 3067 | 3067 | 765 | 16% | 78% | 25% | Amber | [In Prog] Late start; Slow work progress relative to schedule;
DSFFLOW-151 | In Progress | Network Management | Element Management & Reporting | 87 | 86 | 40 | 2025-04-13 | 2025-04-13 | 2025-04-13 | 2025-07-30 | 2025-07-30 |  | 108 | 108 | 1719 | 1711 | 838 | 46% | 84% | 49% | Amber | [In Prog] Slow work progress relative to schedule;
DSFFLOW-168 | In Progress | BOS | Monetization Charging | 59 | 59 | 34 | 2025-03-21 | 2025-03-18 | 2025-03-18 | 2025-09-03 | 2025-09-03 |  | 166 | 169 | 791 | 791 | 641 | 57% | 69% | 82% | Red | [In Prog] Efforts burnt outweigh work output;
DSFFLOW-862 | In Progress | Core Network | MSS | 63 | 63 | 8 | 2025-05-05 | 2025-05-05 | 2025-05-19 | 2025-12-31 | 2025-12-31 |  | 240 | 240 | 2475 | 2475 | 892 | 12% | 29% | 37% | Red | [In Prog] Late start; Efforts burnt outweigh work output;
DSFFLOW-206 | In Progress | Core Network | IMS | 214 | 206 | 60 | 2025-02-16 | 2025-02-16 | 2025-04-22 | 2025-12-18 | 2025-12-18 |  | 305 | 305 | 3892 | 3892 | 1756.7 | 29% | 48% | 46% | Green | [In Prog] Late start; Progress variance within control limts;
DSFFLOW-798 | In Progress | Core Network | Cloud | 77 | 77 |  | 2025-05-05 | 2025-04-01 | 2025-06-03 | 2025-12-30 | 2026-03-20 |  | 239 | 353 | 8456 | 8456 | 385.75 | 0% | 29% | 5% | Amber | [In Prog] Late start; Time ticking without any work progress;
DSFFLOW-760 | In Progress | BOS | Monetization Charging,D&A Mediation | 2546 | 2546 | 325 | 2025-04-08 | 2025-04-08 | 2025-05-12 | 2026-04-20 | 2026-04-20 |  | 377 | 377 | 30977 | 30977 | 5091.7 | 12% | 25% | 17% | Green | [In Prog] Late start; Progress variance within control limts;
DSFFLOW-1416 | In Progress | Core Network,Network Management | Activation,EPC,UDM,IMS,MSS | 153 | 153 | 7 | 2025-04-23 | 2025-04-23 | 2025-05-27 | 2025-12-31 | 2025-12-31 |  | 252 | 252 | 9050 | 9050 | 995.51 | 4% | 32% | 12% | Amber | [In Prog] Late start; Slow work progress relative to schedule;
DSFFLOW-677 | In Progress | Core Network | IMS | 101 | 101 | 64 | 2025-04-24 | 2025-04-24 | 2025-04-14 | 2025-12-31 | 2025-12-31 | 2025-09-30 | 251 | 251 | 1584 | 1584 | 990 | 63% | 63% | 63% | Green | [In Prog] Early start; Progress variance within control limts;
DSFFLOW-662 | In Progress | Network Management | Resource Orchestration | 63 | 62 | 1 | 2025-03-04 | 2025-03-04 | 2025-06-05 | 2026-12-31 | 2026-12-31 |  | 667 | 667 | 915 | 915 | 253.27 | 1% | 19% | 28% | Red | [In Prog] Late start; Efforts burnt outweigh work output;
DSFFLOW-245 | In Progress | Network Management | Element Management & Reporting | 869 | 599 | 7 | 2025-04-09 | 2025-04-09 |  | 2025-08-29 | 2025-08-29 |  | 142 | 142 | 24213 | 17728 | 1708 | 1% | 67% | 10% | Amber | [In Prog] Slow work progress relative to schedule;
DSFFLOW-591 | In Progress | Core Network | Cloud-3PP/MPBN | 30 | 30 | 8 | 2025-04-22 | 2025-04-22 | 2025-06-05 | 2025-06-30 | 2025-06-30 |  | 69 | 69 | 850 | 850 | 229.5 | 26% | 118% | 27% | Amber | [In Prog] Late start; Slow work progress relative to schedule;
DSFFLOW-576 | In Progress | BOS | Monetization Billing | 31 | 31 | 9 | 2025-03-03 | 2025-03-03 | 2025-05-13 | 2025-08-14 | 2025-08-14 |  | 164 | 164 | 6866 | 6866 | 3105.2 | 29% | 80% | 46% | Amber | [In Prog] Late start; Slow work progress relative to schedule;
DSFFLOW-550 | In Progress | Network Management | Element Management & Reporting | 42 | 42 | 39 | 2025-04-30 | 2025-04-07 | 2025-07-02 | 2026-02-27 | 2025-07-23 |  | 303 | 107 | 614 | 614 | 598 | 92% | 90% | 98% | Green | [In Prog] Late start; Progress variance within control limts;
DSFFLOW-535 | In Progress | Core Network | EPC | 14 | 14 | 13 | 2025-01-01 | 2024-12-31 | 2025-01-01 | 2025-07-31 | 2025-05-29 | 2025-04-30 | 211 | 149 | 149 | 149 | 206 | 92% | 80% | 139% | Red | [In Prog] Effort budget already exceeded;
DSFFLOW-447 | In Progress | BOS | Monetization Billing | 36 | 36 | 12 | 2025-04-01 | 2025-04-01 | 2025-05-20 | 2025-12-05 | 2025-12-05 |  | 248 | 248 | 10327 | 10327 | 3981.4 | 33% | 41% | 39% | Green | [In Prog] Late start; Progress variance within control limts;
DSFFLOW-507 | In Progress | Network Management | Element Management & Reporting | 527 | 527 | 115 | 2025-02-28 | 2025-03-01 | 2025-06-26 | 2025-07-30 | 2025-06-30 |  | 152 | 121 | 6645 | 6645 | 1980.5 | 21% | 111% | 30% | Amber | [In Prog] Late start; Slow work progress relative to schedule;
DSFFLOW-477 | In Progress | Core Network | EPC | 76 | 76 | 29 | 2024-11-08 | 2024-11-08 | 2025-04-29 | 2026-02-28 | 2026-02-28 |  | 477 | 477 | 2868 | 2868 | 2014 | 38% | 51% | 71% | Red | [In Prog] Late start; Efforts burnt outweigh work output;
DSFFLOW-1008 | In Progress | Network Management | Resource Orchestration | 25 | 25 | 14 | 2025-04-29 | 2025-04-29 | 2025-06-18 | 2025-07-30 | 2025-07-30 |  | 92 | 92 | 285 | 285 | 279 | 57% | 81% | 98% | Red | [In Prog] Late start; Efforts burnt outweigh work output; Slow work progress relative to schedule;
DSFFLOW-462 | In Progress | Core Network | MSS | 28 | 28 | 10 | 2025-03-17 | 2025-03-17 | 2025-04-30 | 2025-06-30 | 2025-06-30 |  | 105 | 105 | 469 | 469 | 384 | 35% | 113% | 82% | Red | [In Prog] Late start; Efforts burnt outweigh work output; Slow work progress relative to schedule;
DSFFLOW-64 | In Progress | Network Management | Element Management & Reporting | 47 | 47 | 24 | 2025-03-02 | 2025-03-02 | 2025-03-13 | 2025-08-30 | 2025-08-30 |  | 181 | 181 | 1240 | 1240 | 802.51 | 51% | 73% | 65% | Amber | [In Prog] Late start; Slow work progress relative to schedule;
DSFFLOW-1087 | In Progress | Network Management | Element Management & Reporting | 58 | 58 | 4 | 2025-05-14 | 2025-05-14 | 2025-05-17 | 2025-11-29 | 2025-11-29 |  | 199 | 199 | 972 | 972 | 219.5 | 6% | 30% | 23% | Amber | [In Prog] Slow work progress relative to schedule;
DSFFLOW-1103 | In Progress | Core Network,Network Management | Resource Orchestration,EPC | 44 | 44 | 26 | 2025-05-16 | 2025-05-16 | 2025-05-19 | 2025-08-30 | 2025-08-30 |  | 106 | 106 | 938 | 938 | 882.15 | 59% | 56% | 95% | Red | [In Prog] Efforts burnt outweigh work output;
DSFFLOW-1400 | In Progress | Core Network | EPC | 37 | 37 | 5 | 2023-05-22 | 2023-05-22 | 2025-05-27 | 2025-07-30 | 2025-07-30 |  | 800 | 800 | 1432 | 1432 | 376 | 13% | 97% | 27% | Amber | [In Prog] Late start; Slow work progress relative to schedule;
DSFFLOW-1368 | In Progress | Core Network | EPC | 21 | 21 |  | 2025-05-23 | 2025-05-23 | 2025-06-25 | 2025-12-31 | 2025-12-31 |  | 222 | 222 | 1215 | 1215 | 672.03 | 0% | 23% | 56% | Red | [In Prog] Late start; Efforts burning without any work progress; Time ticking without any work progress;
DSFFLOW-1151 | In Progress | BOS | Monetization Charging | 498 | 498 | 1 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2026-02-28 | 2026-02-28 |  | 272 | 272 | 3023 | 3023 | 57.5 | 0% | 15% | 2% | Green | [In Prog] Progress variance within control limts;
DSFFLOW-1166 | In Progress | Core Network | Cloud | 70 | 70 | 17 | 2025-05-19 | 2025-05-19 | 2025-06-06 | 2025-12-30 | 2025-12-30 |  | 225 | 225 | 1196 | 1196 | 484.6 | 24% | 24% | 41% | Green | [In Prog] Late start; Progress variance within control limts;
DSFFLOW-1337 | In Progress | BOS | Monetization Charging | 338 | 338 | 5 | 2025-04-14 | 2025-04-14 | 2025-05-30 | 2026-10-30 | 2026-10-30 |  | 564 | 564 | 5063 | 5063 | 377.5 | 1% | 16% | 8% | Green | [In Prog] Late start; Progress variance within control limts;
DSFFLOW-97 | In Progress | Network Management | Element Management & Reporting | 50 | 47 | 32 | 2025-03-12 | 2025-03-12 | 2025-03-13 | 2025-05-31 | 2025-07-31 |  | 80 | 141 | 826 | 784 | 553.25 | 68% | 87% | 71% | Green | [In Prog] Progress variance within control limts;
DSFFLOW-1247 | In Progress | Core Network | EPC,UDM,IMS | 168 | 168 |  | 2025-05-06 | 2025-05-06 |  | 2025-12-31 | 2025-12-31 |  | 239 | 239 | 2729 | 2729 | 577.25 | 0% | 29% | 22% | Red | [In Prog] Efforts burning without any work progress; Time ticking without any work progress;
DSFFLOW-1263 | In Progress | Core Network | EPC | 36 | 36 | 8 | 2025-05-11 | 2025-05-11 | 2025-07-11 | 2025-08-01 | 2025-08-01 |  | 82 | 82 | 871 | 871 | 380.75 | 22% | 77% | 44% | Red | [In Prog] Late start; Efforts burnt outweigh work output; Slow work progress relative to schedule;
DSFFLOW-1278 | In Progress | Core Network | IMS | 312 | 309 | 65 | 2025-05-08 | 2025-05-08 | 2025-05-22 | 2025-09-15 | 2025-09-15 |  | 130 | 130 | 4282 | 4282 | 1839.05 | 21% | 51% | 43% | Red | [In Prog] Late start; Efforts burnt outweigh work output; Slow work progress relative to schedule;
DSFFLOW-1041 | In Progress | Core Network | IMS | 17 | 13 | 6 | 2025-05-14 | 2025-05-14 | 2025-05-16 | 2027-04-30 | 2027-04-30 | 2025-06-27 | 716 | 716 | 716 | 716 | 640 | 46% | 6% | 90% | Red | [In Prog] Efforts burnt outweigh work output;
DSFFLOW-1307 | In Progress | BOS | Monetization Charging | 161 | 161 | 69 | 2025-05-11 | 2025-05-11 | 2025-05-11 | 2025-08-21 | 2025-08-21 |  | 102 | 102 | 2949 | 2949 | 870.5 | 42% | 62% | 30% | Amber | [In Prog] Slow work progress relative to schedule;
DSFFLOW-1646 | On Hold | Network Management | Element Management & Reporting | 67 | 67 | 21 | 2025-05-27 | 2025-05-27 | 2025-06-09 | 2025-08-29 | 2025-08-29 |  | 94 | 94 | 1440 | 1440 | 454.01 | 31% | 50% | 32% | Green | [Hold] Late start; Progress variance within control limts;
DSFFLOW-1662 | On Hold | Network Management | Element Management & Reporting | 67 | 67 | 20 | 2025-05-07 | 2025-05-07 | 2025-06-06 | 2025-07-31 | 2025-07-31 |  | 85 | 85 | 1440 | 1440 | 438 | 29% | 79% | 31% | Amber | [Hold] Late start; Slow work progress relative to schedule;
DSFFLOW-1057 | On Hold | Core Network | EPC | 86 | 86 | 2 | 2025-05-07 | 2025-05-07 | 2025-05-16 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 268 | 268 | 3894 | 3894 | 238.04 | 2% | 100% | 7% | Amber | [Hold] Late start; Slow work progress relative to schedule;
DSFFLOW-2138 | On Hold | Network Management | Resource Orchestration | 52 | 50 | 7 | 2025-06-12 | 2025-06-12 | 2025-06-18 | 2025-12-31 | 2025-12-31 |  | 202 | 202 | 641 | 641 | 191.3 | 15% | 15% | 30% | Green | [Hold] Progress variance within control limts;
DSFFLOW-325 | Assigned | Core Network | MSS | 34 | 34 |  | 2025-04-22 | 2025-04-22 |  | 2026-12-31 | 2026-12-31 |  | 618 | 618 | 512 | 512 | 40 | 0% | 13% | 8% | Red | [Assigned] with no work done; efforts burnt; 82 days past due start date;
DSFFLOW-2916 | Assigned | Core Network | MSS | 12 | 12 |  | 2025-05-15 | 2025-05-15 |  | 2026-12-21 | 2026-12-21 |  | 585 | 585 | 204 | 204 |  | 0% | 10% |  | Amber | [Assigned] with no work done; 59 days past due start date;
DSFFLOW-2931 | Assigned | Network Management | Activation | 46 | 46 |  | 2025-06-08 | 2025-06-08 |  | 2025-12-30 | 2025-12-30 |  | 205 | 205 | 1062 | 1062 |  | 0% | 17% |  | Amber | [Assigned] with no work done; 35 days past due start date;
DSFFLOW-2858 | Assigned | BOS | Monetization Charging | 34 | 34 |  | 2025-05-09 | 2025-05-09 |  | 2025-07-09 | 2025-07-09 |  | 61 | 61 | 465 | 465 |  | 0% | 106% |  | Amber | [Assigned] with no work done; 65 days past due start date;
DSFFLOW-2947 | Assigned | Core Network | MSS | 21 | 21 |  | 2025-03-18 | 2025-03-18 |  | 2025-08-15 | 2025-08-15 |  | 150 | 150 | 412 | 412 |  | 0% | 78% |  | Amber | [Assigned] with no work done; 117 days past due start date;
DSFFLOW-2843 | Assigned | BOS | Common Services-Data Migration | 10 | 10 |  | 2025-06-16 | 2025-06-16 |  | 2026-12-31 | 2026-12-31 |  | 563 | 563 | 1 | 1 |  | 0% | 4% |  | Amber | [Assigned] with no work done; 27 days past due start date;
DSFFLOW-2689 | Assigned | Network Management | Element Management & Reporting | 119 | 119 |  | 2025-06-23 | 2025-06-23 |  | 2026-03-31 | 2026-03-31 |  | 281 | 281 | 1645 | 1645 |  | 0% | 8% |  | Amber | [Assigned] with no work done; 20 days past due start date;
DSFFLOW-2828 | Assigned | Core Network | UDM | 15 | 15 |  | 2025-07-14 | 2025-07-14 |  | 2025-11-28 | 2025-11-28 |  | 137 | 137 | 593 | 593 |  | 0% | 0% |  | Green | [Assigned] with 1 days left to start;
DSFFLOW-3010 | Assigned | Core Network | Cloud | 47 | 47 |  | 2025-07-04 | 2025-07-04 |  | 2025-12-31 | 2025-12-31 |  | 180 | 180 | 1803 | 1803 |  | 0% | 5% |  | Amber | [Assigned] with no work done; 9 days past due start date;
DSFFLOW-2513 | Assigned | Core Network | EPC,Signaling | 46 | 46 |  | 2024-07-25 | 2024-07-25 |  | 2025-12-31 | 2025-12-31 |  | 524 | 524 | 1896 | 1896 |  | 0% | 67% |  | Amber | [Assigned] with no work done; 353 days past due start date;
DSFFLOW-2962 | Assigned | Core Network | Cloud | 101 | 101 |  | 2025-07-07 | 2025-07-07 |  | 2025-12-30 | 2025-12-30 |  | 176 | 176 | 1816 | 1816 | 0 | 0% | 3% | 0% | Amber | [Assigned] with no work done; 6 days past due start date;
DSFFLOW-1679 | Assigned | Core Network | Cloud-3PP/MPBN | 30 | 30 |  | 2025-05-16 | 2025-05-16 |  | 2026-12-31 | 2026-12-31 |  | 594 | 594 | 1089 | 1089 |  | 0% | 9% |  | Amber | [Assigned] with no work done; 58 days past due start date;
DSFFLOW-611 | Assigned | Core Network | EPC | 58 | 58 |  | 2025-02-10 | 2025-02-10 |  | 2025-12-31 | 2025-12-31 |  | 324 | 324 | 2055 | 2055 | 353 | 0% | 47% | 18% | Red | [Assigned] with no work done; efforts burnt; 153 days past due start date;
DSFFLOW-2419 | Assigned | Core Network | IMS | 52 | 52 |  | 2025-06-05 | 2025-06-05 |  | 2025-06-26 | 2025-06-26 |  | 21 | 21 | 322 | 322 |  | 0% | 177% |  | Amber | [Assigned] with no work done; 38 days past due start date;
DSFFLOW-1713 | Assigned | Core Network | UDM | 18 | 18 |  | 2025-03-15 | 2025-03-15 |  | 2025-07-30 | 2025-07-30 |  | 137 | 137 | 2328 | 2328 | 272 | 0% | 87% | 12% | Red | [Assigned] with no work done; efforts burnt; 120 days past due start date;
DSFFLOW-1809 | Assigned | Core Network | MSS,Signaling | 46 | 46 |  | 2025-03-03 | 2025-03-03 |  | 2025-12-15 | 2025-12-15 |  | 287 | 287 | 1202 | 1202 |  | 0% | 46% |  | Amber | [Assigned] with no work done; 132 days past due start date;
DSFFLOW-2575 | Assigned | Core Network | Cloud | 32 | 32 |  | 2025-06-23 | 2025-06-23 |  | 2025-12-01 | 2025-12-01 |  | 161 | 161 | 1262 | 1262 |  | 0% | 12% |  | Amber | [Assigned] with no work done; 20 days past due start date;
DSFFLOW-970 | Assigned | Core Network | Cloud-3PP/MPBN | 27 | 27 |  | 2025-05-08 | 2025-05-08 |  | 2025-07-29 | 2025-07-29 |  | 82 | 82 | 661 | 661 | 8.5 | 0% | 80% | 2% | Red | [Assigned] with no work done; efforts burnt; 66 days past due start date;
DSFFLOW-993 | Assigned | Core Network | UDM | 40 | 40 | 2 | 2025-02-10 | 2025-02-10 | 2025-02-10 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 324 | 324 | 1955 | 1955 | 845 | 5% | 100% | 44% | Red | [Assigned] with work being done; efforts burnt; 153 days past due start date;
DSFFLOW-1322 | Backlog | Core Network | EPC,UDM,Exposure | 88 | 88 | 13 | 2025-04-22 | 2025-04-22 |  | 2026-12-31 | 2026-12-31 |  | 618 | 618 | 1663 | 1663 | 1007.5 | 15% | 13% | 61% | Red | [Backlog] with work being done; efforts burnt; 82 days past due start date;
DSFFLOW-1223 | Backlog | Core Network | EPC,UDM,Signaling | 166 | 166 | 1 | 2025-05-09 | 2025-05-09 |  | 2025-12-31 | 2025-12-31 |  | 236 | 236 | 33976 | 33976 | 1129 | 0% | 27% | 4% | Red | [Backlog] with no work done; efforts burnt; 65 days past due start date;
DSFFLOW-1119 | Backlog | Network Management | Element Management & Reporting | 161 | 161 |  | 2025-05-15 | 2025-05-15 |  | 2025-12-31 | 2025-12-31 |  | 230 | 230 | 3270 | 3270 | 327 | 0% | 25% | 10% | Red | [Backlog] with no work done; efforts burnt; 59 days past due start date;
DSFFLOW-937 | Backlog | Core Network | IMS | 16 | 16 |  | 2025-05-06 | 2025-05-06 |  | 2025-06-29 | 2025-06-29 |  | 54 | 54 | 176 | 176 | 106 | 0% | 125% | 61% | Red | [Backlog] with no work done; efforts burnt; 68 days past due start date;
DSFFLOW-845 | Backlog | Core Network | MSS | 22 | 22 |  | 2025-02-24 | 2025-02-24 |  | 2025-06-30 | 2025-06-30 |  | 126 | 126 | 674 | 674 |  | 0% | 111% |  | Amber | [Backlog] with no work done; 139 days past due start date;
DSFFLOW-626 | Backlog | Core Network | EPC | 34 | 34 |  | 2025-04-29 | 2025-04-29 | 2025-04-29 | 2025-08-31 | 2025-08-31 | 2025-09-15 | 124 | 124 | 2496 | 2496 | 1084 | 0% | 113% | 44% | Red | [Backlog] with no work done; efforts burnt; 75 days past due start date;
DSFFLOW-340 | Backlog | Core Network | UDM | 17 | 17 |  | 2025-03-04 | 2025-03-04 |  | 2025-06-30 | 2025-06-30 |  | 118 | 118 | 264 | 264 | 44 | 0% | 111% | 17% | Red | [Backlog] with no work done; efforts burnt; 131 days past due start date;
DSFFLOW-356 | Backlog | Core Network | UDM | 13 | 13 |  | 2024-12-18 | 2024-12-18 |  | 2026-07-31 | 2026-07-31 |  | 590 | 590 | 222 | 222 |  | 0% | 35% |  | Amber | [Backlog] with no work done; 207 days past due start date;
DSFFLOW-371 | Backlog | Core Network | MSS | 28 | 28 |  | 2025-03-24 | 2025-03-24 |  | 2025-07-25 | 2025-07-25 |  | 123 | 123 | 700 | 700 |  | 0% | 90% |  | Amber | [Backlog] with no work done; 111 days past due start date;
DSFFLOW-894 | Backlog | Core Network | UDM | 23 | 23 |  | 2025-05-06 | 2025-05-06 |  | 2025-12-31 | 2025-12-31 |  | 239 | 239 | 928 | 928 | 320 | 0% | 29% | 35% | Red | [Backlog] with no work done; efforts burnt; 68 days past due start date;
DSFFLOW-1474 | Backlog | Core Network | IMS | 54 | 54 | 5 | 2025-03-24 | 2025-03-24 |  | 2025-06-30 | 2026-02-02 |  | 98 | 315 | 430 | 430 | 72 | 9% | 35% | 17% | Red | [Backlog] with work being done; efforts burnt; 111 days past due start date;
DSFFLOW-879 | Descoped | Network Management | Element Management & Reporting | 12 | 12 |  | 2025-05-09 | 2025-05-09 |  | 2025-06-29 | 2025-06-29 |  | 51 | 51 |  | 0 | 0.2